## Executive Financial Summary
Total Spend
$225,978,445.81
Total Budget
$221,594,332.00
Variance
$4,384,113.81
Variance %
2%
Margin ($)
$12,636,887.55
Margin (%)
5%
This shape represents a slicer. Slicers are supported in Excel 2010 or later. If the shape was modified in an earlier version of Excel, or if the workbook was saved in Excel 2003 or earlier, the slicer cannot be used.

## Materials Dashboard
Total Material Spend
$3,385,598,274.40
PO Count
1100
Avg Unit Price
$3,077,816.61

## Labor Analysis Dashboard
Total Labor Cost
$2,357,961.71
Total Hours
28976
OT Hours
796

## Program_Costs
Month | Program | Planned_Budget | Actual_Cost | Forecast_EAC | Revenue_Recognized
2024-01-01 | THAAD | 4971958 | 5317416.84 | 4923122.57 | 5553446.64
2024-02-01 | THAAD | 5107892 | 4972036.35 | 5042303.59 | 5152394.72
2024-03-01 | THAAD | 5125203 | 4978776.07 | 5338399.82 | 5168571.12
2024-04-01 | THAAD | 5194027 | 5665555.87 | 5038651.13 | 5967063.04
2024-05-01 | THAAD | 5264176 | 5241204.91 | 5410115.84 | 5605251.19
2024-06-01 | THAAD | 5256730 | 5309187.67 | 5126012.07 | 6024545.48
2024-07-01 | THAAD | 5215725 | 5025825.49 | 5414039.7 | 5514947.49
2024-08-01 | THAAD | 5231551 | 5336257.53 | 5569474.9 | 5765410.54
2024-09-01 | THAAD | 5506840 | 5285232.31 | 5916424.49 | 6304477.17
2024-10-01 | THAAD | 5505041 | 5548049 | 5349558.21 | 5695703
2024-11-01 | THAAD | 5601995 | 5691755.06 | 5509137.48 | 6018091.79
2024-12-01 | THAAD | 5506530 | 5982283.51 | 5498081.87 | 6053759.83
2024-01-01 | Javelin | 3631601 | 3681620.42 | 3605720.7 | 3940850.16
2024-02-01 | Javelin | 3656836 | 4005836 | 3858929.62 | 4172175.03
2024-03-01 | Javelin | 3643165 | 3967402.42 | 3825322.96 | 3821611.28
2024-04-01 | Javelin | 3495397 | 3423382.84 | 3407924.7 | 3665970.8
2024-05-01 | Javelin | 3513247 | 3731412.67 | 3616417.48 | 3822457.27
2024-06-01 | Javelin | 3719776 | 3690539.22 | 3830240.59 | 3798406.98
2024-07-01 | Javelin | 3608984 | 3962783.67 | 3807286.57 | 3716558.26
2024-08-01 | Javelin | 3719375 | 3541261.47 | 3689146.39 | 4116237.12
2024-09-01 | Javelin | 3691858 | 3934378.19 | 3611172.12 | 3890368.69
2024-10-01 | Javelin | 3769488 | 4098353.03 | 4008866.48 | 4023617.84
2024-11-01 | Javelin | 3997366 | 4198538.19 | 4170257.91 | 4351911.05
2024-12-01 | Javelin | 4008109 | 4341110.36 | 4096061.51 | 4080011.02
2024-01-01 | PAC-3 | 4208338 | 4478167.19 | 4341912.72 | 4695011.57
2024-02-01 | PAC-3 | 4182982 | 3999202.85 | 4384488.45 | 4252560.15
2024-03-01 | PAC-3 | 4157419 | 4016830.53 | 4047069.5 | 4554292.71
2024-04-01 | PAC-3 | 4283059 | 4430787.43 | 4482250.24 | 4372573.73
2024-05-01 | PAC-3 | 4420982 | 4472077.23 | 4655783.12 | 4572708.89
2024-06-01 | PAC-3 | 4303585 | 4491449.86 | 4314428.77 | 4371685.53
2024-07-01 | PAC-3 | 4545307 | 4445244.38 | 4855212.8 | 4913028.41
2024-08-01 | PAC-3 | 4632249 | 4485467.82 | 4674832.16 | 5262347.27
2024-09-01 | PAC-3 | 4547152 | 4475262.77 | 4624371.08 | 5105097.62
2024-10-01 | PAC-3 | 4483016 | 4463816.09 | 4429722.55 | 4842165.71
2024-11-01 | PAC-3 | 4735892 | 4990992.74 | 4734165.09 | 4909314.82
2024-12-01 | PAC-3 | 4573087 | 4700303.85 | 4789540.74 | 4822523.47
2024-01-01 | HIMARS | 4689353 | 5131873.62 | 4678548.98 | 5039119.07
2024-02-01 | HIMARS | 4765172 | 4730510.49 | 4641551.83 | 5200873.83
2024-03-01 | HIMARS | 4858859 | 4653435.25 | 4862022.66 | 5520829.38
2024-04-01 | HIMARS | 5051426 | 5314634.68 | 5194900.66 | 5390717.53
2024-05-01 | HIMARS | 4999381 | 4930930.93 | 5219028.36 | 5570525
2024-06-01 | HIMARS | 5177486 | 5542348.43 | 5290008.66 | 5941234.93
2024-07-01 | HIMARS | 5027045 | 5179697.27 | 4926161.63 | 5656910.49
2024-08-01 | HIMARS | 5072202 | 4960500.83 | 4942786.11 | 5521771.26
2024-09-01 | HIMARS | 5146547 | 4902025.16 | 5282056.8 | 5321397.67
2024-10-01 | HIMARS | 5215983 | 5030432.14 | 5599136.38 | 5527042.34
2024-11-01 | HIMARS | 5349686 | 5833883.4 | 5270121.75 | 5623375.68
2024-12-01 | HIMARS | 5225254 | 5388371.78 | 5468417.9 | 5404388.79

## Material_Purchases
PO_Number | PO_Line | Program | Material_Category | Vendor | GL_Account | Cost_Code | Quantity | Unit_Price | Extended_Price | Order_Date | Delivery_Date
PO100001 | 5 | HIMARS | Propulsion | RayTech Components | 5400 | CC671 | 113 | 12282.15 | 1387882.95 | 2024-10-30 | 2024-11-15
PO100002 | 1 | THAAD | Guidance | RayTech Components | 5100 | CC198 | 147 | 36366.3 | 5345846.1 | 2024-05-10 | 2024-06-03
PO100003 | 1 | HIMARS | Composites | Precision Metals Inc | 5100 | CC519 | 166 | 33532.17 | 5566340.22 | 2024-09-10 | 2024-10-19
PO100004 | 5 | PAC-3 | Electronics | DefenseCo Supplies | 5200 | CC995 | 110 | 27549.51 | 3030446.1 | 2024-11-05 | 2024-12-14
PO100005 | 1 | THAAD | Composites | RayTech Components | 5400 | CC900 | 142 | 16438.63 | 2334285.46 | 2024-05-14 | 2024-05-21
PO100006 | 5 | HIMARS | Electronics | Orbital Systems | 5300 | CC982 | 214 | 13443.82 | 2876977.48 | 2024-08-25 | 2024-09-28
PO100007 | 5 | PAC-3 | Hardware | Precision Metals Inc | 5300 | CC325 | 21 | 25256.2 | 530380.2 | 2024-10-10 | 2024-11-16
PO100008 | 5 | HIMARS | Warhead | Precision Metals Inc | 5400 | CC646 | 192 | 32362.25 | 6213552 | 2024-01-17 | 2024-02-18
PO100009 | 3 | Javelin | Warhead | Precision Metals Inc | 5400 | CC844 | 37 | 46433.85 | 1718052.45 | 2024-10-28 | 2024-12-02
PO100010 | 2 | HIMARS | Electronics | Orbital Systems | 5300 | CC352 | 213 | 9747.82 | 2076285.66 | 2024-06-09 | 2024-06-16
PO100011 | 2 | THAAD | Propulsion | AeroDynamics Ltd | 5300 | CC971 | 174 | 5084.53 | 884708.22 | 2024-10-14 | 2024-11-09
PO100012 | 5 | PAC-3 | Guidance | AeroDynamics Ltd | 5200 | CC884 | 104 | 34926.53 | 3632359.12 | 2024-10-25 | 2024-12-07
PO100013 | 5 | Javelin | Propulsion | Precision Metals Inc | 5200 | CC507 | 13 | 4309.31 | 56021.03 | 2024-11-08 | 2024-12-18
PO100014 | 3 | HIMARS | Electronics | Orbital Systems | 5300 | CC570 | 143 | 18935.25 | 2707740.75 | 2024-11-17 | 2024-12-23
PO100015 | 3 | THAAD | Propulsion | DefenseCo Supplies | 5200 | CC413 | 58 | 1767.39 | 102508.62 | 2024-06-28 | 2024-07-08
PO100016 | 4 | HIMARS | Warhead | RayTech Components | 5400 | CC152 | 60 | 10987.1 | 659226 | 2024-01-05 | 2024-02-17
PO100017 | 5 | Javelin | Warhead | Orbital Systems | 5200 | CC146 | 99 | 31962.14 | 3164251.86 | 2024-11-03 | 2024-11-23
PO100018 | 2 | Javelin | Composites | AeroDynamics Ltd | 5200 | CC758 | 145 | 20091.34 | 2913244.3 | 2024-10-01 | 2024-11-02
PO100019 | 2 | PAC-3 | Propulsion | DefenseCo Supplies | 5200 | CC216 | 62 | 41840.01 | 2594080.62 | 2024-05-08 | 2024-05-13
PO100020 | 5 | HIMARS | Hardware | RayTech Components | 5400 | CC336 | 117 | 32003.96 | 3744463.32 | 2024-07-07 | 2024-08-19
PO100021 | 4 | Javelin | Warhead | Precision Metals Inc | 5400 | CC253 | 144 | 8142.66 | 1172543.04 | 2024-03-26 | 2024-04-28
PO100022 | 4 | THAAD | Electronics | Orbital Systems | 5100 | CC303 | 144 | 5117.25 | 736884 | 2024-12-06 | 2025-01-18
PO100023 | 4 | THAAD | Hardware | DefenseCo Supplies | 5300 | CC861 | 10 | 47470 | 474700 | 2024-04-09 | 2024-05-17
PO100024 | 2 | PAC-3 | Propulsion | AeroDynamics Ltd | 5300 | CC541 | 96 | 42860.37 | 4114595.52 | 2024-11-20 | 2024-11-28
PO100025 | 5 | THAAD | Composites | Precision Metals Inc | 5400 | CC763 | 140 | 19561.45 | 2738603 | 2024-02-02 | 2024-03-10
PO100026 | 5 | PAC-3 | Guidance | DefenseCo Supplies | 5400 | CC934 | 65 | 48069.23 | 3124499.95 | 2024-11-25 | 2024-12-28
PO100027 | 5 | HIMARS | Hardware | AeroDynamics Ltd | 5100 | CC598 | 242 | 34229.59 | 8283560.78 | 2024-12-02 | 2025-01-01
PO100028 | 5 | Javelin | Propulsion | AeroDynamics Ltd | 5200 | CC517 | 115 | 14272.28 | 1641312.2 | 2024-07-14 | 2024-07-29
PO100029 | 1 | HIMARS | Composites | RayTech Components | 5100 | CC860 | 164 | 9077.62 | 1488729.68 | 2024-07-10 | 2024-08-18
PO100030 | 4 | PAC-3 | Composites | AeroDynamics Ltd | 5100 | CC195 | 152 | 43389.05 | 6595135.6 | 2024-08-11 | 2024-09-21
PO100031 | 1 | THAAD | Warhead | RayTech Components | 5300 | CC972 | 30 | 45152.01 | 1354560.3 | 2024-03-02 | 2024-03-26
PO100032 | 4 | Javelin | Warhead | Precision Metals Inc | 5300 | CC276 | 100 | 789.17 | 78917 | 2024-08-20 | 2024-09-12
PO100033 | 4 | THAAD | Composites | Orbital Systems | 5300 | CC605 | 111 | 4393.4 | 487667.4 | 2024-03-09 | 2024-04-17
PO100034 | 5 | THAAD | Composites | Precision Metals Inc | 5100 | CC583 | 53 | 39631.06 | 2100446.18 | 2024-02-26 | 2024-04-09
PO100035 | 5 | THAAD | Propulsion | AeroDynamics Ltd | 5300 | CC497 | 223 | 3029.59 | 675598.57 | 2024-06-11 | 2024-07-08
PO100036 | 5 | PAC-3 | Guidance | AeroDynamics Ltd | 5300 | CC687 | 9 | 38135.15 | 343216.35 | 2024-09-09 | 2024-10-21
PO100037 | 3 | HIMARS | Propulsion | RayTech Components | 5200 | CC894 | 122 | 7543.59 | 920317.98 | 2024-01-29 | 2024-03-10
PO100038 | 4 | HIMARS | Warhead | RayTech Components | 5200 | CC599 | 145 | 47375.62 | 6869464.9 | 2024-08-04 | 2024-08-12
PO100039 | 3 | Javelin | Composites | Precision Metals Inc | 5100 | CC975 | 182 | 35327.95 | 6429686.9 | 2024-07-20 | 2024-08-19
PO100040 | 4 | PAC-3 | Hardware | Precision Metals Inc | 5100 | CC752 | 242 | 23565.87 | 5702940.54 | 2024-02-27 | 2024-03-22
PO100041 | 1 | HIMARS | Warhead | RayTech Components | 5300 | CC100 | 131 | 29272.6 | 3834710.6 | 2024-07-08 | 2024-08-06
PO100042 | 5 | Javelin | Warhead | AeroDynamics Ltd | 5400 | CC784 | 160 | 27911.25 | 4465800 | 2024-10-29 | 2024-11-23
PO100043 | 1 | PAC-3 | Composites | DefenseCo Supplies | 5400 | CC326 | 147 | 48472.8 | 7125501.6 | 2024-02-16 | 2024-03-05
PO100044 | 4 | THAAD | Hardware | Precision Metals Inc | 5400 | CC570 | 185 | 45783.9 | 8470021.5 | 2024-11-25 | 2024-12-31
PO100045 | 4 | HIMARS | Composites | DefenseCo Supplies | 5400 | CC221 | 92 | 32430.71 | 2983625.32 | 2024-05-15 | 2024-06-16
PO100046 | 4 | THAAD | Electronics | Orbital Systems | 5400 | CC601 | 191 | 26920.79 | 5141870.89 | 2024-07-30 | 2024-08-16
PO100047 | 1 | HIMARS | Warhead | DefenseCo Supplies | 5200 | CC646 | 134 | 47502.55 | 6365341.7 | 2024-09-12 | 2024-09-21
PO100048 | 2 | Javelin | Propulsion | AeroDynamics Ltd | 5300 | CC976 | 5 | 1561.76 | 7808.8 | 2024-10-15 | 2024-10-20
PO100049 | 1 | HIMARS | Electronics | Precision Metals Inc | 5100 | CC381 | 63 | 19801.23 | 1247477.49 | 2024-11-10 | 2024-12-11
PO100050 | 4 | THAAD | Electronics | AeroDynamics Ltd | 5100 | CC198 | 129 | 930.18 | 119993.22 | 2024-11-06 | 2024-11-16
PO100051 | 2 | THAAD | Warhead | DefenseCo Supplies | 5200 | CC870 | 181 | 29361.19 | 5314375.39 | 2024-02-22 | 2024-04-03
PO100052 | 4 | Javelin | Guidance | RayTech Components | 5100 | CC177 | 201 | 6675.68 | 1341811.68 | 2024-02-20 | 2024-03-08
PO100053 | 2 | Javelin | Electronics | RayTech Components | 5400 | CC899 | 34 | 18068.6 | 614332.4 | 2024-03-12 | 2024-04-24
PO100054 | 3 | Javelin | Propulsion | Precision Metals Inc | 5300 | CC405 | 12 | 40865.19 | 490382.28 | 2024-08-23 | 2024-09-01
PO100055 | 2 | THAAD | Electronics | DefenseCo Supplies | 5100 | CC677 | 75 | 10844.97 | 813372.75 | 2024-07-10 | 2024-08-17
PO100056 | 4 | Javelin | Propulsion | Precision Metals Inc | 5300 | CC546 | 226 | 17575.71 | 3972110.46 | 2024-06-14 | 2024-07-21
PO100057 | 2 | Javelin | Propulsion | Precision Metals Inc | 5100 | CC232 | 29 | 7566.91 | 219440.39 | 2024-07-02 | 2024-07-23
PO100058 | 3 | THAAD | Composites | Orbital Systems | 5400 | CC168 | 34 | 31135.08 | 1058592.72 | 2024-07-23 | 2024-08-07
PO100059 | 3 | PAC-3 | Electronics | Precision Metals Inc | 5200 | CC619 | 132 | 9298.53 | 1227405.96 | 2024-07-02 | 2024-07-31
PO100060 | 5 | HIMARS | Guidance | Precision Metals Inc | 5100 | CC771 | 178 | 30196.29 | 5374939.62 | 2024-02-20 | 2024-03-14
PO100061 | 1 | THAAD | Propulsion | Orbital Systems | 5200 | CC928 | 22 | 4662.95 | 102584.9 | 2024-01-01 | 2024-01-10
PO100062 | 1 | HIMARS | Propulsion | AeroDynamics Ltd | 5100 | CC177 | 218 | 34597.14 | 7542176.52 | 2024-03-13 | 2024-04-12
PO100063 | 1 | PAC-3 | Electronics | Precision Metals Inc | 5300 | CC147 | 61 | 379.1 | 23125.1 | 2024-10-18 | 2024-10-23
PO100064 | 4 | PAC-3 | Warhead | Orbital Systems | 5300 | CC402 | 127 | 46221.08 | 5870077.16 | 2024-01-14 | 2024-02-13
PO100065 | 3 | PAC-3 | Hardware | AeroDynamics Ltd | 5100 | CC765 | 14 | 7600.02 | 106400.28 | 2024-01-07 | 2024-01-14
PO100066 | 5 | PAC-3 | Composites | DefenseCo Supplies | 5200 | CC605 | 38 | 26747.71 | 1016412.98 | 2024-01-15 | 2024-02-13
PO100067 | 1 | HIMARS | Propulsion | RayTech Components | 5100 | CC330 | 86 | 16542.99 | 1422697.14 | 2024-10-26 | 2024-11-24
PO100068 | 2 | THAAD | Composites | RayTech Components | 5400 | CC493 | 67 | 32528.94 | 2179438.98 | 2024-05-25 | 2024-07-04
PO100069 | 2 | PAC-3 | Electronics | Orbital Systems | 5300 | CC653 | 169 | 17037.98 | 2879418.62 | 2024-06-28 | 2024-07-28
PO100070 | 4 | PAC-3 | Guidance | DefenseCo Supplies | 5200 | CC840 | 121 | 12052.03 | 1458295.63 | 2024-05-29 | 2024-06-23
PO100071 | 2 | Javelin | Guidance | RayTech Components | 5300 | CC998 | 243 | 1157.56 | 281287.08 | 2024-08-16 | 2024-09-25
PO100072 | 3 | HIMARS | Composites | Precision Metals Inc | 5400 | CC946 | 134 | 48759.59 | 6533785.06 | 2024-04-03 | 2024-05-15
PO100073 | 2 | Javelin | Electronics | AeroDynamics Ltd | 5300 | CC814 | 136 | 23961.82 | 3258807.52 | 2024-06-21 | 2024-06-30
PO100074 | 2 | Javelin | Composites | Precision Metals Inc | 5400 | CC324 | 20 | 12309.88 | 246197.6 | 2024-02-16 | 2024-02-21
PO100075 | 2 | Javelin | Hardware | DefenseCo Supplies | 5200 | CC238 | 100 | 16201.95 | 1620195 | 2024-09-15 | 2024-10-22
PO100076 | 4 | HIMARS | Propulsion | DefenseCo Supplies | 5300 | CC749 | 172 | 10286.09 | 1769207.48 | 2024-06-16 | 2024-06-22
PO100077 | 1 | THAAD | Warhead | RayTech Components | 5100 | CC876 | 203 | 23790.02 | 4829374.06 | 2024-02-07 | 2024-03-17
PO100078 | 4 | THAAD | Hardware | Orbital Systems | 5400 | CC433 | 117 | 36610.66 | 4283447.22 | 2024-05-16 | 2024-06-23
PO100079 | 3 | PAC-3 | Guidance | RayTech Components | 5400 | CC419 | 150 | 2642.71 | 396406.5 | 2024-12-14 | 2024-12-26
PO100080 | 2 | THAAD | Warhead | Orbital Systems | 5200 | CC390 | 213 | 9523.65 | 2028537.45 | 2024-12-04 | 2024-12-22
PO100081 | 3 | Javelin | Composites | RayTech Components | 5100 | CC141 | 89 | 34228.36 | 3046324.04 | 2024-11-23 | 2025-01-05
PO100082 | 2 | THAAD | Hardware | RayTech Components | 5300 | CC674 | 143 | 28979.94 | 4144131.42 | 2024-05-24 | 2024-06-30
PO100083 | 2 | Javelin | Warhead | Precision Metals Inc | 5300 | CC297 | 134 | 16807.59 | 2252217.06 | 2024-06-27 | 2024-07-09
PO100084 | 1 | HIMARS | Composites | DefenseCo Supplies | 5100 | CC577 | 231 | 28764.25 | 6644541.75 | 2024-06-05 | 2024-07-17
PO100085 | 3 | THAAD | Warhead | DefenseCo Supplies | 5300 | CC388 | 196 | 28602.01 | 5605993.96 | 2024-01-10 | 2024-01-19
PO100086 | 5 | Javelin | Electronics | DefenseCo Supplies | 5300 | CC914 | 228 | 22985.76 | 5240753.28 | 2024-07-02 | 2024-07-21
PO100087 | 4 | HIMARS | Warhead | DefenseCo Supplies | 5300 | CC423 | 76 | 38651.13 | 2937485.88 | 2024-04-04 | 2024-05-14
PO100088 | 2 | Javelin | Guidance | Precision Metals Inc | 5100 | CC759 | 11 | 47963.97 | 527603.67 | 2024-12-25 | 2025-02-05
PO100089 | 4 | Javelin | Guidance | Orbital Systems | 5200 | CC240 | 104 | 25417.96 | 2643467.84 | 2024-04-20 | 2024-06-03
PO100090 | 2 | PAC-3 | Composites | Orbital Systems | 5400 | CC423 | 133 | 46144.34 | 6137197.22 | 2024-11-23 | 2024-12-25
PO100091 | 1 | THAAD | Hardware | Precision Metals Inc | 5100 | CC561 | 40 | 42061.87 | 1682474.8 | 2024-09-23 | 2024-10-20
PO100092 | 3 | Javelin | Warhead | DefenseCo Supplies | 5200 | CC721 | 164 | 6451.97 | 1058123.08 | 2024-11-08 | 2024-11-13
PO100093 | 1 | HIMARS | Warhead | RayTech Components | 5100 | CC236 | 202 | 40191.96 | 8118775.92 | 2024-04-26 | 2024-05-26
PO100094 | 2 | PAC-3 | Composites | RayTech Components | 5200 | CC174 | 38 | 17480.71 | 664266.98 | 2024-07-28 | 2024-08-28
PO100095 | 4 | PAC-3 | Electronics | Precision Metals Inc | 5300 | CC975 | 179 | 12599.27 | 2255269.33 | 2024-01-25 | 2024-02-05
PO100096 | 2 | Javelin | Warhead | RayTech Components | 5100 | CC384 | 63 | 14059.96 | 885777.48 | 2024-06-02 | 2024-07-04
PO100097 | 5 | THAAD | Electronics | RayTech Components | 5400 | CC460 | 177 | 27975.94 | 4951741.38 | 2024-12-07 | 2025-01-08
PO100098 | 5 | HIMARS | Electronics | RayTech Components | 5400 | CC240 | 222 | 37560.53 | 8338437.66 | 2024-07-29 | 2024-09-03
PO100099 | 3 | THAAD | Warhead | DefenseCo Supplies | 5200 | CC243 | 168 | 29475.82 | 4951937.76 | 2024-09-13 | 2024-10-01
PO100100 | 1 | PAC-3 | Propulsion | AeroDynamics Ltd | 5200 | CC212 | 114 | 24976.34 | 2847302.76 | 2024-11-14 | 2024-11-22
PO100101 | 4 | HIMARS | Warhead | Precision Metals Inc | 5400 | CC877 | 202 | 44897.16 | 9069226.32 | 2024-06-10 | 2024-07-17
PO100102 | 1 | HIMARS | Propulsion | DefenseCo Supplies | 5400 | CC932 | 57 | 11293.12 | 643707.84 | 2024-09-11 | 2024-09-23
PO100103 | 3 | PAC-3 | Warhead | Precision Metals Inc | 5300 | CC708 | 92 | 12099.59 | 1113162.28 | 2024-10-17 | 2024-11-22
PO100104 | 2 | HIMARS | Composites | Orbital Systems | 5100 | CC281 | 213 | 20468.02 | 4359688.26 | 2024-11-06 | 2024-11-28
PO100105 | 2 | PAC-3 | Electronics | DefenseCo Supplies | 5300 | CC723 | 125 | 43853.09 | 5481636.25 | 2024-10-11 | 2024-11-02
PO100106 | 4 | THAAD | Warhead | Orbital Systems | 5300 | CC845 | 130 | 18312.2 | 2380586 | 2024-04-28 | 2024-05-14
PO100107 | 1 | THAAD | Warhead | RayTech Components | 5200 | CC152 | 172 | 11170.65 | 1921351.8 | 2024-12-07 | 2025-01-04
PO100108 | 1 | Javelin | Hardware | Precision Metals Inc | 5200 | CC826 | 128 | 9309.83 | 1191658.24 | 2024-04-24 | 2024-05-15
PO100109 | 2 | HIMARS | Propulsion | DefenseCo Supplies | 5100 | CC458 | 201 | 7182.96 | 1443774.96 | 2024-08-22 | 2024-08-30
PO100110 | 2 | Javelin | Warhead | DefenseCo Supplies | 5200 | CC826 | 37 | 1164.94 | 43102.78 | 2024-05-25 | 2024-06-19
PO100111 | 5 | HIMARS | Electronics | AeroDynamics Ltd | 5100 | CC776 | 153 | 24998.88 | 3824828.64 | 2024-03-16 | 2024-04-12
PO100112 | 4 | Javelin | Hardware | DefenseCo Supplies | 5300 | CC924 | 31 | 43726.03 | 1355506.93 | 2024-06-16 | 2024-07-24
PO100113 | 4 | THAAD | Electronics | DefenseCo Supplies | 5300 | CC784 | 145 | 21083.83 | 3057155.35 | 2024-07-08 | 2024-07-14
PO100114 | 3 | Javelin | Guidance | RayTech Components | 5300 | CC792 | 36 | 38606.55 | 1389835.8 | 2024-01-29 | 2024-02-23
PO100115 | 5 | HIMARS | Guidance | Orbital Systems | 5100 | CC286 | 39 | 30617.63 | 1194087.57 | 2024-11-05 | 2024-12-13
PO100116 | 3 | HIMARS | Electronics | AeroDynamics Ltd | 5400 | CC850 | 148 | 8310.19 | 1229908.12 | 2024-08-31 | 2024-09-21
PO100117 | 1 | THAAD | Guidance | AeroDynamics Ltd | 5100 | CC253 | 194 | 5553.26 | 1077332.44 | 2024-07-19 | 2024-09-01
PO100118 | 2 | THAAD | Electronics | DefenseCo Supplies | 5300 | CC715 | 42 | 23119.16 | 971004.72 | 2024-10-17 | 2024-10-24
PO100119 | 4 | THAAD | Composites | Orbital Systems | 5300 | CC577 | 102 | 29613.98 | 3020625.96 | 2024-10-01 | 2024-11-11
PO100120 | 3 | PAC-3 | Guidance | RayTech Components | 5100 | CC116 | 74 | 34605.37 | 2560797.38 | 2024-10-29 | 2024-11-14
PO100121 | 2 | HIMARS | Warhead | RayTech Components | 5300 | CC584 | 118 | 31952.27 | 3770367.86 | 2024-07-18 | 2024-08-16
PO100122 | 1 | THAAD | Composites | Precision Metals Inc | 5200 | CC588 | 109 | 33578.39 | 3660044.51 | 2024-10-14 | 2024-10-28
PO100123 | 1 | PAC-3 | Propulsion | DefenseCo Supplies | 5200 | CC349 | 135 | 1938.81 | 261739.35 | 2024-04-26 | 2024-05-07
PO100124 | 3 | PAC-3 | Propulsion | Precision Metals Inc | 5300 | CC576 | 82 | 37316.96 | 3059990.72 | 2024-04-12 | 2024-05-03
PO100125 | 4 | HIMARS | Composites | DefenseCo Supplies | 5200 | CC230 | 37 | 26630.69 | 985335.53 | 2024-07-01 | 2024-07-28
PO100126 | 3 | PAC-3 | Electronics | Orbital Systems | 5100 | CC496 | 210 | 26128.36 | 5486955.6 | 2024-04-17 | 2024-04-23
PO100127 | 3 | Javelin | Propulsion | Precision Metals Inc | 5300 | CC880 | 141 | 19352.2 | 2728660.2 | 2024-04-05 | 2024-05-14
PO100128 | 4 | PAC-3 | Hardware | Orbital Systems | 5100 | CC576 | 62 | 24123.81 | 1495676.22 | 2024-07-03 | 2024-07-23
PO100129 | 5 | PAC-3 | Electronics | AeroDynamics Ltd | 5200 | CC458 | 84 | 36944.72 | 3103356.48 | 2024-06-25 | 2024-07-02
PO100130 | 1 | Javelin | Hardware | AeroDynamics Ltd | 5400 | CC245 | 190 | 29558.15 | 5616048.5 | 2024-07-11 | 2024-07-30
PO100131 | 3 | PAC-3 | Electronics | RayTech Components | 5400 | CC239 | 187 | 47510.57 | 8884476.59 | 2024-03-01 | 2024-04-11
PO100132 | 3 | HIMARS | Hardware | Precision Metals Inc | 5200 | CC944 | 226 | 8559.94 | 1934546.44 | 2024-02-21 | 2024-02-29
PO100133 | 1 | HIMARS | Composites | DefenseCo Supplies | 5300 | CC409 | 117 | 41574.47 | 4864212.99 | 2024-11-25 | 2025-01-02
PO100134 | 1 | Javelin | Electronics | RayTech Components | 5200 | CC358 | 120 | 17668.73 | 2120247.6 | 2024-09-17 | 2024-10-14
PO100135 | 1 | THAAD | Guidance | Orbital Systems | 5200 | CC852 | 61 | 13196.61 | 804993.21 | 2024-06-26 | 2024-07-18
PO100136 | 4 | HIMARS | Guidance | Precision Metals Inc | 5200 | CC880 | 120 | 37456.61 | 4494793.2 | 2024-03-29 | 2024-04-11
PO100137 | 3 | Javelin | Warhead | AeroDynamics Ltd | 5300 | CC716 | 184 | 13463.6 | 2477302.4 | 2024-01-29 | 2024-02-11
PO100138 | 3 | THAAD | Propulsion | Orbital Systems | 5200 | CC620 | 207 | 32848.29 | 6799596.03 | 2024-09-17 | 2024-10-02
PO100139 | 4 | Javelin | Composites | Precision Metals Inc | 5100 | CC275 | 90 | 26746.98 | 2407228.2 | 2024-02-06 | 2024-02-23
PO100140 | 2 | THAAD | Warhead | RayTech Components | 5200 | CC139 | 45 | 24159.18 | 1087163.1 | 2024-12-14 | 2024-12-21
PO100141 | 4 | HIMARS | Guidance | DefenseCo Supplies | 5100 | CC388 | 6 | 26182.7 | 157096.2 | 2024-12-01 | 2025-01-14
PO100142 | 3 | THAAD | Guidance | Precision Metals Inc | 5400 | CC780 | 13 | 41891.41 | 544588.33 | 2024-12-10 | 2025-01-19
PO100143 | 2 | Javelin | Composites | DefenseCo Supplies | 5300 | CC656 | 58 | 23407.13 | 1357613.54 | 2024-01-31 | 2024-02-27
PO100144 | 5 | Javelin | Guidance | DefenseCo Supplies | 5200 | CC650 | 159 | 305.73 | 48611.07 | 2024-09-14 | 2024-10-02
PO100145 | 2 | THAAD | Composites | AeroDynamics Ltd | 5400 | CC624 | 46 | 16490.07 | 758543.22 | 2024-08-20 | 2024-09-10
PO100146 | 2 | HIMARS | Warhead | Precision Metals Inc | 5400 | CC425 | 211 | 38111.14 | 8041450.54 | 2024-03-14 | 2024-04-19
PO100147 | 4 | PAC-3 | Composites | Orbital Systems | 5300 | CC321 | 37 | 5349.86 | 197944.82 | 2024-07-14 | 2024-08-07
PO100148 | 2 | Javelin | Composites | Precision Metals Inc | 5400 | CC116 | 12 | 3600.69 | 43208.28 | 2024-07-11 | 2024-08-06
PO100149 | 3 | HIMARS | Guidance | AeroDynamics Ltd | 5200 | CC369 | 192 | 33883.6 | 6505651.2 | 2024-07-22 | 2024-08-31
PO100150 | 3 | PAC-3 | Composites | DefenseCo Supplies | 5400 | CC106 | 29 | 1350.65 | 39168.85 | 2024-05-13 | 2024-06-01
PO100151 | 1 | PAC-3 | Propulsion | AeroDynamics Ltd | 5200 | CC529 | 226 | 49856.94 | 11267668.44 | 2024-04-08 | 2024-04-25
PO100152 | 3 | PAC-3 | Warhead | DefenseCo Supplies | 5300 | CC983 | 32 | 4348.46 | 139150.72 | 2024-03-24 | 2024-04-19
PO100153 | 5 | PAC-3 | Guidance | RayTech Components | 5200 | CC847 | 184 | 21758.66 | 4003593.44 | 2024-01-21 | 2024-02-10
PO100154 | 2 | PAC-3 | Composites | Precision Metals Inc | 5100 | CC552 | 131 | 15769.61 | 2065818.91 | 2024-02-27 | 2024-04-09
PO100155 | 4 | THAAD | Guidance | RayTech Components | 5100 | CC891 | 12 | 28246.83 | 338961.96 | 2024-07-26 | 2024-08-26
PO100156 | 3 | Javelin | Electronics | RayTech Components | 5100 | CC408 | 8 | 38603.36 | 308826.88 | 2024-06-22 | 2024-07-03
PO100157 | 1 | THAAD | Composites | DefenseCo Supplies | 5400 | CC927 | 122 | 30928.35 | 3773258.7 | 2024-02-15 | 2024-03-05
PO100158 | 5 | Javelin | Hardware | RayTech Components | 5200 | CC335 | 84 | 21657.72 | 1819248.48 | 2024-06-14 | 2024-07-10
PO100159 | 2 | THAAD | Propulsion | Precision Metals Inc | 5400 | CC816 | 209 | 828.12 | 173077.08 | 2024-09-30 | 2024-11-03
PO100160 | 3 | Javelin | Hardware | Precision Metals Inc | 5100 | CC828 | 33 | 47644.27 | 1572260.91 | 2024-09-23 | 2024-10-19
PO100161 | 4 | HIMARS | Electronics | RayTech Components | 5400 | CC988 | 46 | 7339.15 | 337600.9 | 2024-03-20 | 2024-04-15
PO100162 | 1 | HIMARS | Electronics | AeroDynamics Ltd | 5400 | CC341 | 97 | 26006.15 | 2522596.55 | 2024-10-15 | 2024-11-01
PO100163 | 2 | THAAD | Composites | AeroDynamics Ltd | 5200 | CC202 | 194 | 48878.95 | 9482516.3 | 2024-03-30 | 2024-04-18
PO100164 | 1 | Javelin | Composites | RayTech Components | 5400 | CC416 | 195 | 44837.01 | 8743216.95 | 2024-01-09 | 2024-01-19
PO100165 | 3 | PAC-3 | Electronics | AeroDynamics Ltd | 5400 | CC363 | 72 | 35775.82 | 2575859.04 | 2024-11-13 | 2024-12-07
PO100166 | 3 | PAC-3 | Guidance | Orbital Systems | 5400 | CC489 | 58 | 39245.67 | 2276248.86 | 2024-01-03 | 2024-01-21
PO100167 | 4 | Javelin | Hardware | Orbital Systems | 5300 | CC623 | 141 | 24094.13 | 3397272.33 | 2024-08-30 | 2024-09-22
PO100168 | 5 | THAAD | Warhead | DefenseCo Supplies | 5300 | CC387 | 51 | 8293.21 | 422953.71 | 2024-07-29 | 2024-08-24
PO100169 | 1 | HIMARS | Electronics | Precision Metals Inc | 5300 | CC813 | 243 | 34091.36 | 8284200.48 | 2024-04-02 | 2024-04-21
PO100170 | 5 | PAC-3 | Composites | RayTech Components | 5200 | CC824 | 159 | 20941.39 | 3329681.01 | 2024-01-24 | 2024-02-17
PO100171 | 1 | HIMARS | Composites | Orbital Systems | 5200 | CC631 | 188 | 2245.43 | 422140.84 | 2024-06-25 | 2024-07-31
PO100172 | 2 | HIMARS | Propulsion | DefenseCo Supplies | 5200 | CC611 | 228 | 43702.81 | 9964240.68 | 2024-09-18 | 2024-10-31
PO100173 | 5 | PAC-3 | Guidance | AeroDynamics Ltd | 5200 | CC736 | 12 | 19346.4 | 232156.8 | 2024-01-18 | 2024-03-02
PO100174 | 2 | PAC-3 | Electronics | Precision Metals Inc | 5200 | CC619 | 100 | 45474.37 | 4547437 | 2024-03-27 | 2024-04-14
PO100175 | 1 | PAC-3 | Warhead | DefenseCo Supplies | 5200 | CC652 | 62 | 5095.32 | 315909.84 | 2024-04-20 | 2024-05-08
PO100176 | 5 | HIMARS | Propulsion | RayTech Components | 5300 | CC956 | 249 | 20102.54 | 5005532.46 | 2024-06-11 | 2024-07-22
PO100177 | 2 | PAC-3 | Electronics | Orbital Systems | 5400 | CC775 | 45 | 12042.14 | 541896.3 | 2024-10-13 | 2024-10-28
PO100178 | 4 | PAC-3 | Hardware | AeroDynamics Ltd | 5100 | CC877 | 76 | 41486.95 | 3153008.2 | 2024-09-13 | 2024-09-22
PO100179 | 5 | HIMARS | Guidance | Orbital Systems | 5100 | CC412 | 64 | 18122.72 | 1159854.08 | 2024-10-10 | 2024-11-20
PO100180 | 4 | HIMARS | Warhead | RayTech Components | 5100 | CC731 | 44 | 22456.84 | 988100.96 | 2024-07-25 | 2024-08-04
PO100181 | 2 | PAC-3 | Warhead | Orbital Systems | 5200 | CC433 | 130 | 6367.8 | 827814 | 2024-10-19 | 2024-11-12
PO100182 | 4 | THAAD | Electronics | Precision Metals Inc | 5200 | CC584 | 245 | 4655.64 | 1140631.8 | 2024-06-09 | 2024-06-27
PO100183 | 1 | Javelin | Composites | DefenseCo Supplies | 5200 | CC315 | 43 | 1114.64 | 47929.52 | 2024-08-04 | 2024-09-06
PO100184 | 2 | PAC-3 | Guidance | AeroDynamics Ltd | 5300 | CC527 | 38 | 7197.65 | 273510.7 | 2024-05-05 | 2024-05-25
PO100185 | 5 | Javelin | Composites | AeroDynamics Ltd | 5100 | CC228 | 247 | 33711.96 | 8326854.12 | 2024-12-17 | 2025-01-28
PO100186 | 1 | PAC-3 | Hardware | AeroDynamics Ltd | 5100 | CC410 | 119 | 47244.56 | 5622102.64 | 2024-04-23 | 2024-05-15
PO100187 | 3 | Javelin | Electronics | Orbital Systems | 5300 | CC939 | 89 | 34553.96 | 3075302.44 | 2024-10-15 | 2024-10-20
PO100188 | 2 | PAC-3 | Hardware | DefenseCo Supplies | 5400 | CC168 | 105 | 5553 | 583065 | 2024-08-07 | 2024-08-13
PO100189 | 1 | HIMARS | Hardware | RayTech Components | 5100 | CC780 | 89 | 43569.98 | 3877728.22 | 2024-03-13 | 2024-03-30
PO100190 | 2 | PAC-3 | Composites | AeroDynamics Ltd | 5100 | CC201 | 238 | 46302.32 | 11019952.16 | 2024-01-19 | 2024-01-29
PO100191 | 1 | Javelin | Warhead | RayTech Components | 5300 | CC950 | 109 | 40937.25 | 4462160.25 | 2024-12-09 | 2024-12-20
PO100192 | 1 | THAAD | Electronics | Orbital Systems | 5200 | CC810 | 143 | 34849.49 | 4983477.07 | 2024-11-11 | 2024-12-14
PO100193 | 2 | THAAD | Electronics | RayTech Components | 5300 | CC201 | 218 | 29456.32 | 6421477.76 | 2024-04-19 | 2024-05-07
PO100194 | 2 | Javelin | Hardware | RayTech Components | 5300 | CC184 | 26 | 47586.06 | 1237237.56 | 2024-04-26 | 2024-05-29
PO100195 | 3 | THAAD | Composites | DefenseCo Supplies | 5200 | CC403 | 37 | 12491.97 | 462202.89 | 2024-08-15 | 2024-09-03
PO100196 | 5 | HIMARS | Hardware | AeroDynamics Ltd | 5400 | CC990 | 171 | 1157.07 | 197858.97 | 2024-04-16 | 2024-05-06
PO100197 | 3 | HIMARS | Electronics | Orbital Systems | 5300 | CC150 | 15 | 10058.42 | 150876.3 | 2024-05-20 | 2024-06-15
PO100198 | 3 | Javelin | Hardware | DefenseCo Supplies | 5400 | CC472 | 52 | 33587.28 | 1746538.56 | 2024-06-05 | 2024-07-07
PO100199 | 1 | HIMARS | Propulsion | Orbital Systems | 5200 | CC757 | 2 | 13813.04 | 27626.08 | 2024-05-11 | 2024-06-10
PO100200 | 4 | Javelin | Guidance | Orbital Systems | 5200 | CC138 | 141 | 9433.11 | 1330068.51 | 2024-11-07 | 2024-12-17
PO100201 | 5 | HIMARS | Hardware | RayTech Components | 5400 | CC475 | 173 | 31749.28 | 5492625.44 | 2024-05-20 | 2024-06-15
PO100202 | 1 | Javelin | Composites | RayTech Components | 5200 | CC620 | 15 | 30646.3 | 459694.5 | 2024-04-30 | 2024-05-12
PO100203 | 2 | Javelin | Guidance | DefenseCo Supplies | 5400 | CC149 | 152 | 41175.06 | 6258609.12 | 2024-02-29 | 2024-04-12
PO100204 | 4 | THAAD | Propulsion | Precision Metals Inc | 5400 | CC538 | 242 | 7860.94 | 1902347.48 | 2024-02-18 | 2024-03-28
PO100205 | 2 | Javelin | Electronics | DefenseCo Supplies | 5100 | CC761 | 176 | 15785.52 | 2778251.52 | 2024-06-08 | 2024-06-23
PO100206 | 5 | THAAD | Hardware | DefenseCo Supplies | 5100 | CC540 | 153 | 49392.33 | 7557026.49 | 2024-10-17 | 2024-10-28
PO100207 | 4 | Javelin | Guidance | AeroDynamics Ltd | 5200 | CC736 | 167 | 36294.71 | 6061216.57 | 2024-10-06 | 2024-10-29
PO100208 | 1 | Javelin | Hardware | AeroDynamics Ltd | 5400 | CC266 | 109 | 4201.11 | 457920.99 | 2024-08-19 | 2024-09-29
PO100209 | 1 | HIMARS | Guidance | RayTech Components | 5400 | CC452 | 123 | 17342.13 | 2133081.99 | 2024-07-14 | 2024-07-31
PO100210 | 2 | HIMARS | Propulsion | Orbital Systems | 5100 | CC527 | 27 | 32098.37 | 866655.99 | 2024-09-20 | 2024-11-01
PO100211 | 4 | PAC-3 | Hardware | Orbital Systems | 5100 | CC157 | 3 | 9718.66 | 29155.98 | 2024-05-09 | 2024-06-05
PO100212 | 4 | Javelin | Hardware | RayTech Components | 5300 | CC453 | 215 | 23393.98 | 5029705.7 | 2024-09-20 | 2024-10-16
PO100213 | 2 | Javelin | Composites | DefenseCo Supplies | 5100 | CC576 | 31 | 37803.18 | 1171898.58 | 2024-11-06 | 2024-11-26
PO100214 | 3 | Javelin | Hardware | RayTech Components | 5300 | CC111 | 145 | 15217.44 | 2206528.8 | 2024-05-15 | 2024-06-08
PO100215 | 4 | HIMARS | Hardware | DefenseCo Supplies | 5300 | CC447 | 115 | 7832.7 | 900760.5 | 2024-01-05 | 2024-01-29
PO100216 | 5 | THAAD | Electronics | DefenseCo Supplies | 5400 | CC505 | 210 | 39448.12 | 8284105.2 | 2024-10-14 | 2024-11-20
PO100217 | 1 | HIMARS | Composites | Orbital Systems | 5200 | CC608 | 142 | 6103.04 | 866631.68 | 2024-05-30 | 2024-06-05
PO100218 | 2 | THAAD | Propulsion | Precision Metals Inc | 5100 | CC548 | 75 | 41307.98 | 3098098.5 | 2024-07-08 | 2024-08-04
PO100219 | 1 | HIMARS | Propulsion | Precision Metals Inc | 5200 | CC242 | 86 | 28437.12 | 2445592.32 | 2024-08-31 | 2024-09-16
PO100220 | 3 | Javelin | Hardware | AeroDynamics Ltd | 5100 | CC902 | 158 | 43929.22 | 6940816.76 | 2024-06-06 | 2024-06-24
PO100221 | 2 | HIMARS | Composites | RayTech Components | 5300 | CC504 | 163 | 8882.84 | 1447902.92 | 2024-05-09 | 2024-06-17
PO100222 | 4 | Javelin | Composites | AeroDynamics Ltd | 5400 | CC365 | 25 | 28864.38 | 721609.5 | 2024-09-09 | 2024-10-16
PO100223 | 5 | PAC-3 | Hardware | RayTech Components | 5200 | CC435 | 54 | 41509.29 | 2241501.66 | 2024-01-25 | 2024-02-11
PO100224 | 4 | Javelin | Warhead | AeroDynamics Ltd | 5400 | CC636 | 79 | 48164.98 | 3805033.42 | 2024-01-12 | 2024-02-17
PO100225 | 4 | THAAD | Hardware | Orbital Systems | 5200 | CC927 | 191 | 32131.11 | 6137042.01 | 2024-12-14 | 2024-12-20
PO100226 | 2 | PAC-3 | Guidance | Precision Metals Inc | 5100 | CC566 | 162 | 23125.07 | 3746261.34 | 2024-05-09 | 2024-05-24
PO100227 | 4 | THAAD | Electronics | Precision Metals Inc | 5100 | CC198 | 149 | 6288.9 | 937046.1 | 2024-07-08 | 2024-07-19
PO100228 | 4 | THAAD | Composites | Orbital Systems | 5300 | CC651 | 17 | 11824.12 | 201010.04 | 2024-11-03 | 2024-12-06
PO100229 | 3 | HIMARS | Composites | AeroDynamics Ltd | 5300 | CC584 | 116 | 20388.72 | 2365091.52 | 2024-09-12 | 2024-10-21
PO100230 | 5 | HIMARS | Hardware | DefenseCo Supplies | 5100 | CC697 | 133 | 798.81 | 106241.73 | 2024-03-02 | 2024-04-02
PO100231 | 5 | Javelin | Hardware | DefenseCo Supplies | 5200 | CC570 | 58 | 9687.32 | 561864.56 | 2024-03-05 | 2024-03-22
PO100232 | 1 | Javelin | Propulsion | DefenseCo Supplies | 5100 | CC792 | 82 | 3464.68 | 284103.76 | 2024-06-08 | 2024-07-18
PO100233 | 4 | PAC-3 | Electronics | Orbital Systems | 5300 | CC802 | 149 | 42256.76 | 6296257.24 | 2024-07-01 | 2024-07-31
PO100234 | 2 | Javelin | Composites | Orbital Systems | 5200 | CC843 | 227 | 18950.44 | 4301749.88 | 2024-02-11 | 2024-03-07
PO100235 | 4 | THAAD | Electronics | RayTech Components | 5400 | CC116 | 120 | 15941.49 | 1912978.8 | 2024-05-08 | 2024-05-14
PO100236 | 4 | HIMARS | Warhead | RayTech Components | 5200 | CC341 | 58 | 12839.66 | 744700.28 | 2024-08-19 | 2024-09-13
PO100237 | 5 | PAC-3 | Propulsion | Precision Metals Inc | 5200 | CC299 | 177 | 30793.2 | 5450396.4 | 2024-12-08 | 2025-01-05
PO100238 | 3 | PAC-3 | Warhead | Orbital Systems | 5100 | CC186 | 101 | 2629.58 | 265587.58 | 2024-07-18 | 2024-08-14
PO100239 | 2 | THAAD | Warhead | Precision Metals Inc | 5400 | CC582 | 152 | 2019.65 | 306986.8 | 2024-05-27 | 2024-06-21
PO100240 | 5 | PAC-3 | Hardware | Orbital Systems | 5300 | CC535 | 143 | 47130.19 | 6739617.17 | 2024-01-28 | 2024-02-06
PO100241 | 1 | Javelin | Hardware | AeroDynamics Ltd | 5200 | CC722 | 224 | 25854.21 | 5791343.04 | 2024-12-02 | 2025-01-06
PO100242 | 2 | THAAD | Propulsion | AeroDynamics Ltd | 5300 | CC660 | 36 | 30846.9 | 1110488.4 | 2024-03-18 | 2024-04-16
PO100243 | 5 | PAC-3 | Hardware | AeroDynamics Ltd | 5200 | CC248 | 164 | 14817.9 | 2430135.6 | 2024-09-14 | 2024-10-01
PO100244 | 1 | HIMARS | Composites | AeroDynamics Ltd | 5300 | CC621 | 15 | 5762.7 | 86440.5 | 2024-07-01 | 2024-07-14
PO100245 | 3 | HIMARS | Guidance | Orbital Systems | 5200 | CC725 | 22 | 13871.12 | 305164.64 | 2024-07-31 | 2024-09-05
PO100246 | 1 | Javelin | Electronics | DefenseCo Supplies | 5300 | CC221 | 32 | 16016.89 | 512540.48 | 2024-02-08 | 2024-02-24
PO100247 | 4 | PAC-3 | Propulsion | DefenseCo Supplies | 5100 | CC760 | 126 | 42139.43 | 5309568.18 | 2024-12-25 | 2025-01-05
PO100248 | 5 | HIMARS | Guidance | Precision Metals Inc | 5100 | CC633 | 92 | 2397.89 | 220605.88 | 2024-09-14 | 2024-10-17
PO100249 | 3 | PAC-3 | Composites | Precision Metals Inc | 5200 | CC706 | 207 | 25416.17 | 5261147.19 | 2024-03-28 | 2024-04-14
PO100250 | 4 | THAAD | Warhead | RayTech Components | 5400 | CC614 | 191 | 5520.05 | 1054329.55 | 2024-01-23 | 2024-02-25
PO100251 | 4 | PAC-3 | Electronics | DefenseCo Supplies | 5300 | CC235 | 106 | 28012.61 | 2969336.66 | 2024-03-12 | 2024-03-17
PO100252 | 3 | THAAD | Guidance | RayTech Components | 5400 | CC203 | 227 | 20224.34 | 4590925.18 | 2024-12-27 | 2025-02-03
PO100253 | 1 | THAAD | Propulsion | DefenseCo Supplies | 5400 | CC401 | 231 | 30845.17 | 7125234.27 | 2024-03-06 | 2024-03-23
PO100254 | 5 | HIMARS | Composites | AeroDynamics Ltd | 5200 | CC413 | 54 | 41675.85 | 2250495.9 | 2024-01-14 | 2024-02-21
PO100255 | 5 | THAAD | Composites | Precision Metals Inc | 5400 | CC854 | 223 | 15453.81 | 3446199.63 | 2024-11-07 | 2024-11-30
PO100256 | 5 | Javelin | Composites | DefenseCo Supplies | 5400 | CC119 | 138 | 44338.24 | 6118677.12 | 2024-08-14 | 2024-09-13
PO100257 | 1 | Javelin | Warhead | DefenseCo Supplies | 5200 | CC137 | 174 | 17935.78 | 3120825.72 | 2024-02-26 | 2024-03-21
PO100258 | 2 | PAC-3 | Composites | DefenseCo Supplies | 5200 | CC614 | 216 | 5430.83 | 1173059.28 | 2024-07-04 | 2024-07-12
PO100259 | 5 | Javelin | Propulsion | Precision Metals Inc | 5300 | CC287 | 60 | 16274.87 | 976492.2 | 2024-11-14 | 2024-12-07
PO100260 | 1 | HIMARS | Hardware | AeroDynamics Ltd | 5200 | CC216 | 159 | 41300.25 | 6566739.75 | 2024-01-19 | 2024-02-28
PO100261 | 1 | PAC-3 | Electronics | AeroDynamics Ltd | 5300 | CC727 | 113 | 30011.71 | 3391323.23 | 2024-09-07 | 2024-09-22
PO100262 | 4 | HIMARS | Hardware | DefenseCo Supplies | 5100 | CC500 | 198 | 31899.82 | 6316164.36 | 2024-08-27 | 2024-09-27
PO100263 | 5 | PAC-3 | Electronics | AeroDynamics Ltd | 5400 | CC936 | 249 | 28386.11 | 7068141.39 | 2024-05-17 | 2024-05-24
PO100264 | 3 | PAC-3 | Electronics | DefenseCo Supplies | 5200 | CC948 | 109 | 39183.45 | 4270996.05 | 2024-02-04 | 2024-03-05
PO100265 | 2 | THAAD | Warhead | DefenseCo Supplies | 5400 | CC148 | 149 | 23044.8 | 3433675.2 | 2024-09-17 | 2024-10-27
PO100266 | 4 | HIMARS | Hardware | AeroDynamics Ltd | 5300 | CC740 | 24 | 36543.03 | 877032.72 | 2024-11-21 | 2024-12-26
PO100267 | 3 | HIMARS | Electronics | Orbital Systems | 5100 | CC507 | 108 | 2468.6 | 266608.8 | 2024-12-07 | 2025-01-08
PO100268 | 4 | PAC-3 | Composites | AeroDynamics Ltd | 5400 | CC499 | 182 | 21587.12 | 3928855.84 | 2024-08-04 | 2024-08-21
PO100269 | 4 | THAAD | Warhead | Orbital Systems | 5400 | CC718 | 84 | 31080.05 | 2610724.2 | 2024-12-28 | 2025-01-22
PO100270 | 4 | Javelin | Electronics | Precision Metals Inc | 5300 | CC169 | 127 | 12030.02 | 1527812.54 | 2024-06-08 | 2024-06-23
PO100271 | 2 | HIMARS | Warhead | AeroDynamics Ltd | 5200 | CC591 | 120 | 13192.85 | 1583142 | 2024-11-08 | 2024-12-19
PO100272 | 3 | THAAD | Propulsion | DefenseCo Supplies | 5300 | CC698 | 218 | 9761.74 | 2128059.32 | 2024-10-31 | 2024-11-23
PO100273 | 2 | THAAD | Warhead | Orbital Systems | 5100 | CC544 | 169 | 1346.25 | 227516.25 | 2024-04-26 | 2024-05-04
PO100274 | 1 | THAAD | Hardware | RayTech Components | 5100 | CC763 | 61 | 11563.62 | 705380.82 | 2024-01-28 | 2024-03-11
PO100275 | 2 | THAAD | Propulsion | AeroDynamics Ltd | 5100 | CC941 | 85 | 7262.74 | 617332.9 | 2024-01-22 | 2024-01-28
PO100276 | 3 | Javelin | Guidance | DefenseCo Supplies | 5300 | CC185 | 76 | 3348.09 | 254454.84 | 2024-10-20 | 2024-11-03
PO100277 | 4 | HIMARS | Guidance | RayTech Components | 5400 | CC131 | 135 | 43638.75 | 5891231.25 | 2024-06-02 | 2024-06-10
PO100278 | 2 | Javelin | Warhead | Orbital Systems | 5400 | CC881 | 155 | 47345.24 | 7338512.2 | 2024-06-16 | 2024-07-18
PO100279 | 4 | THAAD | Propulsion | RayTech Components | 5400 | CC353 | 131 | 45483.71 | 5958366.01 | 2024-04-06 | 2024-05-15
PO100280 | 2 | PAC-3 | Electronics | Precision Metals Inc | 5200 | CC526 | 147 | 22193.34 | 3262420.98 | 2024-09-23 | 2024-10-09
PO100281 | 2 | HIMARS | Composites | Orbital Systems | 5100 | CC263 | 229 | 31820.48 | 7286889.92 | 2024-02-24 | 2024-03-08
PO100282 | 3 | Javelin | Composites | Orbital Systems | 5200 | CC367 | 130 | 16008.89 | 2081155.7 | 2024-12-30 | 2025-01-06
PO100283 | 4 | Javelin | Guidance | RayTech Components | 5400 | CC228 | 247 | 9415.19 | 2325551.93 | 2024-04-10 | 2024-05-16
PO100284 | 3 | HIMARS | Guidance | DefenseCo Supplies | 5400 | CC465 | 246 | 42879.48 | 10548352.08 | 2024-05-16 | 2024-06-01
PO100285 | 2 | Javelin | Electronics | DefenseCo Supplies | 5300 | CC632 | 158 | 31824.9 | 5028334.2 | 2024-09-16 | 2024-10-18
PO100286 | 2 | PAC-3 | Guidance | Precision Metals Inc | 5100 | CC636 | 131 | 26488.13 | 3469945.03 | 2024-10-07 | 2024-10-31
PO100287 | 4 | Javelin | Hardware | DefenseCo Supplies | 5300 | CC800 | 220 | 42944.31 | 9447748.2 | 2024-05-13 | 2024-06-05
PO100288 | 3 | HIMARS | Electronics | Precision Metals Inc | 5200 | CC463 | 108 | 15874.52 | 1714448.16 | 2024-08-03 | 2024-09-10
PO100289 | 5 | HIMARS | Composites | AeroDynamics Ltd | 5400 | CC376 | 156 | 41342.42 | 6449417.52 | 2024-07-08 | 2024-08-14
PO100290 | 1 | PAC-3 | Composites | AeroDynamics Ltd | 5100 | CC406 | 175 | 9765.21 | 1708911.75 | 2024-03-15 | 2024-04-11
PO100291 | 2 | THAAD | Composites | Precision Metals Inc | 5200 | CC882 | 91 | 31798.57 | 2893669.87 | 2024-07-30 | 2024-08-19
PO100292 | 3 | Javelin | Guidance | Orbital Systems | 5300 | CC553 | 201 | 32850.3 | 6602910.3 | 2024-01-01 | 2024-01-13
PO100293 | 4 | HIMARS | Propulsion | RayTech Components | 5300 | CC905 | 143 | 10829.06 | 1548555.58 | 2024-08-14 | 2024-09-01
PO100294 | 3 | HIMARS | Electronics | RayTech Components | 5300 | CC863 | 77 | 44967.66 | 3462509.82 | 2024-04-24 | 2024-05-31
PO100295 | 3 | PAC-3 | Guidance | Precision Metals Inc | 5200 | CC987 | 46 | 23152.82 | 1065029.72 | 2024-04-09 | 2024-04-21
PO100296 | 1 | PAC-3 | Hardware | Precision Metals Inc | 5400 | CC980 | 25 | 21216.84 | 530421 | 2024-09-26 | 2024-10-26
PO100297 | 1 | PAC-3 | Hardware | Precision Metals Inc | 5300 | CC525 | 19 | 40294.11 | 765588.09 | 2024-06-21 | 2024-07-02
PO100298 | 5 | PAC-3 | Composites | RayTech Components | 5400 | CC886 | 175 | 22629.65 | 3960188.75 | 2024-04-29 | 2024-06-10
PO100299 | 3 | THAAD | Composites | RayTech Components | 5200 | CC364 | 64 | 28466.75 | 1821872 | 2024-11-03 | 2024-12-02
PO100300 | 2 | THAAD | Guidance | RayTech Components | 5300 | CC433 | 222 | 30040.71 | 6669037.62 | 2024-03-08 | 2024-04-09
PO100301 | 4 | THAAD | Warhead | RayTech Components | 5400 | CC226 | 183 | 26683 | 4882989 | 2024-03-02 | 2024-04-05
PO100302 | 3 | PAC-3 | Guidance | AeroDynamics Ltd | 5100 | CC866 | 149 | 3416.14 | 509004.86 | 2024-10-02 | 2024-11-12
PO100303 | 2 | HIMARS | Electronics | DefenseCo Supplies | 5100 | CC300 | 189 | 1874.12 | 354208.68 | 2024-02-04 | 2024-02-25
PO100304 | 1 | HIMARS | Electronics | DefenseCo Supplies | 5300 | CC530 | 168 | 16018.09 | 2691039.12 | 2024-03-16 | 2024-04-04
PO100305 | 1 | PAC-3 | Propulsion | Orbital Systems | 5100 | CC505 | 232 | 47418.39 | 11001066.48 | 2024-02-07 | 2024-03-02
PO100306 | 4 | THAAD | Guidance | Orbital Systems | 5300 | CC554 | 92 | 5435.18 | 500036.56 | 2024-03-16 | 2024-03-23
PO100307 | 1 | Javelin | Propulsion | Precision Metals Inc | 5300 | CC460 | 1 | 13630.71 | 13630.71 | 2024-09-18 | 2024-10-14
PO100308 | 1 | Javelin | Electronics | DefenseCo Supplies | 5400 | CC361 | 218 | 45392.16 | 9895490.88 | 2024-12-27 | 2025-01-01
PO100309 | 1 | THAAD | Warhead | RayTech Components | 5300 | CC523 | 142 | 30636.31 | 4350356.02 | 2024-08-24 | 2024-09-17
PO100310 | 5 | THAAD | Warhead | RayTech Components | 5200 | CC980 | 190 | 41707.52 | 7924428.8 | 2024-12-18 | 2025-01-17
PO100311 | 1 | THAAD | Electronics | AeroDynamics Ltd | 5300 | CC921 | 126 | 14071.65 | 1773027.9 | 2024-12-09 | 2025-01-19
PO100312 | 3 | THAAD | Electronics | DefenseCo Supplies | 5300 | CC670 | 167 | 28845.28 | 4817161.76 | 2024-02-08 | 2024-02-25
PO100313 | 4 | Javelin | Guidance | Precision Metals Inc | 5100 | CC226 | 46 | 8468.9 | 389569.4 | 2024-06-16 | 2024-07-09
PO100314 | 4 | HIMARS | Warhead | DefenseCo Supplies | 5100 | CC367 | 189 | 15641.29 | 2956203.81 | 2024-10-27 | 2024-11-26
PO100315 | 2 | Javelin | Warhead | RayTech Components | 5300 | CC273 | 87 | 35949.21 | 3127581.27 | 2024-08-02 | 2024-08-26
PO100316 | 4 | Javelin | Propulsion | Orbital Systems | 5200 | CC772 | 127 | 33217.56 | 4218630.12 | 2024-05-26 | 2024-06-27
PO100317 | 1 | THAAD | Electronics | Orbital Systems | 5200 | CC854 | 143 | 37555.08 | 5370376.44 | 2024-09-14 | 2024-10-17
PO100318 | 1 | Javelin | Propulsion | Precision Metals Inc | 5300 | CC365 | 142 | 31895.78 | 4529200.76 | 2024-04-27 | 2024-05-10
PO100319 | 3 | PAC-3 | Composites | Precision Metals Inc | 5400 | CC553 | 155 | 37113.82 | 5752642.1 | 2024-04-02 | 2024-05-14
PO100320 | 2 | HIMARS | Hardware | AeroDynamics Ltd | 5100 | CC367 | 163 | 22580.44 | 3680611.72 | 2024-11-06 | 2024-11-25
PO100321 | 5 | THAAD | Warhead | RayTech Components | 5300 | CC322 | 153 | 36526.38 | 5588536.14 | 2024-10-20 | 2024-11-21
PO100322 | 4 | Javelin | Guidance | AeroDynamics Ltd | 5400 | CC710 | 173 | 13950.21 | 2413386.33 | 2024-05-01 | 2024-06-04
PO100323 | 3 | HIMARS | Propulsion | Precision Metals Inc | 5300 | CC255 | 172 | 45852.6 | 7886647.2 | 2024-03-03 | 2024-03-30
PO100324 | 4 | HIMARS | Propulsion | Precision Metals Inc | 5100 | CC217 | 100 | 19800.47 | 1980047 | 2024-06-15 | 2024-07-23
PO100325 | 2 | THAAD | Composites | DefenseCo Supplies | 5400 | CC932 | 193 | 47345.56 | 9137693.08 | 2024-10-01 | 2024-11-03
PO100326 | 1 | HIMARS | Propulsion | Orbital Systems | 5300 | CC526 | 239 | 3817.67 | 912423.13 | 2024-05-05 | 2024-05-20
PO100327 | 4 | THAAD | Hardware | DefenseCo Supplies | 5400 | CC787 | 116 | 29116.02 | 3377458.32 | 2024-11-16 | 2024-12-21
PO100328 | 2 | THAAD | Warhead | AeroDynamics Ltd | 5100 | CC475 | 88 | 25396.39 | 2234882.32 | 2024-03-15 | 2024-03-23
PO100329 | 5 | PAC-3 | Hardware | Precision Metals Inc | 5400 | CC333 | 51 | 1411.77 | 72000.27 | 2024-11-10 | 2024-11-29
PO100330 | 4 | Javelin | Propulsion | DefenseCo Supplies | 5200 | CC224 | 37 | 47806.96 | 1768857.52 | 2024-12-22 | 2025-01-30
PO100331 | 5 | Javelin | Composites | RayTech Components | 5100 | CC896 | 77 | 30442.15 | 2344045.55 | 2024-05-05 | 2024-05-26
PO100332 | 5 | HIMARS | Hardware | Orbital Systems | 5100 | CC264 | 233 | 27797.15 | 6476735.95 | 2024-06-10 | 2024-07-06
PO100333 | 4 | PAC-3 | Guidance | Precision Metals Inc | 5200 | CC453 | 160 | 35523.43 | 5683748.8 | 2024-09-06 | 2024-10-01
PO100334 | 5 | THAAD | Composites | Precision Metals Inc | 5300 | CC935 | 243 | 8470.79 | 2058401.97 | 2024-10-06 | 2024-11-14
PO100335 | 1 | PAC-3 | Propulsion | Precision Metals Inc | 5400 | CC534 | 17 | 36795.25 | 625519.25 | 2024-12-03 | 2025-01-16
PO100336 | 4 | HIMARS | Propulsion | Precision Metals Inc | 5100 | CC952 | 8 | 2213.11 | 17704.88 | 2024-05-24 | 2024-07-04
PO100337 | 5 | Javelin | Guidance | Precision Metals Inc | 5100 | CC965 | 11 | 17834.67 | 196181.37 | 2024-02-16 | 2024-03-03
PO100338 | 1 | Javelin | Guidance | Orbital Systems | 5100 | CC283 | 20 | 23472.41 | 469448.2 | 2024-01-12 | 2024-01-22
PO100339 | 3 | PAC-3 | Guidance | AeroDynamics Ltd | 5400 | CC719 | 236 | 37792.41 | 8919008.76 | 2024-03-10 | 2024-04-19
PO100340 | 3 | THAAD | Hardware | Precision Metals Inc | 5300 | CC803 | 249 | 18272.84 | 4549937.16 | 2024-06-27 | 2024-07-15
PO100341 | 4 | Javelin | Composites | Precision Metals Inc | 5300 | CC850 | 4 | 40377.82 | 161511.28 | 2024-06-11 | 2024-06-24
PO100342 | 3 | THAAD | Electronics | RayTech Components | 5100 | CC836 | 96 | 12209.02 | 1172065.92 | 2024-03-03 | 2024-04-14
PO100343 | 5 | PAC-3 | Warhead | DefenseCo Supplies | 5300 | CC593 | 189 | 46337.53 | 8757793.17 | 2024-07-26 | 2024-08-31
PO100344 | 1 | Javelin | Guidance | Precision Metals Inc | 5200 | CC909 | 64 | 15144.93 | 969275.52 | 2024-07-22 | 2024-07-28
PO100345 | 1 | HIMARS | Guidance | RayTech Components | 5200 | CC402 | 163 | 49891.59 | 8132329.17 | 2024-09-20 | 2024-10-20
PO100346 | 5 | HIMARS | Hardware | Precision Metals Inc | 5100 | CC391 | 25 | 31737.09 | 793427.25 | 2024-02-06 | 2024-02-23
PO100347 | 2 | HIMARS | Electronics | RayTech Components | 5400 | CC646 | 194 | 5444.11 | 1056157.34 | 2024-01-23 | 2024-02-05
PO100348 | 4 | Javelin | Hardware | Orbital Systems | 5200 | CC457 | 75 | 17603.82 | 1320286.5 | 2024-09-15 | 2024-10-03
PO100349 | 1 | THAAD | Warhead | AeroDynamics Ltd | 5100 | CC672 | 83 | 26248.19 | 2178599.77 | 2024-01-16 | 2024-01-22
PO100350 | 4 | PAC-3 | Propulsion | AeroDynamics Ltd | 5400 | CC755 | 102 | 2748.74 | 280371.48 | 2024-01-13 | 2024-02-17
PO100351 | 1 | Javelin | Guidance | Precision Metals Inc | 5200 | CC832 | 231 | 23952.74 | 5533082.94 | 2024-11-16 | 2024-12-07
PO100352 | 1 | Javelin | Warhead | DefenseCo Supplies | 5100 | CC502 | 53 | 20952.04 | 1110458.12 | 2024-10-07 | 2024-11-02
PO100353 | 2 | PAC-3 | Hardware | AeroDynamics Ltd | 5200 | CC583 | 200 | 27844.2 | 5568840 | 2024-05-27 | 2024-07-02
PO100354 | 5 | Javelin | Propulsion | Orbital Systems | 5200 | CC152 | 152 | 14676.01 | 2230753.52 | 2024-01-30 | 2024-02-07
PO100355 | 1 | PAC-3 | Propulsion | Orbital Systems | 5300 | CC389 | 82 | 41232.96 | 3381102.72 | 2024-05-06 | 2024-05-21
PO100356 | 1 | HIMARS | Electronics | RayTech Components | 5300 | CC340 | 93 | 2580.88 | 240021.84 | 2024-04-05 | 2024-05-01
PO100357 | 3 | PAC-3 | Propulsion | RayTech Components | 5200 | CC424 | 172 | 37109.98 | 6382916.56 | 2024-06-05 | 2024-07-07
PO100358 | 3 | THAAD | Electronics | Precision Metals Inc | 5300 | CC236 | 155 | 43360.76 | 6720917.8 | 2024-04-09 | 2024-05-01
PO100359 | 2 | THAAD | Guidance | RayTech Components | 5200 | CC723 | 56 | 48212.9 | 2699922.4 | 2024-07-04 | 2024-07-31
PO100360 | 5 | THAAD | Electronics | Orbital Systems | 5300 | CC828 | 120 | 33873.43 | 4064811.6 | 2024-06-23 | 2024-07-20
PO100361 | 1 | THAAD | Guidance | DefenseCo Supplies | 5100 | CC635 | 108 | 6697.63 | 723344.04 | 2024-10-07 | 2024-11-10
PO100362 | 4 | THAAD | Composites | Precision Metals Inc | 5300 | CC751 | 37 | 2647.25 | 97948.25 | 2024-04-10 | 2024-05-23
PO100363 | 1 | HIMARS | Electronics | Precision Metals Inc | 5300 | CC595 | 146 | 31812.6 | 4644639.6 | 2024-08-14 | 2024-08-25
PO100364 | 3 | THAAD | Propulsion | DefenseCo Supplies | 5100 | CC199 | 31 | 36052.78 | 1117636.18 | 2024-05-16 | 2024-05-29
PO100365 | 4 | Javelin | Hardware | RayTech Components | 5400 | CC720 | 87 | 30485.67 | 2652253.29 | 2024-06-10 | 2024-06-23
PO100366 | 5 | Javelin | Guidance | Orbital Systems | 5200 | CC248 | 28 | 35732.04 | 1000497.12 | 2024-03-05 | 2024-04-14
PO100367 | 5 | HIMARS | Guidance | Precision Metals Inc | 5100 | CC412 | 49 | 5797.73 | 284088.77 | 2024-05-17 | 2024-05-31
PO100368 | 3 | THAAD | Hardware | AeroDynamics Ltd | 5200 | CC948 | 100 | 47455.09 | 4745509 | 2024-06-11 | 2024-07-10
PO100369 | 4 | PAC-3 | Hardware | RayTech Components | 5400 | CC281 | 116 | 743.71 | 86270.36 | 2024-06-19 | 2024-07-18
PO100370 | 4 | Javelin | Composites | AeroDynamics Ltd | 5200 | CC932 | 84 | 22882.21 | 1922105.64 | 2024-09-28 | 2024-10-19
PO100371 | 5 | Javelin | Composites | Precision Metals Inc | 5200 | CC792 | 170 | 38565.37 | 6556112.9 | 2024-08-09 | 2024-09-16
PO100372 | 3 | Javelin | Warhead | RayTech Components | 5100 | CC154 | 186 | 11357.35 | 2112467.1 | 2024-11-08 | 2024-11-24
PO100373 | 1 | THAAD | Composites | DefenseCo Supplies | 5300 | CC327 | 111 | 33860.11 | 3758472.21 | 2024-06-08 | 2024-06-23
PO100374 | 2 | PAC-3 | Electronics | DefenseCo Supplies | 5200 | CC158 | 132 | 44997.9 | 5939722.8 | 2024-06-05 | 2024-07-13
PO100375 | 4 | HIMARS | Warhead | Orbital Systems | 5300 | CC317 | 4 | 47900.04 | 191600.16 | 2024-04-28 | 2024-05-07
PO100376 | 1 | Javelin | Guidance | Orbital Systems | 5200 | CC332 | 17 | 11462.72 | 194866.24 | 2024-07-17 | 2024-08-16
PO100377 | 4 | Javelin | Guidance | DefenseCo Supplies | 5300 | CC366 | 205 | 40603.41 | 8323699.05 | 2024-12-25 | 2025-01-02
PO100378 | 1 | PAC-3 | Guidance | RayTech Components | 5100 | CC786 | 52 | 17032.67 | 885698.84 | 2024-07-06 | 2024-08-10
PO100379 | 1 | Javelin | Propulsion | AeroDynamics Ltd | 5100 | CC981 | 5 | 24991.29 | 124956.45 | 2024-12-26 | 2025-01-10
PO100380 | 2 | Javelin | Hardware | Precision Metals Inc | 5200 | CC114 | 224 | 25155.03 | 5634726.72 | 2024-10-03 | 2024-10-12
PO100381 | 4 | Javelin | Propulsion | DefenseCo Supplies | 5300 | CC833 | 3 | 8496.05 | 25488.15 | 2024-04-02 | 2024-04-14
PO100382 | 4 | THAAD | Guidance | Orbital Systems | 5100 | CC820 | 240 | 49750.32 | 11940076.8 | 2024-02-19 | 2024-03-05
PO100383 | 1 | HIMARS | Hardware | RayTech Components | 5400 | CC679 | 99 | 25037.24 | 2478686.76 | 2024-07-02 | 2024-08-01
PO100384 | 2 | HIMARS | Guidance | DefenseCo Supplies | 5100 | CC373 | 19 | 9010.75 | 171204.25 | 2024-12-23 | 2025-01-14
PO100385 | 2 | Javelin | Composites | Orbital Systems | 5300 | CC896 | 59 | 17913.29 | 1056884.11 | 2024-09-29 | 2024-10-19
PO100386 | 3 | Javelin | Warhead | AeroDynamics Ltd | 5400 | CC577 | 96 | 15672.5 | 1504560 | 2024-04-03 | 2024-04-08
PO100387 | 5 | PAC-3 | Electronics | Precision Metals Inc | 5400 | CC699 | 242 | 38638.44 | 9350502.48 | 2024-03-26 | 2024-04-08
PO100388 | 2 | Javelin | Composites | DefenseCo Supplies | 5400 | CC611 | 156 | 11626.67 | 1813760.52 | 2024-06-19 | 2024-07-14
PO100389 | 5 | HIMARS | Propulsion | Precision Metals Inc | 5200 | CC712 | 155 | 1701.2 | 263686 | 2024-12-29 | 2025-01-15
PO100390 | 1 | Javelin | Composites | RayTech Components | 5200 | CC859 | 247 | 45996.67 | 11361177.49 | 2024-05-08 | 2024-06-13
PO100391 | 3 | THAAD | Electronics | Precision Metals Inc | 5400 | CC503 | 117 | 1872.74 | 219110.58 | 2024-04-08 | 2024-05-21
PO100392 | 2 | Javelin | Hardware | RayTech Components | 5200 | CC784 | 116 | 19469.58 | 2258471.28 | 2024-06-29 | 2024-07-30
PO100393 | 2 | HIMARS | Electronics | AeroDynamics Ltd | 5100 | CC157 | 154 | 45932.39 | 7073588.06 | 2024-04-25 | 2024-05-22
PO100394 | 4 | PAC-3 | Guidance | RayTech Components | 5100 | CC989 | 193 | 8967.28 | 1730685.04 | 2024-12-19 | 2025-01-21
PO100395 | 2 | THAAD | Guidance | Precision Metals Inc | 5100 | CC198 | 76 | 37999.12 | 2887933.12 | 2024-04-18 | 2024-04-29
PO100396 | 1 | HIMARS | Warhead | DefenseCo Supplies | 5200 | CC231 | 23 | 23947.7 | 550797.1 | 2024-08-29 | 2024-10-01
PO100397 | 5 | HIMARS | Guidance | Orbital Systems | 5200 | CC604 | 219 | 3683.13 | 806605.47 | 2024-09-27 | 2024-11-05
PO100398 | 2 | THAAD | Guidance | Precision Metals Inc | 5400 | CC288 | 164 | 34757.5 | 5700230 | 2024-01-24 | 2024-02-21
PO100399 | 5 | HIMARS | Guidance | AeroDynamics Ltd | 5100 | CC532 | 215 | 2508.81 | 539394.15 | 2024-04-25 | 2024-05-22
PO100400 | 5 | THAAD | Hardware | DefenseCo Supplies | 5200 | CC780 | 57 | 29623.95 | 1688565.15 | 2024-07-06 | 2024-07-16
PO100401 | 4 | THAAD | Propulsion | DefenseCo Supplies | 5100 | CC311 | 3 | 44166.04 | 132498.12 | 2024-12-07 | 2024-12-15
PO100402 | 5 | HIMARS | Hardware | Precision Metals Inc | 5300 | CC519 | 239 | 20943.21 | 5005427.19 | 2024-12-08 | 2025-01-11
PO100403 | 5 | THAAD | Guidance | Precision Metals Inc | 5200 | CC284 | 126 | 17014 | 2143764 | 2024-02-16 | 2024-03-27
PO100404 | 3 | Javelin | Warhead | RayTech Components | 5400 | CC670 | 247 | 27338.72 | 6752663.84 | 2024-07-20 | 2024-08-25
PO100405 | 4 | Javelin | Hardware | RayTech Components | 5100 | CC750 | 224 | 2360.51 | 528754.24 | 2024-09-29 | 2024-10-07
PO100406 | 3 | PAC-3 | Electronics | Precision Metals Inc | 5100 | CC968 | 102 | 39091.41 | 3987323.82 | 2024-07-09 | 2024-08-07
PO100407 | 3 | HIMARS | Electronics | RayTech Components | 5300 | CC187 | 194 | 34936.17 | 6777616.98 | 2024-04-05 | 2024-05-18
PO100408 | 1 | Javelin | Electronics | AeroDynamics Ltd | 5300 | CC608 | 126 | 17394.05 | 2191650.3 | 2024-09-07 | 2024-10-10
PO100409 | 5 | THAAD | Hardware | Orbital Systems | 5400 | CC344 | 3 | 6164 | 18492 | 2024-02-18 | 2024-03-05
PO100410 | 2 | PAC-3 | Electronics | RayTech Components | 5300 | CC573 | 15 | 25456.96 | 381854.4 | 2024-12-17 | 2024-12-25
PO100411 | 2 | THAAD | Guidance | Precision Metals Inc | 5400 | CC518 | 232 | 39927.98 | 9263291.36 | 2024-10-15 | 2024-11-02
PO100412 | 5 | THAAD | Composites | Precision Metals Inc | 5100 | CC950 | 134 | 27434.91 | 3676277.94 | 2024-06-16 | 2024-07-09
PO100413 | 3 | THAAD | Warhead | Precision Metals Inc | 5400 | CC489 | 232 | 9167.97 | 2126969.04 | 2024-11-15 | 2024-12-24
PO100414 | 3 | HIMARS | Guidance | Precision Metals Inc | 5200 | CC188 | 148 | 33938.33 | 5022872.84 | 2024-05-30 | 2024-06-05
PO100415 | 4 | THAAD | Warhead | Precision Metals Inc | 5200 | CC883 | 247 | 45327.83 | 11195974.01 | 2024-07-28 | 2024-08-17
PO100416 | 1 | THAAD | Electronics | Orbital Systems | 5200 | CC664 | 75 | 9773.53 | 733014.75 | 2024-05-19 | 2024-06-09
PO100417 | 5 | THAAD | Electronics | Orbital Systems | 5200 | CC168 | 118 | 12544.79 | 1480285.22 | 2024-02-02 | 2024-02-25
PO100418 | 3 | PAC-3 | Propulsion | Orbital Systems | 5100 | CC240 | 84 | 33656.09 | 2827111.56 | 2024-03-19 | 2024-04-15
PO100419 | 1 | HIMARS | Hardware | DefenseCo Supplies | 5400 | CC503 | 29 | 16431.38 | 476510.02 | 2024-11-14 | 2024-11-28
PO100420 | 1 | THAAD | Propulsion | DefenseCo Supplies | 5200 | CC116 | 66 | 48541.16 | 3203716.56 | 2024-11-20 | 2024-12-22
PO100421 | 3 | THAAD | Propulsion | AeroDynamics Ltd | 5400 | CC524 | 177 | 17489.58 | 3095655.66 | 2024-07-22 | 2024-08-02
PO100422 | 2 | PAC-3 | Propulsion | AeroDynamics Ltd | 5100 | CC902 | 208 | 31627.35 | 6578488.8 | 2024-10-06 | 2024-10-20
PO100423 | 4 | PAC-3 | Guidance | DefenseCo Supplies | 5300 | CC329 | 20 | 15040.22 | 300804.4 | 2024-05-27 | 2024-06-19
PO100424 | 1 | PAC-3 | Propulsion | DefenseCo Supplies | 5200 | CC934 | 134 | 12731.93 | 1706078.62 | 2024-09-22 | 2024-10-05
PO100425 | 2 | HIMARS | Hardware | RayTech Components | 5300 | CC199 | 59 | 29984 | 1769056 | 2024-03-05 | 2024-03-28
PO100426 | 4 | THAAD | Propulsion | DefenseCo Supplies | 5300 | CC414 | 150 | 46968.09 | 7045213.5 | 2024-09-04 | 2024-09-30
PO100427 | 1 | Javelin | Hardware | RayTech Components | 5100 | CC383 | 193 | 1015.9 | 196068.7 | 2024-03-08 | 2024-03-19
PO100428 | 1 | THAAD | Composites | Precision Metals Inc | 5100 | CC749 | 164 | 36354.86 | 5962197.04 | 2024-02-15 | 2024-03-22
PO100429 | 4 | Javelin | Propulsion | Precision Metals Inc | 5200 | CC789 | 163 | 44530.34 | 7258445.42 | 2024-12-06 | 2025-01-04
PO100430 | 1 | PAC-3 | Composites | DefenseCo Supplies | 5300 | CC172 | 155 | 700.44 | 108568.2 | 2024-09-04 | 2024-10-06
PO100431 | 4 | PAC-3 | Electronics | RayTech Components | 5200 | CC311 | 237 | 4796.73 | 1136825.01 | 2024-09-01 | 2024-09-28
PO100432 | 5 | PAC-3 | Electronics | RayTech Components | 5200 | CC168 | 43 | 12566.1 | 540342.3 | 2024-10-22 | 2024-11-06
PO100433 | 2 | Javelin | Guidance | AeroDynamics Ltd | 5100 | CC430 | 16 | 4287.17 | 68594.72 | 2024-10-30 | 2024-11-13
PO100434 | 3 | Javelin | Guidance | Orbital Systems | 5300 | CC418 | 77 | 39391.78 | 3033167.06 | 2024-12-23 | 2024-12-28
PO100435 | 1 | Javelin | Guidance | AeroDynamics Ltd | 5100 | CC172 | 134 | 40036.01 | 5364825.34 | 2024-10-21 | 2024-11-22
PO100436 | 2 | Javelin | Warhead | RayTech Components | 5200 | CC667 | 187 | 22853.68 | 4273638.16 | 2024-02-27 | 2024-04-09
PO100437 | 3 | HIMARS | Composites | AeroDynamics Ltd | 5400 | CC718 | 37 | 39253.37 | 1452374.69 | 2024-01-18 | 2024-02-25
PO100438 | 4 | Javelin | Electronics | DefenseCo Supplies | 5400 | CC313 | 135 | 3044.76 | 411042.6 | 2024-11-05 | 2024-12-03
PO100439 | 5 | HIMARS | Electronics | Precision Metals Inc | 5200 | CC853 | 121 | 13196.77 | 1596809.17 | 2024-02-07 | 2024-03-03
PO100440 | 3 | THAAD | Electronics | AeroDynamics Ltd | 5400 | CC120 | 242 | 44114.11 | 10675614.62 | 2024-04-18 | 2024-05-12
PO100441 | 1 | PAC-3 | Composites | DefenseCo Supplies | 5100 | CC295 | 140 | 12685.36 | 1775950.4 | 2024-11-07 | 2024-12-04
PO100442 | 5 | THAAD | Warhead | AeroDynamics Ltd | 5400 | CC955 | 153 | 41448.81 | 6341667.93 | 2024-10-28 | 2024-12-03
PO100443 | 5 | HIMARS | Hardware | AeroDynamics Ltd | 5100 | CC461 | 58 | 47070.76 | 2730104.08 | 2024-04-06 | 2024-05-01
PO100444 | 2 | THAAD | Hardware | Precision Metals Inc | 5100 | CC646 | 39 | 9894.69 | 385892.91 | 2024-04-27 | 2024-05-06
PO100445 | 5 | PAC-3 | Electronics | Orbital Systems | 5300 | CC513 | 57 | 909.24 | 51826.68 | 2024-10-11 | 2024-11-21
PO100446 | 5 | HIMARS | Hardware | Orbital Systems | 5300 | CC723 | 151 | 21623.03 | 3265077.53 | 2024-09-03 | 2024-10-17
PO100447 | 2 | Javelin | Warhead | Orbital Systems | 5200 | CC705 | 150 | 27183.14 | 4077471 | 2024-07-27 | 2024-09-01
PO100448 | 3 | PAC-3 | Hardware | AeroDynamics Ltd | 5200 | CC214 | 164 | 6141.15 | 1007148.6 | 2024-08-21 | 2024-09-22
PO100449 | 1 | Javelin | Hardware | Precision Metals Inc | 5200 | CC481 | 156 | 28702.63 | 4477610.28 | 2024-12-28 | 2025-01-10
PO100450 | 1 | Javelin | Electronics | Precision Metals Inc | 5300 | CC429 | 168 | 35181.77 | 5910537.36 | 2024-12-19 | 2025-01-05
PO100451 | 2 | Javelin | Warhead | DefenseCo Supplies | 5400 | CC532 | 245 | 6080.89 | 1489818.05 | 2024-10-21 | 2024-11-18
PO100452 | 5 | THAAD | Warhead | DefenseCo Supplies | 5200 | CC404 | 195 | 10414.74 | 2030874.3 | 2024-10-31 | 2024-12-13
PO100453 | 2 | THAAD | Electronics | RayTech Components | 5300 | CC636 | 131 | 28143.75 | 3686831.25 | 2024-04-26 | 2024-06-01
PO100454 | 1 | HIMARS | Electronics | Orbital Systems | 5100 | CC731 | 56 | 41846.86 | 2343424.16 | 2024-03-26 | 2024-04-15
PO100455 | 2 | PAC-3 | Composites | Precision Metals Inc | 5200 | CC844 | 199 | 22701.88 | 4517674.12 | 2024-12-04 | 2024-12-27
PO100456 | 3 | THAAD | Warhead | Precision Metals Inc | 5300 | CC792 | 174 | 19544.35 | 3400716.9 | 2024-08-19 | 2024-09-10
PO100457 | 2 | HIMARS | Propulsion | Orbital Systems | 5300 | CC284 | 104 | 48411.27 | 5034772.08 | 2024-08-07 | 2024-08-29
PO100458 | 3 | THAAD | Warhead | Orbital Systems | 5400 | CC320 | 123 | 2381.17 | 292883.91 | 2024-11-18 | 2024-12-11
PO100459 | 3 | Javelin | Hardware | Precision Metals Inc | 5300 | CC673 | 132 | 23345.87 | 3081654.84 | 2024-11-26 | 2024-12-31
PO100460 | 5 | HIMARS | Guidance | Precision Metals Inc | 5200 | CC161 | 49 | 18818.75 | 922118.75 | 2024-06-07 | 2024-07-15
PO100461 | 2 | HIMARS | Electronics | Orbital Systems | 5400 | CC300 | 58 | 39152.51 | 2270845.58 | 2024-11-13 | 2024-12-26
PO100462 | 4 | HIMARS | Electronics | Precision Metals Inc | 5100 | CC310 | 192 | 35733.48 | 6860828.16 | 2024-02-28 | 2024-03-10
PO100463 | 4 | THAAD | Composites | DefenseCo Supplies | 5200 | CC500 | 144 | 37996.09 | 5471436.96 | 2024-10-03 | 2024-11-02
PO100464 | 3 | Javelin | Warhead | DefenseCo Supplies | 5200 | CC673 | 170 | 15518.5 | 2638145 | 2024-09-25 | 2024-10-10
PO100465 | 1 | THAAD | Warhead | Precision Metals Inc | 5200 | CC705 | 222 | 45414.97 | 10082123.34 | 2024-10-26 | 2024-11-10
PO100466 | 1 | Javelin | Propulsion | AeroDynamics Ltd | 5400 | CC470 | 90 | 22676.12 | 2040850.8 | 2024-11-13 | 2024-12-19
PO100467 | 5 | HIMARS | Hardware | RayTech Components | 5300 | CC294 | 166 | 37474.58 | 6220780.28 | 2024-03-01 | 2024-03-06
PO100468 | 5 | HIMARS | Composites | DefenseCo Supplies | 5200 | CC721 | 13 | 32821.78 | 426683.14 | 2024-10-04 | 2024-10-18
PO100469 | 1 | PAC-3 | Composites | Orbital Systems | 5200 | CC968 | 84 | 18575.27 | 1560322.68 | 2024-01-28 | 2024-02-09
PO100470 | 1 | THAAD | Hardware | DefenseCo Supplies | 5100 | CC707 | 163 | 41260.26 | 6725422.38 | 2024-11-11 | 2024-11-21
PO100471 | 2 | HIMARS | Hardware | Precision Metals Inc | 5400 | CC843 | 157 | 21961.88 | 3448015.16 | 2024-03-17 | 2024-04-28
PO100472 | 3 | Javelin | Guidance | RayTech Components | 5200 | CC992 | 38 | 4972.17 | 188942.46 | 2024-10-02 | 2024-10-18
PO100473 | 5 | THAAD | Guidance | DefenseCo Supplies | 5200 | CC550 | 109 | 23424.83 | 2553306.47 | 2024-12-16 | 2025-01-04
PO100474 | 2 | THAAD | Electronics | Precision Metals Inc | 5400 | CC558 | 187 | 42496.66 | 7946875.42 | 2024-10-30 | 2024-12-08
PO100475 | 3 | THAAD | Composites | Precision Metals Inc | 5200 | CC454 | 3 | 31324.55 | 93973.65 | 2024-12-06 | 2024-12-20
PO100476 | 4 | THAAD | Composites | DefenseCo Supplies | 5100 | CC482 | 19 | 22254.12 | 422828.28 | 2024-03-14 | 2024-04-12
PO100477 | 3 | HIMARS | Guidance | Precision Metals Inc | 5200 | CC794 | 28 | 26501.95 | 742054.6 | 2024-11-10 | 2024-11-19
PO100478 | 3 | THAAD | Composites | AeroDynamics Ltd | 5400 | CC857 | 113 | 23193.05 | 2620814.65 | 2024-06-14 | 2024-07-13
PO100479 | 4 | HIMARS | Guidance | DefenseCo Supplies | 5200 | CC254 | 55 | 43216.16 | 2376888.8 | 2024-03-15 | 2024-04-09
PO100480 | 4 | THAAD | Electronics | Precision Metals Inc | 5300 | CC956 | 233 | 3722.58 | 867361.14 | 2024-12-04 | 2024-12-09
PO100481 | 3 | THAAD | Composites | AeroDynamics Ltd | 5300 | CC820 | 93 | 47450.03 | 4412852.79 | 2024-04-21 | 2024-05-28
PO100482 | 5 | PAC-3 | Composites | Orbital Systems | 5200 | CC265 | 131 | 32041.85 | 4197482.35 | 2024-03-30 | 2024-05-03
PO100483 | 4 | THAAD | Propulsion | DefenseCo Supplies | 5100 | CC841 | 66 | 46085.05 | 3041613.3 | 2024-01-26 | 2024-02-10
PO100484 | 4 | HIMARS | Guidance | Orbital Systems | 5400 | CC128 | 40 | 11732.03 | 469281.2 | 2024-07-27 | 2024-08-20
PO100485 | 1 | PAC-3 | Hardware | Precision Metals Inc | 5300 | CC144 | 187 | 44333.15 | 8290299.05 | 2024-06-03 | 2024-06-30
PO100486 | 5 | PAC-3 | Guidance | Orbital Systems | 5100 | CC333 | 209 | 31225.87 | 6526206.83 | 2024-04-28 | 2024-05-10
PO100487 | 5 | Javelin | Hardware | Orbital Systems | 5400 | CC842 | 53 | 48773.32 | 2584985.96 | 2024-09-29 | 2024-11-02
PO100488 | 2 | PAC-3 | Hardware | Precision Metals Inc | 5200 | CC170 | 108 | 8613.88 | 930299.04 | 2024-09-07 | 2024-10-01
PO100489 | 4 | Javelin | Propulsion | Orbital Systems | 5300 | CC584 | 84 | 48660.57 | 4087487.88 | 2024-05-05 | 2024-06-18
PO100490 | 5 | HIMARS | Guidance | DefenseCo Supplies | 5200 | CC667 | 60 | 41374.26 | 2482455.6 | 2024-01-28 | 2024-03-08
PO100491 | 2 | THAAD | Composites | DefenseCo Supplies | 5200 | CC185 | 4 | 7559.37 | 30237.48 | 2024-06-14 | 2024-07-12
PO100492 | 3 | PAC-3 | Guidance | Orbital Systems | 5200 | CC195 | 190 | 7073.14 | 1343896.6 | 2024-09-22 | 2024-11-05
PO100493 | 1 | HIMARS | Composites | RayTech Components | 5100 | CC346 | 223 | 15496.56 | 3455732.88 | 2024-11-08 | 2024-12-16
PO100494 | 5 | Javelin | Warhead | RayTech Components | 5400 | CC629 | 115 | 49590.7 | 5702930.5 | 2024-04-15 | 2024-05-04
PO100495 | 4 | THAAD | Electronics | Orbital Systems | 5200 | CC830 | 213 | 24597.28 | 5239220.64 | 2024-07-26 | 2024-08-08
PO100496 | 4 | HIMARS | Hardware | Precision Metals Inc | 5400 | CC426 | 249 | 43024.79 | 10713172.71 | 2024-01-18 | 2024-02-07
PO100497 | 4 | PAC-3 | Electronics | DefenseCo Supplies | 5100 | CC948 | 241 | 8980.71 | 2164351.11 | 2024-03-17 | 2024-04-16
PO100498 | 5 | HIMARS | Electronics | DefenseCo Supplies | 5400 | CC286 | 230 | 6799.77 | 1563947.1 | 2024-04-29 | 2024-05-31
PO100499 | 1 | Javelin | Guidance | Orbital Systems | 5300 | CC336 | 246 | 41329.12 | 10166963.52 | 2024-04-05 | 2024-05-17
PO100500 | 5 | Javelin | Hardware | Precision Metals Inc | 5200 | CC486 | 187 | 17039.65 | 3186414.55 | 2024-11-10 | 2024-12-15
PO100501 | 4 | PAC-3 | Warhead | Orbital Systems | 5100 | CC226 | 169 | 12819.14 | 2166434.66 | 2024-07-31 | 2024-08-24
PO100502 | 2 | THAAD | Warhead | AeroDynamics Ltd | 5200 | CC375 | 244 | 37575.72 | 9168475.68 | 2024-09-29 | 2024-10-27
PO100503 | 3 | HIMARS | Propulsion | Precision Metals Inc | 5100 | CC378 | 174 | 30594.59 | 5323458.66 | 2024-11-10 | 2024-12-10
PO100504 | 1 | THAAD | Warhead | RayTech Components | 5400 | CC572 | 189 | 7935.99 | 1499902.11 | 2024-01-02 | 2024-01-24
PO100505 | 5 | Javelin | Warhead | AeroDynamics Ltd | 5100 | CC337 | 94 | 23915.47 | 2248054.18 | 2024-06-19 | 2024-07-14
PO100506 | 5 | HIMARS | Electronics | Precision Metals Inc | 5400 | CC242 | 201 | 23549.43 | 4733435.43 | 2024-12-29 | 2025-02-02
PO100507 | 3 | PAC-3 | Composites | RayTech Components | 5100 | CC407 | 137 | 41999.22 | 5753893.14 | 2024-01-01 | 2024-02-09
PO100508 | 4 | Javelin | Electronics | Orbital Systems | 5100 | CC336 | 206 | 45769.55 | 9428527.3 | 2024-03-12 | 2024-04-12
PO100509 | 1 | THAAD | Guidance | AeroDynamics Ltd | 5200 | CC982 | 139 | 28531.13 | 3965827.07 | 2024-12-16 | 2025-01-06
PO100510 | 5 | HIMARS | Propulsion | DefenseCo Supplies | 5100 | CC952 | 168 | 46474.95 | 7807791.6 | 2024-12-07 | 2025-01-18
PO100511 | 3 | THAAD | Guidance | RayTech Components | 5100 | CC326 | 115 | 17417.92 | 2003060.8 | 2024-10-31 | 2024-11-25
PO100512 | 5 | Javelin | Guidance | Orbital Systems | 5300 | CC372 | 6 | 34005.37 | 204032.22 | 2024-01-28 | 2024-02-03
PO100513 | 4 | PAC-3 | Composites | Orbital Systems | 5200 | CC317 | 177 | 14260.4 | 2524090.8 | 2024-02-27 | 2024-03-15
PO100514 | 3 | Javelin | Electronics | RayTech Components | 5400 | CC346 | 188 | 49507.92 | 9307488.96 | 2024-07-04 | 2024-08-12
PO100515 | 4 | HIMARS | Electronics | AeroDynamics Ltd | 5200 | CC915 | 40 | 27164.89 | 1086595.6 | 2024-07-26 | 2024-08-03
PO100516 | 3 | PAC-3 | Electronics | Orbital Systems | 5300 | CC571 | 119 | 48411.8 | 5761004.2 | 2024-01-25 | 2024-03-03
PO100517 | 3 | Javelin | Hardware | AeroDynamics Ltd | 5100 | CC381 | 148 | 37754.94 | 5587731.12 | 2024-01-10 | 2024-02-02
PO100518 | 1 | HIMARS | Warhead | Precision Metals Inc | 5200 | CC382 | 208 | 39264.26 | 8166966.08 | 2024-06-11 | 2024-06-27
PO100519 | 4 | THAAD | Composites | AeroDynamics Ltd | 5300 | CC261 | 215 | 44258.2 | 9515513 | 2024-12-05 | 2024-12-21
PO100520 | 5 | PAC-3 | Electronics | RayTech Components | 5200 | CC769 | 131 | 17269.85 | 2262350.35 | 2024-12-05 | 2024-12-31
PO100521 | 5 | Javelin | Warhead | RayTech Components | 5400 | CC393 | 143 | 47507.51 | 6793573.93 | 2024-10-28 | 2024-11-26
PO100522 | 4 | HIMARS | Electronics | AeroDynamics Ltd | 5100 | CC169 | 113 | 2501.15 | 282629.95 | 2024-12-29 | 2025-01-25
PO100523 | 2 | PAC-3 | Propulsion | DefenseCo Supplies | 5400 | CC838 | 214 | 26276.37 | 5623143.18 | 2024-07-10 | 2024-07-17
PO100524 | 2 | Javelin | Electronics | Orbital Systems | 5100 | CC811 | 247 | 12883.4 | 3182199.8 | 2024-07-10 | 2024-07-19
PO100525 | 3 | THAAD | Warhead | DefenseCo Supplies | 5400 | CC542 | 237 | 29357.65 | 6957763.05 | 2024-07-15 | 2024-07-28
PO100526 | 2 | HIMARS | Propulsion | RayTech Components | 5400 | CC799 | 51 | 33021.2 | 1684081.2 | 2024-04-17 | 2024-05-03
PO100527 | 2 | THAAD | Guidance | DefenseCo Supplies | 5100 | CC537 | 220 | 49182.47 | 10820143.4 | 2024-04-12 | 2024-05-17
PO100528 | 1 | THAAD | Propulsion | Orbital Systems | 5100 | CC687 | 129 | 23031.97 | 2971124.13 | 2024-02-09 | 2024-03-21
PO100529 | 3 | THAAD | Electronics | AeroDynamics Ltd | 5200 | CC525 | 149 | 37322.68 | 5561079.32 | 2024-01-22 | 2024-03-04
PO100530 | 5 | THAAD | Hardware | RayTech Components | 5100 | CC701 | 141 | 4463.25 | 629318.25 | 2024-12-02 | 2024-12-20
PO100531 | 4 | Javelin | Guidance | DefenseCo Supplies | 5300 | CC921 | 27 | 39129.91 | 1056507.57 | 2024-09-01 | 2024-10-10
PO100532 | 2 | Javelin | Warhead | AeroDynamics Ltd | 5100 | CC506 | 217 | 30183.69 | 6549860.73 | 2024-10-29 | 2024-11-07
PO100533 | 5 | HIMARS | Hardware | Precision Metals Inc | 5400 | CC853 | 146 | 16772.46 | 2448779.16 | 2024-09-05 | 2024-09-23
PO100534 | 3 | PAC-3 | Composites | Precision Metals Inc | 5300 | CC590 | 239 | 33173.44 | 7928452.16 | 2024-12-02 | 2025-01-10
PO100535 | 3 | HIMARS | Composites | Precision Metals Inc | 5400 | CC221 | 176 | 2577.6 | 453657.6 | 2024-11-12 | 2024-12-03
PO100536 | 5 | Javelin | Electronics | Precision Metals Inc | 5400 | CC263 | 141 | 26700.14 | 3764719.74 | 2024-05-07 | 2024-05-25
PO100537 | 5 | HIMARS | Hardware | Orbital Systems | 5400 | CC286 | 208 | 41408.28 | 8612922.24 | 2024-07-08 | 2024-07-16
PO100538 | 3 | Javelin | Composites | DefenseCo Supplies | 5200 | CC386 | 3 | 11761.19 | 35283.57 | 2024-10-06 | 2024-10-25
PO100539 | 3 | PAC-3 | Electronics | DefenseCo Supplies | 5200 | CC875 | 71 | 46731.63 | 3317945.73 | 2024-04-12 | 2024-05-02
PO100540 | 3 | Javelin | Propulsion | AeroDynamics Ltd | 5200 | CC296 | 117 | 21565.78 | 2523196.26 | 2024-02-29 | 2024-04-07
PO100541 | 2 | Javelin | Warhead | DefenseCo Supplies | 5200 | CC733 | 238 | 5603.81 | 1333706.78 | 2024-04-02 | 2024-04-29
PO100542 | 3 | Javelin | Propulsion | RayTech Components | 5100 | CC301 | 212 | 10956.42 | 2322761.04 | 2024-11-18 | 2024-12-03
PO100543 | 3 | THAAD | Composites | Orbital Systems | 5100 | CC908 | 211 | 17453.85 | 3682762.35 | 2024-08-01 | 2024-08-11
PO100544 | 1 | Javelin | Electronics | Orbital Systems | 5200 | CC979 | 247 | 13479.94 | 3329545.18 | 2024-09-07 | 2024-09-14
PO100545 | 5 | HIMARS | Composites | RayTech Components | 5200 | CC212 | 233 | 10105.25 | 2354523.25 | 2024-07-20 | 2024-08-12
PO100546 | 2 | PAC-3 | Warhead | Orbital Systems | 5400 | CC826 | 30 | 38870.45 | 1166113.5 | 2024-08-24 | 2024-09-22
PO100547 | 3 | Javelin | Propulsion | RayTech Components | 5200 | CC413 | 94 | 5237.22 | 492298.68 | 2024-01-25 | 2024-02-12
PO100548 | 1 | HIMARS | Propulsion | AeroDynamics Ltd | 5300 | CC558 | 11 | 41550.01 | 457050.11 | 2024-08-01 | 2024-08-12
PO100549 | 1 | HIMARS | Hardware | AeroDynamics Ltd | 5400 | CC220 | 42 | 46364.09 | 1947291.78 | 2024-11-26 | 2024-12-16
PO100550 | 4 | PAC-3 | Propulsion | Precision Metals Inc | 5100 | CC286 | 90 | 47351.11 | 4261599.9 | 2024-12-29 | 2025-01-14
PO100551 | 4 | THAAD | Composites | AeroDynamics Ltd | 5200 | CC926 | 155 | 35544.58 | 5509409.9 | 2024-03-12 | 2024-03-23
PO100552 | 2 | HIMARS | Warhead | Precision Metals Inc | 5100 | CC162 | 209 | 11497.43 | 2402962.87 | 2024-01-08 | 2024-01-17
PO100553 | 2 | HIMARS | Composites | Orbital Systems | 5200 | CC960 | 175 | 43566.75 | 7624181.25 | 2024-05-30 | 2024-06-19
PO100554 | 5 | PAC-3 | Warhead | Orbital Systems | 5400 | CC480 | 37 | 36444.58 | 1348449.46 | 2024-08-15 | 2024-09-07
PO100555 | 4 | Javelin | Warhead | DefenseCo Supplies | 5300 | CC410 | 244 | 27483.89 | 6706069.16 | 2024-10-07 | 2024-10-17
PO100556 | 3 | Javelin | Hardware | AeroDynamics Ltd | 5100 | CC967 | 30 | 19747.55 | 592426.5 | 2024-02-03 | 2024-02-20
PO100557 | 3 | Javelin | Hardware | DefenseCo Supplies | 5400 | CC633 | 180 | 44810.57 | 8065902.6 | 2024-11-24 | 2025-01-06
PO100558 | 2 | PAC-3 | Hardware | Orbital Systems | 5300 | CC434 | 185 | 7270.1 | 1344968.5 | 2024-10-14 | 2024-10-22
PO100559 | 4 | Javelin | Warhead | Orbital Systems | 5300 | CC737 | 75 | 18183.61 | 1363770.75 | 2024-11-19 | 2024-12-22
PO100560 | 3 | Javelin | Warhead | AeroDynamics Ltd | 5100 | CC717 | 95 | 49423.94 | 4695274.3 | 2024-05-26 | 2024-06-29
PO100561 | 2 | THAAD | Warhead | DefenseCo Supplies | 5300 | CC438 | 95 | 23517.14 | 2234128.3 | 2024-11-17 | 2024-12-01
PO100562 | 3 | Javelin | Composites | RayTech Components | 5400 | CC243 | 16 | 10276.04 | 164416.64 | 2024-09-01 | 2024-10-06
PO100563 | 1 | HIMARS | Electronics | Precision Metals Inc | 5300 | CC440 | 4 | 30258.81 | 121035.24 | 2024-11-01 | 2024-11-17
PO100564 | 2 | THAAD | Guidance | Orbital Systems | 5400 | CC420 | 47 | 10713.35 | 503527.45 | 2024-04-15 | 2024-04-26
PO100565 | 5 | Javelin | Composites | Orbital Systems | 5300 | CC509 | 203 | 48962.79 | 9939446.37 | 2024-06-19 | 2024-07-04
PO100566 | 2 | PAC-3 | Composites | Precision Metals Inc | 5200 | CC894 | 113 | 47210.43 | 5334778.59 | 2024-10-31 | 2024-11-20
PO100567 | 1 | HIMARS | Hardware | Orbital Systems | 5200 | CC895 | 25 | 1164.71 | 29117.75 | 2024-09-22 | 2024-11-05
PO100568 | 2 | THAAD | Electronics | AeroDynamics Ltd | 5300 | CC520 | 246 | 6765.94 | 1664421.24 | 2024-01-22 | 2024-02-15
PO100569 | 1 | PAC-3 | Guidance | RayTech Components | 5400 | CC261 | 160 | 24056.79 | 3849086.4 | 2024-11-17 | 2024-12-03
PO100570 | 4 | HIMARS | Propulsion | RayTech Components | 5200 | CC963 | 249 | 13114.93 | 3265617.57 | 2024-10-02 | 2024-11-14
PO100571 | 2 | Javelin | Electronics | Precision Metals Inc | 5400 | CC775 | 152 | 24756.8 | 3763033.6 | 2024-06-07 | 2024-06-25
PO100572 | 5 | THAAD | Composites | DefenseCo Supplies | 5400 | CC439 | 125 | 1478.04 | 184755 | 2024-04-19 | 2024-05-07
PO100573 | 5 | Javelin | Hardware | AeroDynamics Ltd | 5400 | CC413 | 76 | 7746.7 | 588749.2 | 2024-02-05 | 2024-03-16
PO100574 | 5 | HIMARS | Electronics | RayTech Components | 5100 | CC263 | 148 | 47309.75 | 7001843 | 2024-07-13 | 2024-08-09
PO100575 | 4 | PAC-3 | Guidance | DefenseCo Supplies | 5400 | CC760 | 104 | 6606.79 | 687106.16 | 2024-08-18 | 2024-09-22
PO100576 | 4 | HIMARS | Electronics | DefenseCo Supplies | 5300 | CC241 | 61 | 17300.86 | 1055352.46 | 2024-10-14 | 2024-11-02
PO100577 | 3 | THAAD | Electronics | Orbital Systems | 5200 | CC872 | 109 | 44739.69 | 4876626.21 | 2024-12-08 | 2025-01-21
PO100578 | 5 | Javelin | Guidance | RayTech Components | 5100 | CC386 | 99 | 17990.66 | 1781075.34 | 2024-03-23 | 2024-04-19
PO100579 | 2 | PAC-3 | Composites | Precision Metals Inc | 5100 | CC300 | 29 | 4481.56 | 129965.24 | 2024-04-04 | 2024-04-30
PO100580 | 3 | THAAD | Warhead | Orbital Systems | 5300 | CC700 | 72 | 4974.52 | 358165.44 | 2024-07-30 | 2024-08-26
PO100581 | 1 | PAC-3 | Hardware | Precision Metals Inc | 5100 | CC153 | 218 | 3524.14 | 768262.52 | 2024-01-20 | 2024-01-27
PO100582 | 5 | PAC-3 | Propulsion | DefenseCo Supplies | 5300 | CC228 | 81 | 24579.53 | 1990941.93 | 2024-12-05 | 2024-12-15
PO100583 | 4 | HIMARS | Guidance | RayTech Components | 5300 | CC287 | 163 | 33414.2 | 5446514.6 | 2024-12-29 | 2025-01-14
PO100584 | 5 | THAAD | Composites | RayTech Components | 5300 | CC871 | 243 | 25122.96 | 6104879.28 | 2024-04-11 | 2024-05-12
PO100585 | 3 | PAC-3 | Warhead | DefenseCo Supplies | 5400 | CC540 | 86 | 15549.61 | 1337266.46 | 2024-04-20 | 2024-05-16
PO100586 | 4 | PAC-3 | Composites | AeroDynamics Ltd | 5200 | CC851 | 115 | 24054.93 | 2766316.95 | 2024-10-25 | 2024-11-11
PO100587 | 2 | THAAD | Composites | Precision Metals Inc | 5400 | CC650 | 179 | 29382.99 | 5259555.21 | 2024-09-23 | 2024-10-23
PO100588 | 1 | PAC-3 | Guidance | AeroDynamics Ltd | 5300 | CC374 | 192 | 20108.55 | 3860841.6 | 2024-08-17 | 2024-09-18
PO100589 | 1 | PAC-3 | Guidance | Orbital Systems | 5200 | CC475 | 7 | 32138.04 | 224966.28 | 2024-11-12 | 2024-11-20
PO100590 | 1 | HIMARS | Propulsion | Orbital Systems | 5300 | CC662 | 117 | 26603.27 | 3112582.59 | 2024-11-04 | 2024-12-02
PO100591 | 1 | THAAD | Electronics | DefenseCo Supplies | 5200 | CC665 | 185 | 48335.74 | 8942111.9 | 2024-09-16 | 2024-10-01
PO100592 | 3 | PAC-3 | Hardware | AeroDynamics Ltd | 5300 | CC447 | 182 | 27635.97 | 5029746.54 | 2024-10-05 | 2024-11-06
PO100593 | 3 | PAC-3 | Electronics | AeroDynamics Ltd | 5100 | CC153 | 29 | 17130.44 | 496782.76 | 2024-06-12 | 2024-06-30
PO100594 | 1 | Javelin | Composites | RayTech Components | 5300 | CC819 | 238 | 17897.75 | 4259664.5 | 2024-04-02 | 2024-04-21
PO100595 | 1 | PAC-3 | Hardware | AeroDynamics Ltd | 5300 | CC658 | 181 | 22241.16 | 4025649.96 | 2024-08-31 | 2024-10-12
PO100596 | 3 | Javelin | Hardware | RayTech Components | 5200 | CC268 | 74 | 24001.46 | 1776108.04 | 2024-11-01 | 2024-12-13
PO100597 | 4 | HIMARS | Electronics | RayTech Components | 5400 | CC287 | 162 | 2144.79 | 347455.98 | 2024-05-11 | 2024-06-10
PO100598 | 1 | THAAD | Hardware | AeroDynamics Ltd | 5100 | CC288 | 35 | 6044.77 | 211566.95 | 2024-10-18 | 2024-11-18
PO100599 | 4 | Javelin | Composites | Orbital Systems | 5100 | CC627 | 99 | 7784.41 | 770656.59 | 2024-07-05 | 2024-08-09
PO100600 | 3 | THAAD | Electronics | AeroDynamics Ltd | 5400 | CC138 | 233 | 41464.82 | 9661303.06 | 2024-06-06 | 2024-07-02
PO100601 | 5 | Javelin | Composites | Orbital Systems | 5200 | CC903 | 18 | 15521.87 | 279393.66 | 2024-09-11 | 2024-09-22
PO100602 | 3 | THAAD | Propulsion | AeroDynamics Ltd | 5300 | CC189 | 237 | 19858.27 | 4706409.99 | 2024-02-13 | 2024-02-25
PO100603 | 3 | THAAD | Propulsion | DefenseCo Supplies | 5200 | CC860 | 170 | 24193.58 | 4112908.6 | 2024-08-16 | 2024-09-01
PO100604 | 2 | PAC-3 | Electronics | DefenseCo Supplies | 5400 | CC858 | 29 | 14196.65 | 411702.85 | 2024-07-08 | 2024-07-27
PO100605 | 5 | HIMARS | Warhead | Orbital Systems | 5200 | CC373 | 3 | 9666.86 | 29000.58 | 2024-07-28 | 2024-09-08
PO100606 | 1 | Javelin | Electronics | Orbital Systems | 5300 | CC706 | 122 | 22197.24 | 2708063.28 | 2024-07-28 | 2024-08-05
PO100607 | 3 | Javelin | Warhead | AeroDynamics Ltd | 5400 | CC482 | 134 | 23439.29 | 3140864.86 | 2024-07-03 | 2024-07-28
PO100608 | 5 | HIMARS | Hardware | Orbital Systems | 5400 | CC319 | 179 | 31376.13 | 5616327.27 | 2024-09-21 | 2024-10-17
PO100609 | 5 | PAC-3 | Warhead | AeroDynamics Ltd | 5100 | CC579 | 187 | 11531.94 | 2156472.78 | 2024-10-21 | 2024-11-09
PO100610 | 5 | PAC-3 | Guidance | Precision Metals Inc | 5200 | CC447 | 29 | 19488.68 | 565171.72 | 2024-01-06 | 2024-01-22
PO100611 | 3 | THAAD | Guidance | Precision Metals Inc | 5400 | CC619 | 247 | 9909.6 | 2447671.2 | 2024-06-23 | 2024-07-01
PO100612 | 5 | THAAD | Guidance | DefenseCo Supplies | 5400 | CC954 | 16 | 28409.42 | 454550.72 | 2024-01-09 | 2024-01-27
PO100613 | 3 | THAAD | Electronics | AeroDynamics Ltd | 5100 | CC889 | 152 | 26363.77 | 4007293.04 | 2024-01-01 | 2024-01-15
PO100614 | 1 | HIMARS | Hardware | RayTech Components | 5100 | CC405 | 12 | 49205.57 | 590466.84 | 2024-07-06 | 2024-08-05
PO100615 | 4 | HIMARS | Electronics | Precision Metals Inc | 5200 | CC526 | 25 | 7342.19 | 183554.75 | 2024-05-20 | 2024-06-07
PO100616 | 1 | Javelin | Guidance | Orbital Systems | 5300 | CC540 | 92 | 32180.52 | 2960607.84 | 2024-06-03 | 2024-07-09
PO100617 | 5 | HIMARS | Composites | Orbital Systems | 5100 | CC167 | 46 | 49429.86 | 2273773.56 | 2024-11-18 | 2024-12-18
PO100618 | 5 | THAAD | Warhead | RayTech Components | 5400 | CC217 | 82 | 39926.32 | 3273958.24 | 2024-03-06 | 2024-03-20
PO100619 | 5 | Javelin | Composites | DefenseCo Supplies | 5200 | CC210 | 249 | 32461.03 | 8082796.47 | 2024-05-26 | 2024-07-04
PO100620 | 3 | Javelin | Hardware | DefenseCo Supplies | 5400 | CC827 | 233 | 31628.19 | 7369368.27 | 2024-08-01 | 2024-08-28
PO100621 | 2 | Javelin | Composites | Orbital Systems | 5400 | CC798 | 33 | 41672.44 | 1375190.52 | 2024-06-28 | 2024-08-08
PO100622 | 4 | PAC-3 | Propulsion | Precision Metals Inc | 5400 | CC691 | 38 | 20286.29 | 770879.02 | 2024-12-08 | 2025-01-03
PO100623 | 2 | HIMARS | Guidance | Orbital Systems | 5100 | CC657 | 72 | 8147.15 | 586594.8 | 2024-08-01 | 2024-08-26
PO100624 | 3 | HIMARS | Warhead | RayTech Components | 5100 | CC164 | 134 | 17933.11 | 2403036.74 | 2024-03-04 | 2024-03-31
PO100625 | 3 | PAC-3 | Hardware | DefenseCo Supplies | 5300 | CC757 | 87 | 12379.15 | 1076986.05 | 2024-11-08 | 2024-12-21
PO100626 | 2 | THAAD | Composites | AeroDynamics Ltd | 5400 | CC982 | 47 | 1503.65 | 70671.55 | 2024-06-18 | 2024-06-29
PO100627 | 5 | HIMARS | Composites | Precision Metals Inc | 5200 | CC446 | 137 | 37300.65 | 5110189.05 | 2024-11-08 | 2024-12-13
PO100628 | 1 | Javelin | Warhead | DefenseCo Supplies | 5100 | CC442 | 148 | 13251.32 | 1961195.36 | 2024-04-26 | 2024-05-28
PO100629 | 5 | HIMARS | Electronics | AeroDynamics Ltd | 5100 | CC157 | 242 | 20921.82 | 5063080.44 | 2024-11-26 | 2025-01-07
PO100630 | 3 | PAC-3 | Hardware | AeroDynamics Ltd | 5400 | CC870 | 247 | 28799.07 | 7113370.29 | 2024-08-12 | 2024-09-09
PO100631 | 1 | Javelin | Electronics | Orbital Systems | 5100 | CC443 | 237 | 12867.24 | 3049535.88 | 2024-01-01 | 2024-02-10
PO100632 | 3 | THAAD | Electronics | Orbital Systems | 5200 | CC590 | 226 | 44560.26 | 10070618.76 | 2024-08-13 | 2024-09-15
PO100633 | 1 | PAC-3 | Guidance | RayTech Components | 5400 | CC281 | 243 | 12973.25 | 3152499.75 | 2024-02-11 | 2024-03-05
PO100634 | 1 | Javelin | Composites | AeroDynamics Ltd | 5200 | CC444 | 125 | 29803.96 | 3725495 | 2024-01-21 | 2024-01-31
PO100635 | 4 | HIMARS | Guidance | AeroDynamics Ltd | 5200 | CC641 | 249 | 10896.24 | 2713163.76 | 2024-03-28 | 2024-04-10
PO100636 | 1 | PAC-3 | Electronics | DefenseCo Supplies | 5100 | CC253 | 132 | 13483.39 | 1779807.48 | 2024-05-22 | 2024-06-30
PO100637 | 4 | HIMARS | Warhead | DefenseCo Supplies | 5400 | CC178 | 146 | 44324.22 | 6471336.12 | 2024-04-02 | 2024-04-19
PO100638 | 5 | Javelin | Warhead | AeroDynamics Ltd | 5100 | CC194 | 105 | 44017.68 | 4621856.4 | 2024-07-09 | 2024-07-22
PO100639 | 5 | PAC-3 | Guidance | DefenseCo Supplies | 5100 | CC397 | 141 | 10670.42 | 1504529.22 | 2024-05-20 | 2024-06-05
PO100640 | 5 | Javelin | Composites | RayTech Components | 5400 | CC298 | 130 | 34103.85 | 4433500.5 | 2024-02-29 | 2024-03-27
PO100641 | 4 | PAC-3 | Warhead | AeroDynamics Ltd | 5300 | CC296 | 247 | 7780.72 | 1921837.84 | 2024-10-13 | 2024-11-06
PO100642 | 3 | PAC-3 | Electronics | DefenseCo Supplies | 5200 | CC764 | 13 | 21552.15 | 280177.95 | 2024-08-07 | 2024-08-17
PO100643 | 1 | Javelin | Guidance | AeroDynamics Ltd | 5300 | CC985 | 84 | 37324.43 | 3135252.12 | 2024-08-01 | 2024-08-24
PO100644 | 3 | HIMARS | Electronics | Orbital Systems | 5300 | CC646 | 183 | 7372.28 | 1349127.24 | 2024-12-23 | 2025-02-01
PO100645 | 5 | THAAD | Electronics | Precision Metals Inc | 5400 | CC821 | 220 | 30098.4 | 6621648 | 2024-03-23 | 2024-04-13
PO100646 | 5 | THAAD | Guidance | AeroDynamics Ltd | 5200 | CC647 | 153 | 45612.98 | 6978785.94 | 2024-08-02 | 2024-08-12
PO100647 | 4 | Javelin | Electronics | RayTech Components | 5200 | CC251 | 75 | 25650.88 | 1923816 | 2024-04-24 | 2024-06-01
PO100648 | 3 | PAC-3 | Guidance | DefenseCo Supplies | 5200 | CC701 | 176 | 16608.93 | 2923171.68 | 2024-07-02 | 2024-08-14
PO100649 | 5 | HIMARS | Guidance | Orbital Systems | 5400 | CC835 | 214 | 42960.7 | 9193589.8 | 2024-04-18 | 2024-04-23
PO100650 | 3 | PAC-3 | Hardware | Orbital Systems | 5300 | CC478 | 131 | 8650.71 | 1133243.01 | 2024-04-13 | 2024-04-24
PO100651 | 5 | THAAD | Guidance | Orbital Systems | 5300 | CC652 | 123 | 41863 | 5149149 | 2024-06-26 | 2024-08-05
PO100652 | 4 | THAAD | Guidance | RayTech Components | 5300 | CC531 | 133 | 49066.77 | 6525880.41 | 2024-01-03 | 2024-02-11
PO100653 | 2 | Javelin | Warhead | DefenseCo Supplies | 5300 | CC194 | 17 | 15386.03 | 261562.51 | 2024-04-25 | 2024-05-22
PO100654 | 3 | Javelin | Hardware | AeroDynamics Ltd | 5300 | CC178 | 70 | 17652.35 | 1235664.5 | 2024-02-19 | 2024-03-30
PO100655 | 4 | Javelin | Warhead | RayTech Components | 5200 | CC587 | 96 | 29235.78 | 2806634.88 | 2024-09-12 | 2024-10-16
PO100656 | 2 | THAAD | Warhead | RayTech Components | 5200 | CC545 | 79 | 18020.32 | 1423605.28 | 2024-12-14 | 2025-01-21
PO100657 | 1 | Javelin | Warhead | DefenseCo Supplies | 5100 | CC649 | 14 | 49141.29 | 687978.06 | 2024-11-05 | 2024-11-11
PO100658 | 3 | THAAD | Hardware | RayTech Components | 5400 | CC193 | 93 | 23532.03 | 2188478.79 | 2024-09-01 | 2024-09-27
PO100659 | 5 | THAAD | Propulsion | AeroDynamics Ltd | 5400 | CC724 | 171 | 23036.92 | 3939313.32 | 2024-05-09 | 2024-05-17
PO100660 | 1 | PAC-3 | Propulsion | RayTech Components | 5300 | CC424 | 69 | 46054.4 | 3177753.6 | 2024-01-16 | 2024-02-26
PO100661 | 2 | THAAD | Propulsion | RayTech Components | 5200 | CC364 | 107 | 45771.33 | 4897532.31 | 2024-11-15 | 2024-12-11
PO100662 | 4 | PAC-3 | Warhead | Precision Metals Inc | 5200 | CC708 | 18 | 36208.53 | 651753.54 | 2024-04-06 | 2024-04-11
PO100663 | 4 | HIMARS | Warhead | AeroDynamics Ltd | 5300 | CC782 | 59 | 31161.2 | 1838510.8 | 2024-10-10 | 2024-11-19
PO100664 | 2 | Javelin | Hardware | AeroDynamics Ltd | 5300 | CC981 | 106 | 13906.71 | 1474111.26 | 2024-04-22 | 2024-05-09
PO100665 | 3 | Javelin | Warhead | RayTech Components | 5100 | CC270 | 39 | 40799.84 | 1591193.76 | 2024-03-19 | 2024-04-10
PO100666 | 2 | Javelin | Propulsion | AeroDynamics Ltd | 5200 | CC807 | 67 | 40451.37 | 2710241.79 | 2024-05-25 | 2024-06-05
PO100667 | 3 | THAAD | Composites | RayTech Components | 5400 | CC981 | 107 | 13536.98 | 1448456.86 | 2024-11-29 | 2024-12-12
PO100668 | 3 | PAC-3 | Composites | AeroDynamics Ltd | 5300 | CC795 | 179 | 1159.18 | 207493.22 | 2024-01-20 | 2024-02-17
PO100669 | 1 | Javelin | Electronics | RayTech Components | 5100 | CC635 | 128 | 3642.28 | 466211.84 | 2024-03-23 | 2024-04-18
PO100670 | 3 | PAC-3 | Composites | Precision Metals Inc | 5200 | CC385 | 221 | 43826.27 | 9685605.67 | 2024-07-30 | 2024-09-01
PO100671 | 1 | THAAD | Propulsion | AeroDynamics Ltd | 5100 | CC642 | 158 | 3246.29 | 512913.82 | 2024-09-03 | 2024-09-24
PO100672 | 4 | PAC-3 | Hardware | Precision Metals Inc | 5400 | CC986 | 147 | 16482.54 | 2422933.38 | 2024-10-17 | 2024-10-22
PO100673 | 2 | THAAD | Warhead | DefenseCo Supplies | 5100 | CC278 | 129 | 12536.32 | 1617185.28 | 2024-01-16 | 2024-02-29
PO100674 | 4 | HIMARS | Composites | RayTech Components | 5400 | CC685 | 192 | 45482.81 | 8732699.52 | 2024-07-05 | 2024-08-01
PO100675 | 3 | THAAD | Composites | AeroDynamics Ltd | 5200 | CC551 | 206 | 27341.63 | 5632375.78 | 2024-11-22 | 2024-12-28
PO100676 | 1 | Javelin | Propulsion | AeroDynamics Ltd | 5100 | CC180 | 229 | 41533.61 | 9511196.69 | 2024-05-29 | 2024-07-04
PO100677 | 2 | HIMARS | Electronics | DefenseCo Supplies | 5200 | CC297 | 211 | 19023.82 | 4014026.02 | 2024-02-14 | 2024-03-22
PO100678 | 1 | THAAD | Composites | Precision Metals Inc | 5200 | CC196 | 207 | 35054.93 | 7256370.51 | 2024-02-24 | 2024-03-26
PO100679 | 5 | THAAD | Warhead | AeroDynamics Ltd | 5300 | CC989 | 97 | 25530.05 | 2476414.85 | 2024-10-20 | 2024-11-09
PO100680 | 3 | Javelin | Guidance | Precision Metals Inc | 5300 | CC512 | 34 | 22651.55 | 770152.7 | 2024-06-17 | 2024-07-14
PO100681 | 2 | Javelin | Propulsion | Precision Metals Inc | 5300 | CC716 | 1 | 28202.72 | 28202.72 | 2024-06-28 | 2024-08-03
PO100682 | 2 | PAC-3 | Propulsion | AeroDynamics Ltd | 5200 | CC839 | 149 | 19260.64 | 2869835.36 | 2024-07-27 | 2024-09-02
PO100683 | 3 | PAC-3 | Propulsion | Precision Metals Inc | 5400 | CC815 | 56 | 29428.96 | 1648021.76 | 2024-02-01 | 2024-02-20
PO100684 | 5 | HIMARS | Electronics | Precision Metals Inc | 5200 | CC541 | 130 | 19066.67 | 2478667.1 | 2024-04-23 | 2024-05-04
PO100685 | 1 | PAC-3 | Electronics | Orbital Systems | 5200 | CC611 | 191 | 28895.35 | 5519011.85 | 2024-07-21 | 2024-08-04
PO100686 | 1 | THAAD | Guidance | DefenseCo Supplies | 5200 | CC140 | 173 | 27388.14 | 4738148.22 | 2024-04-29 | 2024-06-05
PO100687 | 1 | HIMARS | Warhead | RayTech Components | 5200 | CC451 | 121 | 12466.14 | 1508402.94 | 2024-05-16 | 2024-05-24
PO100688 | 2 | THAAD | Warhead | AeroDynamics Ltd | 5400 | CC193 | 168 | 35806.11 | 6015426.48 | 2024-12-06 | 2024-12-31
PO100689 | 1 | PAC-3 | Warhead | AeroDynamics Ltd | 5100 | CC373 | 42 | 8519.91 | 357836.22 | 2024-04-10 | 2024-05-02
PO100690 | 5 | THAAD | Hardware | RayTech Components | 5100 | CC834 | 132 | 47615.11 | 6285194.52 | 2024-02-16 | 2024-02-29
PO100691 | 2 | PAC-3 | Guidance | Orbital Systems | 5100 | CC346 | 19 | 4583.69 | 87090.11 | 2024-01-26 | 2024-02-24
PO100692 | 1 | Javelin | Hardware | Orbital Systems | 5100 | CC437 | 224 | 24580.16 | 5505955.84 | 2024-10-24 | 2024-11-16
PO100693 | 3 | HIMARS | Electronics | Orbital Systems | 5100 | CC795 | 63 | 36324.28 | 2288429.64 | 2024-02-18 | 2024-03-19
PO100694 | 5 | HIMARS | Composites | Orbital Systems | 5100 | CC729 | 7 | 17126.21 | 119883.47 | 2024-12-21 | 2025-01-10
PO100695 | 5 | Javelin | Hardware | RayTech Components | 5100 | CC636 | 10 | 3359.72 | 33597.2 | 2024-05-23 | 2024-06-04
PO100696 | 1 | PAC-3 | Composites | Orbital Systems | 5400 | CC170 | 233 | 11151.52 | 2598304.16 | 2024-06-02 | 2024-07-02
PO100697 | 3 | Javelin | Electronics | DefenseCo Supplies | 5400 | CC674 | 195 | 48371.74 | 9432489.3 | 2024-09-09 | 2024-10-09
PO100698 | 2 | Javelin | Hardware | Orbital Systems | 5200 | CC660 | 140 | 48114.58 | 6736041.2 | 2024-09-25 | 2024-10-13
PO100699 | 5 | HIMARS | Propulsion | DefenseCo Supplies | 5400 | CC915 | 228 | 2925.65 | 667048.2 | 2024-08-21 | 2024-09-03
PO100700 | 2 | PAC-3 | Electronics | Orbital Systems | 5200 | CC695 | 20 | 36473.79 | 729475.8 | 2024-07-01 | 2024-07-17
PO100701 | 2 | HIMARS | Composites | Precision Metals Inc | 5200 | CC655 | 238 | 3654.93 | 869873.34 | 2024-07-10 | 2024-08-19
PO100702 | 3 | HIMARS | Composites | Precision Metals Inc | 5200 | CC833 | 117 | 19833.37 | 2320504.29 | 2024-03-11 | 2024-04-16
PO100703 | 3 | Javelin | Composites | Precision Metals Inc | 5100 | CC718 | 101 | 38895.72 | 3928467.72 | 2024-03-09 | 2024-03-24
PO100704 | 5 | Javelin | Warhead | DefenseCo Supplies | 5100 | CC108 | 15 | 7242.22 | 108633.3 | 2024-01-17 | 2024-02-16
PO100705 | 2 | HIMARS | Warhead | RayTech Components | 5300 | CC521 | 72 | 46447.69 | 3344233.68 | 2024-02-04 | 2024-02-22
PO100706 | 1 | HIMARS | Hardware | Orbital Systems | 5300 | CC337 | 34 | 2878.13 | 97856.42 | 2024-05-01 | 2024-05-22
PO100707 | 1 | PAC-3 | Hardware | Precision Metals Inc | 5100 | CC879 | 103 | 30129.01 | 3103288.03 | 2024-12-19 | 2025-01-13
PO100708 | 5 | HIMARS | Propulsion | DefenseCo Supplies | 5300 | CC741 | 12 | 38170.05 | 458040.6 | 2024-12-19 | 2024-12-29
PO100709 | 4 | PAC-3 | Guidance | RayTech Components | 5300 | CC751 | 73 | 20542.51 | 1499603.23 | 2024-09-06 | 2024-09-21
PO100710 | 5 | THAAD | Composites | AeroDynamics Ltd | 5100 | CC311 | 112 | 9492.4 | 1063148.8 | 2024-12-27 | 2025-01-12
PO100711 | 1 | Javelin | Hardware | AeroDynamics Ltd | 5100 | CC953 | 149 | 7058.05 | 1051649.45 | 2024-06-15 | 2024-07-09
PO100712 | 3 | THAAD | Propulsion | DefenseCo Supplies | 5400 | CC185 | 44 | 42647.57 | 1876493.08 | 2024-05-24 | 2024-07-05
PO100713 | 1 | Javelin | Warhead | DefenseCo Supplies | 5100 | CC481 | 39 | 24304.03 | 947857.17 | 2024-01-18 | 2024-02-19
PO100714 | 1 | HIMARS | Composites | AeroDynamics Ltd | 5300 | CC685 | 110 | 41441.83 | 4558601.3 | 2024-02-01 | 2024-03-02
PO100715 | 1 | PAC-3 | Propulsion | RayTech Components | 5400 | CC331 | 126 | 19298.44 | 2431603.44 | 2024-10-13 | 2024-10-24
PO100716 | 5 | THAAD | Propulsion | AeroDynamics Ltd | 5300 | CC328 | 226 | 30931.46 | 6990509.96 | 2024-09-02 | 2024-09-24
PO100717 | 4 | Javelin | Composites | DefenseCo Supplies | 5200 | CC442 | 180 | 49664.94 | 8939689.2 | 2024-07-12 | 2024-08-11
PO100718 | 2 | THAAD | Warhead | RayTech Components | 5400 | CC141 | 147 | 34337.43 | 5047602.21 | 2024-12-15 | 2025-01-07
PO100719 | 2 | PAC-3 | Guidance | RayTech Components | 5400 | CC891 | 34 | 3047.16 | 103603.44 | 2024-01-18 | 2024-01-27
PO100720 | 2 | Javelin | Hardware | DefenseCo Supplies | 5300 | CC896 | 3 | 42639.41 | 127918.23 | 2024-07-04 | 2024-07-20
PO100721 | 2 | PAC-3 | Composites | Orbital Systems | 5200 | CC688 | 229 | 30259.85 | 6929505.65 | 2024-09-14 | 2024-10-25
PO100722 | 2 | Javelin | Composites | Orbital Systems | 5100 | CC643 | 15 | 44021.93 | 660328.95 | 2024-01-05 | 2024-01-20
PO100723 | 4 | HIMARS | Warhead | RayTech Components | 5100 | CC465 | 178 | 42287.3 | 7527139.4 | 2024-09-04 | 2024-09-15
PO100724 | 5 | HIMARS | Guidance | Orbital Systems | 5100 | CC809 | 65 | 10649.59 | 692223.35 | 2024-04-17 | 2024-05-17
PO100725 | 5 | THAAD | Warhead | DefenseCo Supplies | 5400 | CC336 | 237 | 22280.76 | 5280540.12 | 2024-05-30 | 2024-06-19
PO100726 | 4 | PAC-3 | Composites | DefenseCo Supplies | 5200 | CC508 | 44 | 22429.82 | 986912.08 | 2024-12-22 | 2025-01-28
PO100727 | 2 | THAAD | Composites | DefenseCo Supplies | 5200 | CC855 | 182 | 31154.02 | 5670031.64 | 2024-04-08 | 2024-04-17
PO100728 | 2 | Javelin | Propulsion | DefenseCo Supplies | 5300 | CC717 | 109 | 33911.71 | 3696376.39 | 2024-03-18 | 2024-04-02
PO100729 | 3 | Javelin | Composites | DefenseCo Supplies | 5100 | CC170 | 56 | 31466.53 | 1762125.68 | 2024-04-10 | 2024-04-24
PO100730 | 2 | THAAD | Hardware | DefenseCo Supplies | 5100 | CC694 | 182 | 14317.58 | 2605799.56 | 2024-01-04 | 2024-02-08
PO100731 | 3 | HIMARS | Composites | RayTech Components | 5300 | CC709 | 164 | 31536.43 | 5171974.52 | 2024-01-09 | 2024-01-31
PO100732 | 4 | PAC-3 | Hardware | RayTech Components | 5300 | CC325 | 105 | 29754.55 | 3124227.75 | 2024-12-14 | 2025-01-02
PO100733 | 1 | Javelin | Composites | Orbital Systems | 5100 | CC965 | 234 | 18625.37 | 4358336.58 | 2024-12-17 | 2025-01-16
PO100734 | 4 | HIMARS | Guidance | Precision Metals Inc | 5400 | CC785 | 170 | 33783.38 | 5743174.6 | 2024-03-30 | 2024-05-11
PO100735 | 3 | THAAD | Guidance | RayTech Components | 5400 | CC298 | 215 | 615.81 | 132399.15 | 2024-08-19 | 2024-09-23
PO100736 | 4 | PAC-3 | Propulsion | RayTech Components | 5400 | CC573 | 80 | 26923.73 | 2153898.4 | 2024-01-27 | 2024-02-04
PO100737 | 5 | Javelin | Composites | Precision Metals Inc | 5200 | CC468 | 86 | 43216.14 | 3716588.04 | 2024-08-29 | 2024-09-14
PO100738 | 4 | HIMARS | Composites | Orbital Systems | 5300 | CC797 | 87 | 8132.79 | 707552.73 | 2024-03-24 | 2024-04-12
PO100739 | 4 | HIMARS | Warhead | DefenseCo Supplies | 5300 | CC244 | 242 | 42012.8 | 10167097.6 | 2024-02-14 | 2024-03-07
PO100740 | 3 | HIMARS | Composites | Orbital Systems | 5300 | CC464 | 44 | 11567.21 | 508957.24 | 2024-04-26 | 2024-05-04
PO100741 | 2 | Javelin | Propulsion | DefenseCo Supplies | 5300 | CC877 | 224 | 24390.22 | 5463409.28 | 2024-08-18 | 2024-08-27
PO100742 | 1 | Javelin | Propulsion | Precision Metals Inc | 5400 | CC227 | 179 | 26197.16 | 4689291.64 | 2024-07-11 | 2024-08-12
PO100743 | 4 | PAC-3 | Hardware | DefenseCo Supplies | 5200 | CC824 | 49 | 1336.87 | 65506.63 | 2024-03-09 | 2024-04-13
PO100744 | 1 | THAAD | Hardware | Precision Metals Inc | 5300 | CC246 | 228 | 28206.28 | 6431031.84 | 2024-05-20 | 2024-06-07
PO100745 | 1 | Javelin | Warhead | Precision Metals Inc | 5100 | CC903 | 122 | 12730.96 | 1553177.12 | 2024-04-04 | 2024-04-14
PO100746 | 4 | THAAD | Propulsion | Precision Metals Inc | 5100 | CC191 | 127 | 3097.53 | 393386.31 | 2024-08-25 | 2024-09-21
PO100747 | 3 | HIMARS | Hardware | RayTech Components | 5400 | CC616 | 120 | 23744.36 | 2849323.2 | 2024-07-16 | 2024-08-18
PO100748 | 3 | HIMARS | Electronics | RayTech Components | 5100 | CC486 | 170 | 29032.46 | 4935518.2 | 2024-08-20 | 2024-10-03
PO100749 | 3 | THAAD | Warhead | DefenseCo Supplies | 5300 | CC535 | 172 | 4576.61 | 787176.92 | 2024-07-02 | 2024-07-29
PO100750 | 2 | THAAD | Warhead | RayTech Components | 5300 | CC300 | 81 | 31354.5 | 2539714.5 | 2024-10-01 | 2024-10-24
PO100751 | 3 | Javelin | Guidance | Orbital Systems | 5100 | CC116 | 27 | 13067.19 | 352814.13 | 2024-03-03 | 2024-04-12
PO100752 | 5 | THAAD | Warhead | AeroDynamics Ltd | 5100 | CC857 | 199 | 26782.85 | 5329787.15 | 2024-02-05 | 2024-03-20
PO100753 | 4 | HIMARS | Hardware | RayTech Components | 5100 | CC769 | 204 | 42289.36 | 8627029.44 | 2024-10-11 | 2024-10-24
PO100754 | 3 | PAC-3 | Hardware | DefenseCo Supplies | 5200 | CC156 | 211 | 30664.25 | 6470156.75 | 2024-01-17 | 2024-02-20
PO100755 | 3 | PAC-3 | Electronics | RayTech Components | 5300 | CC387 | 9 | 39143.55 | 352291.95 | 2024-07-06 | 2024-08-14
PO100756 | 3 | PAC-3 | Warhead | Orbital Systems | 5400 | CC420 | 213 | 11413.05 | 2430979.65 | 2024-05-08 | 2024-05-22
PO100757 | 2 | PAC-3 | Hardware | Orbital Systems | 5200 | CC245 | 112 | 48356.68 | 5415948.16 | 2024-01-27 | 2024-02-28
PO100758 | 4 | PAC-3 | Electronics | DefenseCo Supplies | 5200 | CC527 | 72 | 29259.51 | 2106684.72 | 2024-09-10 | 2024-10-18
PO100759 | 2 | Javelin | Composites | Precision Metals Inc | 5300 | CC492 | 201 | 12388.77 | 2490142.77 | 2024-09-11 | 2024-10-20
PO100760 | 3 | THAAD | Hardware | Orbital Systems | 5200 | CC103 | 167 | 48339.46 | 8072689.82 | 2024-07-22 | 2024-07-28
PO100761 | 1 | Javelin | Hardware | Orbital Systems | 5100 | CC777 | 55 | 2702.4 | 148632 | 2024-03-28 | 2024-04-26
PO100762 | 2 | PAC-3 | Electronics | Orbital Systems | 5200 | CC232 | 108 | 9814.83 | 1060001.64 | 2024-12-23 | 2025-01-08
PO100763 | 3 | Javelin | Propulsion | Orbital Systems | 5200 | CC116 | 196 | 20404.13 | 3999209.48 | 2024-10-23 | 2024-11-27
PO100764 | 4 | HIMARS | Guidance | AeroDynamics Ltd | 5200 | CC597 | 230 | 49327.75 | 11345382.5 | 2024-06-27 | 2024-08-04
PO100765 | 3 | PAC-3 | Hardware | AeroDynamics Ltd | 5100 | CC515 | 195 | 46906.83 | 9146831.85 | 2024-12-07 | 2024-12-21
PO100766 | 2 | PAC-3 | Warhead | Orbital Systems | 5100 | CC787 | 145 | 31106.68 | 4510468.6 | 2024-11-17 | 2024-11-25
PO100767 | 3 | PAC-3 | Electronics | Orbital Systems | 5200 | CC822 | 69 | 36189.97 | 2497107.93 | 2024-08-06 | 2024-08-23
PO100768 | 3 | THAAD | Hardware | Orbital Systems | 5400 | CC582 | 3 | 22358.68 | 67076.04 | 2024-12-22 | 2025-02-04
PO100769 | 1 | PAC-3 | Composites | RayTech Components | 5400 | CC560 | 68 | 37393.51 | 2542758.68 | 2024-05-20 | 2024-06-20
PO100770 | 3 | HIMARS | Electronics | Precision Metals Inc | 5100 | CC869 | 249 | 38941.45 | 9696421.05 | 2024-03-06 | 2024-04-07
PO100771 | 4 | PAC-3 | Propulsion | Precision Metals Inc | 5300 | CC934 | 227 | 40850.59 | 9273083.93 | 2024-08-03 | 2024-08-12
PO100772 | 1 | PAC-3 | Warhead | RayTech Components | 5100 | CC792 | 237 | 30581.67 | 7247855.79 | 2024-04-29 | 2024-05-13
PO100773 | 5 | THAAD | Hardware | DefenseCo Supplies | 5300 | CC358 | 120 | 16855.39 | 2022646.8 | 2024-01-11 | 2024-01-22
PO100774 | 5 | HIMARS | Propulsion | AeroDynamics Ltd | 5400 | CC261 | 67 | 2795.48 | 187297.16 | 2024-03-15 | 2024-03-26
PO100775 | 1 | Javelin | Hardware | RayTech Components | 5300 | CC515 | 20 | 16309.79 | 326195.8 | 2024-07-17 | 2024-08-29
PO100776 | 4 | THAAD | Guidance | DefenseCo Supplies | 5300 | CC190 | 238 | 38849.89 | 9246273.82 | 2024-05-09 | 2024-06-04
PO100777 | 2 | THAAD | Composites | RayTech Components | 5100 | CC683 | 165 | 38297.62 | 6319107.3 | 2024-10-15 | 2024-11-10
PO100778 | 2 | PAC-3 | Warhead | AeroDynamics Ltd | 5200 | CC473 | 117 | 43342.64 | 5071088.88 | 2024-08-30 | 2024-10-04
PO100779 | 3 | PAC-3 | Propulsion | Precision Metals Inc | 5400 | CC399 | 82 | 11211.29 | 919325.78 | 2024-01-16 | 2024-02-27
PO100780 | 5 | Javelin | Composites | AeroDynamics Ltd | 5200 | CC780 | 208 | 5558.91 | 1156253.28 | 2024-04-01 | 2024-05-14
PO100781 | 2 | HIMARS | Warhead | Precision Metals Inc | 5200 | CC413 | 237 | 2703.12 | 640639.44 | 2024-05-07 | 2024-05-18
PO100782 | 2 | PAC-3 | Warhead | Precision Metals Inc | 5200 | CC552 | 215 | 41101.84 | 8836895.6 | 2024-02-22 | 2024-03-12
PO100783 | 4 | HIMARS | Guidance | RayTech Components | 5400 | CC448 | 182 | 32045.62 | 5832302.84 | 2024-06-27 | 2024-08-09
PO100784 | 1 | Javelin | Guidance | DefenseCo Supplies | 5400 | CC622 | 97 | 49910.45 | 4841313.65 | 2024-07-21 | 2024-08-21
PO100785 | 3 | THAAD | Hardware | AeroDynamics Ltd | 5300 | CC263 | 203 | 34127.43 | 6927868.29 | 2024-05-02 | 2024-05-07
PO100786 | 2 | PAC-3 | Composites | RayTech Components | 5100 | CC142 | 230 | 29521.19 | 6789873.7 | 2024-07-09 | 2024-07-15
PO100787 | 5 | Javelin | Composites | DefenseCo Supplies | 5400 | CC680 | 9 | 21488.01 | 193392.09 | 2024-07-06 | 2024-08-17
PO100788 | 2 | PAC-3 | Propulsion | AeroDynamics Ltd | 5400 | CC775 | 246 | 46591.08 | 11461405.68 | 2024-11-21 | 2024-11-28
PO100789 | 5 | THAAD | Hardware | AeroDynamics Ltd | 5100 | CC445 | 230 | 15519.82 | 3569558.6 | 2024-01-26 | 2024-02-07
PO100790 | 3 | Javelin | Guidance | RayTech Components | 5400 | CC520 | 3 | 43517.37 | 130552.11 | 2024-12-16 | 2025-01-02
PO100791 | 3 | THAAD | Propulsion | Precision Metals Inc | 5200 | CC189 | 186 | 28744.84 | 5346540.24 | 2024-12-23 | 2025-01-21
PO100792 | 2 | HIMARS | Electronics | DefenseCo Supplies | 5300 | CC931 | 230 | 5318.47 | 1223248.1 | 2024-12-06 | 2024-12-30
PO100793 | 4 | Javelin | Propulsion | RayTech Components | 5100 | CC876 | 15 | 34268.46 | 514026.9 | 2024-10-11 | 2024-10-31
PO100794 | 4 | HIMARS | Warhead | DefenseCo Supplies | 5200 | CC938 | 151 | 19980.38 | 3017037.38 | 2024-04-02 | 2024-04-22
PO100795 | 5 | HIMARS | Hardware | DefenseCo Supplies | 5100 | CC604 | 73 | 14381.9 | 1049878.7 | 2024-03-31 | 2024-04-28
PO100796 | 2 | Javelin | Warhead | Precision Metals Inc | 5100 | CC319 | 72 | 37148.79 | 2674712.88 | 2024-02-11 | 2024-02-22
PO100797 | 2 | HIMARS | Electronics | Precision Metals Inc | 5200 | CC913 | 66 | 33890.74 | 2236788.84 | 2024-05-08 | 2024-06-04
PO100798 | 5 | Javelin | Composites | RayTech Components | 5200 | CC224 | 67 | 30212.25 | 2024220.75 | 2024-11-09 | 2024-11-19
PO100799 | 4 | Javelin | Propulsion | AeroDynamics Ltd | 5200 | CC698 | 2 | 3046.64 | 6093.28 | 2024-10-19 | 2024-11-12
PO100800 | 3 | THAAD | Electronics | RayTech Components | 5300 | CC996 | 117 | 1912.82 | 223799.94 | 2024-04-14 | 2024-04-21
PO100801 | 4 | HIMARS | Hardware | Orbital Systems | 5100 | CC944 | 193 | 978.69 | 188887.17 | 2024-02-04 | 2024-03-03
PO100802 | 2 | HIMARS | Guidance | RayTech Components | 5300 | CC306 | 144 | 28802.97 | 4147627.68 | 2024-09-23 | 2024-09-28
PO100803 | 3 | PAC-3 | Composites | Precision Metals Inc | 5100 | CC582 | 141 | 49208.45 | 6938391.45 | 2024-04-12 | 2024-05-09
PO100804 | 2 | PAC-3 | Guidance | Orbital Systems | 5300 | CC148 | 26 | 10034.19 | 260888.94 | 2024-06-24 | 2024-07-13
PO100805 | 4 | THAAD | Composites | Orbital Systems | 5200 | CC728 | 164 | 9713.84 | 1593069.76 | 2024-11-28 | 2024-12-03
PO100806 | 5 | HIMARS | Guidance | Orbital Systems | 5100 | CC538 | 217 | 25860.52 | 5611732.84 | 2024-03-23 | 2024-03-28
PO100807 | 4 | HIMARS | Guidance | Precision Metals Inc | 5100 | CC471 | 101 | 5106.1 | 515716.1 | 2024-06-12 | 2024-06-20
PO100808 | 4 | HIMARS | Warhead | AeroDynamics Ltd | 5200 | CC563 | 169 | 18453.49 | 3118639.81 | 2024-03-06 | 2024-03-31
PO100809 | 3 | HIMARS | Composites | DefenseCo Supplies | 5200 | CC701 | 85 | 21691.44 | 1843772.4 | 2024-07-06 | 2024-08-10
PO100810 | 3 | THAAD | Hardware | RayTech Components | 5100 | CC613 | 244 | 590.33 | 144040.52 | 2024-02-28 | 2024-04-05
PO100811 | 2 | Javelin | Propulsion | Precision Metals Inc | 5400 | CC613 | 243 | 11374.73 | 2764059.39 | 2024-05-02 | 2024-06-12
PO100812 | 1 | HIMARS | Composites | Orbital Systems | 5100 | CC490 | 14 | 22028.81 | 308403.34 | 2024-12-20 | 2024-12-29
PO100813 | 4 | Javelin | Propulsion | AeroDynamics Ltd | 5300 | CC948 | 69 | 43768.5 | 3020026.5 | 2024-05-16 | 2024-06-22
PO100814 | 2 | HIMARS | Propulsion | RayTech Components | 5200 | CC796 | 29 | 31750.64 | 920768.56 | 2024-05-22 | 2024-06-01
PO100815 | 3 | THAAD | Warhead | Orbital Systems | 5200 | CC853 | 185 | 5004.07 | 925752.95 | 2024-08-18 | 2024-09-07
PO100816 | 2 | Javelin | Guidance | Precision Metals Inc | 5200 | CC161 | 106 | 5595.66 | 593139.96 | 2024-12-27 | 2025-01-18
PO100817 | 4 | PAC-3 | Composites | AeroDynamics Ltd | 5400 | CC412 | 230 | 4070.59 | 936235.7 | 2024-12-18 | 2025-01-19
PO100818 | 1 | THAAD | Composites | AeroDynamics Ltd | 5400 | CC473 | 69 | 48877.55 | 3372550.95 | 2024-05-16 | 2024-06-21
PO100819 | 1 | Javelin | Guidance | AeroDynamics Ltd | 5400 | CC128 | 131 | 10386.84 | 1360676.04 | 2024-09-09 | 2024-10-13
PO100820 | 1 | Javelin | Propulsion | Precision Metals Inc | 5200 | CC679 | 25 | 35520.97 | 888024.25 | 2024-08-18 | 2024-09-26
PO100821 | 2 | Javelin | Warhead | RayTech Components | 5400 | CC675 | 31 | 29143.24 | 903440.44 | 2024-05-09 | 2024-06-14
PO100822 | 2 | THAAD | Hardware | DefenseCo Supplies | 5200 | CC205 | 44 | 30654.29 | 1348788.76 | 2024-11-07 | 2024-12-06
PO100823 | 3 | THAAD | Hardware | Precision Metals Inc | 5100 | CC614 | 26 | 31837.75 | 827781.5 | 2024-02-22 | 2024-03-03
PO100824 | 2 | HIMARS | Propulsion | RayTech Components | 5200 | CC815 | 241 | 35818.9 | 8632354.9 | 2024-01-11 | 2024-02-23
PO100825 | 2 | Javelin | Propulsion | DefenseCo Supplies | 5400 | CC715 | 180 | 1079.41 | 194293.8 | 2024-10-04 | 2024-11-07
PO100826 | 1 | PAC-3 | Warhead | Orbital Systems | 5200 | CC363 | 98 | 8334.93 | 816823.14 | 2024-11-24 | 2024-12-18
PO100827 | 2 | PAC-3 | Warhead | Precision Metals Inc | 5300 | CC995 | 72 | 34567.11 | 2488831.92 | 2024-02-09 | 2024-03-16
PO100828 | 3 | PAC-3 | Hardware | Precision Metals Inc | 5400 | CC781 | 157 | 21278.66 | 3340749.62 | 2024-06-17 | 2024-07-24
PO100829 | 5 | THAAD | Guidance | RayTech Components | 5300 | CC627 | 23 | 19299.42 | 443886.66 | 2024-12-17 | 2025-01-02
PO100830 | 1 | Javelin | Composites | DefenseCo Supplies | 5100 | CC788 | 26 | 29982.21 | 779537.46 | 2024-09-25 | 2024-10-27
PO100831 | 1 | PAC-3 | Electronics | Precision Metals Inc | 5200 | CC853 | 117 | 31433.43 | 3677711.31 | 2024-05-23 | 2024-06-09
PO100832 | 2 | Javelin | Electronics | RayTech Components | 5200 | CC997 | 113 | 43480.72 | 4913321.36 | 2024-02-19 | 2024-04-01
PO100833 | 2 | HIMARS | Propulsion | Precision Metals Inc | 5100 | CC171 | 220 | 9817.71 | 2159896.2 | 2024-09-03 | 2024-10-06
PO100834 | 2 | Javelin | Hardware | AeroDynamics Ltd | 5300 | CC751 | 99 | 31945.02 | 3162556.98 | 2024-02-20 | 2024-03-18
PO100835 | 4 | THAAD | Warhead | DefenseCo Supplies | 5100 | CC493 | 245 | 15294.19 | 3747076.55 | 2024-01-09 | 2024-01-28
PO100836 | 2 | Javelin | Electronics | DefenseCo Supplies | 5200 | CC150 | 186 | 21091.45 | 3923009.7 | 2024-08-17 | 2024-08-24
PO100837 | 3 | HIMARS | Guidance | RayTech Components | 5300 | CC422 | 210 | 48300.37 | 10143077.7 | 2024-05-12 | 2024-05-19
PO100838 | 4 | THAAD | Hardware | Orbital Systems | 5100 | CC228 | 91 | 492.2 | 44790.2 | 2024-01-29 | 2024-02-20
PO100839 | 4 | THAAD | Electronics | AeroDynamics Ltd | 5100 | CC272 | 208 | 49403.69 | 10275967.52 | 2024-04-08 | 2024-05-04
PO100840 | 2 | PAC-3 | Propulsion | DefenseCo Supplies | 5300 | CC595 | 246 | 2317.6 | 570129.6 | 2024-12-16 | 2025-01-05
PO100841 | 5 | THAAD | Guidance | AeroDynamics Ltd | 5400 | CC314 | 66 | 34092.47 | 2250103.02 | 2024-08-19 | 2024-09-18
PO100842 | 1 | PAC-3 | Propulsion | RayTech Components | 5400 | CC932 | 181 | 31221.71 | 5651129.51 | 2024-12-11 | 2025-01-02
PO100843 | 4 | Javelin | Warhead | RayTech Components | 5100 | CC504 | 27 | 47370.86 | 1279013.22 | 2024-07-16 | 2024-08-25
PO100844 | 2 | THAAD | Electronics | Precision Metals Inc | 5400 | CC605 | 244 | 10976.59 | 2678287.96 | 2024-08-18 | 2024-09-03
PO100845 | 1 | HIMARS | Hardware | DefenseCo Supplies | 5100 | CC184 | 11 | 9348.93 | 102838.23 | 2024-12-12 | 2024-12-18
PO100846 | 1 | PAC-3 | Hardware | DefenseCo Supplies | 5300 | CC319 | 188 | 2468.26 | 464032.88 | 2024-12-08 | 2024-12-14
PO100847 | 5 | PAC-3 | Guidance | AeroDynamics Ltd | 5300 | CC200 | 21 | 17248.31 | 362214.51 | 2024-06-28 | 2024-07-23
PO100848 | 1 | HIMARS | Warhead | Orbital Systems | 5200 | CC636 | 130 | 38335.78 | 4983651.4 | 2024-01-26 | 2024-02-05
PO100849 | 1 | THAAD | Guidance | RayTech Components | 5100 | CC918 | 5 | 43651.63 | 218258.15 | 2024-02-17 | 2024-03-17
PO100850 | 4 | PAC-3 | Guidance | Orbital Systems | 5200 | CC360 | 226 | 31434.94 | 7104296.44 | 2024-07-23 | 2024-07-30
PO100851 | 4 | THAAD | Composites | DefenseCo Supplies | 5400 | CC203 | 246 | 43355.94 | 10665561.24 | 2024-08-03 | 2024-08-27
PO100852 | 4 | HIMARS | Propulsion | Orbital Systems | 5400 | CC816 | 109 | 281.22 | 30652.98 | 2024-03-29 | 2024-05-04
PO100853 | 1 | THAAD | Propulsion | AeroDynamics Ltd | 5100 | CC799 | 224 | 39498.47 | 8847657.28 | 2024-10-18 | 2024-10-27
PO100854 | 3 | Javelin | Propulsion | RayTech Components | 5200 | CC874 | 4 | 29780.37 | 119121.48 | 2024-02-29 | 2024-03-20
PO100855 | 5 | HIMARS | Propulsion | AeroDynamics Ltd | 5100 | CC762 | 245 | 5513.38 | 1350778.1 | 2024-10-15 | 2024-11-13
PO100856 | 5 | THAAD | Electronics | Precision Metals Inc | 5100 | CC285 | 142 | 26581.06 | 3774510.52 | 2024-06-06 | 2024-06-29
PO100857 | 1 | PAC-3 | Warhead | AeroDynamics Ltd | 5300 | CC545 | 238 | 3007.79 | 715854.02 | 2024-01-18 | 2024-01-31
PO100858 | 4 | HIMARS | Warhead | RayTech Components | 5300 | CC830 | 70 | 39749.27 | 2782448.9 | 2024-04-10 | 2024-05-18
PO100859 | 1 | THAAD | Composites | AeroDynamics Ltd | 5200 | CC443 | 85 | 5536.73 | 470622.05 | 2024-08-05 | 2024-09-08
PO100860 | 1 | HIMARS | Guidance | AeroDynamics Ltd | 5400 | CC523 | 12 | 15100.03 | 181200.36 | 2024-01-21 | 2024-03-01
PO100861 | 3 | HIMARS | Electronics | Precision Metals Inc | 5400 | CC764 | 66 | 4061.96 | 268089.36 | 2024-11-12 | 2024-12-24
PO100862 | 5 | HIMARS | Hardware | RayTech Components | 5300 | CC868 | 101 | 10447.72 | 1055219.72 | 2024-08-13 | 2024-09-01
PO100863 | 3 | Javelin | Electronics | AeroDynamics Ltd | 5200 | CC810 | 46 | 41090.73 | 1890173.58 | 2024-01-31 | 2024-02-28
PO100864 | 5 | PAC-3 | Warhead | AeroDynamics Ltd | 5400 | CC372 | 142 | 24778.25 | 3518511.5 | 2024-09-12 | 2024-10-10
PO100865 | 1 | PAC-3 | Hardware | Precision Metals Inc | 5100 | CC286 | 32 | 1973.87 | 63163.84 | 2024-02-06 | 2024-03-07
PO100866 | 3 | HIMARS | Guidance | Orbital Systems | 5200 | CC973 | 86 | 2838.18 | 244083.48 | 2024-02-22 | 2024-03-25
PO100867 | 3 | PAC-3 | Guidance | RayTech Components | 5400 | CC199 | 222 | 15178.34 | 3369591.48 | 2024-01-15 | 2024-02-19
PO100868 | 4 | THAAD | Warhead | DefenseCo Supplies | 5200 | CC718 | 154 | 15845.5 | 2440207 | 2024-03-24 | 2024-04-12
PO100869 | 2 | HIMARS | Hardware | AeroDynamics Ltd | 5200 | CC890 | 59 | 40140.84 | 2368309.56 | 2024-11-26 | 2024-12-28
PO100870 | 3 | PAC-3 | Warhead | Precision Metals Inc | 5100 | CC373 | 183 | 4988.63 | 912919.29 | 2024-04-27 | 2024-05-11
PO100871 | 3 | THAAD | Guidance | Precision Metals Inc | 5300 | CC975 | 204 | 8876.45 | 1810795.8 | 2024-03-18 | 2024-04-19
PO100872 | 4 | PAC-3 | Electronics | DefenseCo Supplies | 5200 | CC270 | 15 | 7018.8 | 105282 | 2024-03-26 | 2024-04-20
PO100873 | 1 | HIMARS | Composites | AeroDynamics Ltd | 5300 | CC240 | 69 | 12919.52 | 891446.88 | 2024-11-29 | 2024-12-11
PO100874 | 3 | THAAD | Guidance | Precision Metals Inc | 5100 | CC760 | 186 | 15305.5 | 2846823 | 2024-08-30 | 2024-09-20
PO100875 | 5 | PAC-3 | Propulsion | Precision Metals Inc | 5400 | CC711 | 12 | 10085.09 | 121021.08 | 2024-09-14 | 2024-10-03
PO100876 | 3 | THAAD | Hardware | Orbital Systems | 5200 | CC527 | 158 | 40184.2 | 6349103.6 | 2024-11-21 | 2024-12-19
PO100877 | 1 | Javelin | Warhead | AeroDynamics Ltd | 5400 | CC146 | 207 | 34673.39 | 7177391.73 | 2024-09-02 | 2024-09-30
PO100878 | 5 | Javelin | Composites | Orbital Systems | 5100 | CC462 | 156 | 30643.59 | 4780400.04 | 2024-07-17 | 2024-08-13
PO100879 | 2 | Javelin | Guidance | AeroDynamics Ltd | 5300 | CC215 | 93 | 46351.61 | 4310699.73 | 2024-07-28 | 2024-08-15
PO100880 | 1 | HIMARS | Propulsion | DefenseCo Supplies | 5100 | CC555 | 132 | 17697.81 | 2336110.92 | 2024-09-17 | 2024-10-24
PO100881 | 4 | Javelin | Hardware | AeroDynamics Ltd | 5100 | CC392 | 226 | 18239.96 | 4122230.96 | 2024-04-01 | 2024-05-14
PO100882 | 4 | PAC-3 | Hardware | DefenseCo Supplies | 5200 | CC585 | 132 | 3752.67 | 495352.44 | 2024-12-29 | 2025-01-27
PO100883 | 3 | THAAD | Guidance | Orbital Systems | 5300 | CC466 | 234 | 48610.95 | 11374962.3 | 2024-03-23 | 2024-04-07
PO100884 | 1 | PAC-3 | Warhead | AeroDynamics Ltd | 5200 | CC502 | 58 | 25139.45 | 1458088.1 | 2024-04-24 | 2024-05-16
PO100885 | 3 | HIMARS | Warhead | AeroDynamics Ltd | 5100 | CC983 | 78 | 4535.25 | 353749.5 | 2024-02-08 | 2024-02-27
PO100886 | 2 | HIMARS | Propulsion | Orbital Systems | 5300 | CC246 | 28 | 33258.64 | 931241.92 | 2024-07-24 | 2024-08-30
PO100887 | 3 | PAC-3 | Hardware | Precision Metals Inc | 5100 | CC204 | 210 | 42166.28 | 8854918.8 | 2024-09-14 | 2024-09-30
PO100888 | 1 | PAC-3 | Composites | DefenseCo Supplies | 5300 | CC321 | 2 | 46436.53 | 92873.06 | 2024-09-14 | 2024-10-17
PO100889 | 4 | Javelin | Propulsion | Orbital Systems | 5300 | CC811 | 101 | 31191.35 | 3150326.35 | 2024-12-18 | 2024-12-28
PO100890 | 5 | PAC-3 | Warhead | Precision Metals Inc | 5400 | CC254 | 1 | 35751.97 | 35751.97 | 2024-10-15 | 2024-11-28
PO100891 | 5 | THAAD | Hardware | RayTech Components | 5200 | CC709 | 137 | 7353.59 | 1007441.83 | 2024-08-29 | 2024-09-09
PO100892 | 3 | Javelin | Composites | AeroDynamics Ltd | 5100 | CC422 | 190 | 4392.07 | 834493.3 | 2024-05-31 | 2024-07-08
PO100893 | 2 | HIMARS | Guidance | Precision Metals Inc | 5100 | CC401 | 38 | 28388.78 | 1078773.64 | 2024-08-06 | 2024-09-07
PO100894 | 1 | HIMARS | Composites | RayTech Components | 5100 | CC786 | 110 | 33618.68 | 3698054.8 | 2024-08-08 | 2024-08-21
PO100895 | 3 | HIMARS | Electronics | DefenseCo Supplies | 5100 | CC504 | 186 | 32474.07 | 6040177.02 | 2024-09-22 | 2024-10-02
PO100896 | 1 | THAAD | Warhead | RayTech Components | 5400 | CC924 | 239 | 4303.33 | 1028495.87 | 2024-01-10 | 2024-01-23
PO100897 | 5 | THAAD | Guidance | Precision Metals Inc | 5400 | CC788 | 177 | 48951.25 | 8664371.25 | 2024-04-27 | 2024-06-06
PO100898 | 5 | Javelin | Hardware | RayTech Components | 5400 | CC217 | 132 | 45040.53 | 5945349.96 | 2024-09-24 | 2024-11-02
PO100899 | 3 | HIMARS | Hardware | Precision Metals Inc | 5300 | CC807 | 52 | 3885.98 | 202070.96 | 2024-01-22 | 2024-02-24
PO100900 | 2 | HIMARS | Electronics | AeroDynamics Ltd | 5100 | CC291 | 103 | 26030.74 | 2681166.22 | 2024-05-07 | 2024-06-19
PO100901 | 4 | Javelin | Propulsion | RayTech Components | 5100 | CC453 | 237 | 15731.94 | 3728469.78 | 2024-10-18 | 2024-11-16
PO100902 | 1 | THAAD | Propulsion | DefenseCo Supplies | 5300 | CC192 | 114 | 29211.7 | 3330133.8 | 2024-05-22 | 2024-06-26
PO100903 | 1 | HIMARS | Propulsion | Orbital Systems | 5100 | CC812 | 23 | 46792.27 | 1076222.21 | 2024-09-26 | 2024-10-27
PO100904 | 5 | THAAD | Warhead | DefenseCo Supplies | 5300 | CC840 | 240 | 2921.43 | 701143.2 | 2024-11-05 | 2024-11-14
PO100905 | 5 | HIMARS | Guidance | RayTech Components | 5300 | CC198 | 47 | 23115.83 | 1086444.01 | 2024-03-07 | 2024-04-19
PO100906 | 3 | PAC-3 | Propulsion | RayTech Components | 5400 | CC702 | 33 | 34746.69 | 1146640.77 | 2024-10-24 | 2024-11-09
PO100907 | 1 | HIMARS | Composites | AeroDynamics Ltd | 5100 | CC980 | 64 | 44151.45 | 2825692.8 | 2024-04-23 | 2024-05-17
PO100908 | 1 | HIMARS | Guidance | DefenseCo Supplies | 5100 | CC716 | 100 | 2627.12 | 262712 | 2024-10-26 | 2024-11-11
PO100909 | 2 | PAC-3 | Electronics | AeroDynamics Ltd | 5400 | CC495 | 96 | 45791.96 | 4396028.16 | 2024-08-11 | 2024-08-21
PO100910 | 2 | HIMARS | Guidance | Orbital Systems | 5300 | CC325 | 230 | 29440.72 | 6771365.6 | 2024-09-05 | 2024-09-14
PO100911 | 5 | HIMARS | Electronics | AeroDynamics Ltd | 5400 | CC185 | 159 | 47078.63 | 7485502.17 | 2024-07-02 | 2024-07-18
PO100912 | 3 | HIMARS | Hardware | Precision Metals Inc | 5400 | CC232 | 23 | 5958.41 | 137043.43 | 2024-07-05 | 2024-08-07
PO100913 | 3 | HIMARS | Guidance | DefenseCo Supplies | 5200 | CC261 | 75 | 31213.2 | 2340990 | 2024-06-09 | 2024-07-14
PO100914 | 1 | Javelin | Composites | AeroDynamics Ltd | 5200 | CC989 | 113 | 1884.62 | 212962.06 | 2024-01-23 | 2024-02-03
PO100915 | 1 | THAAD | Guidance | Precision Metals Inc | 5200 | CC311 | 162 | 49099.38 | 7954099.56 | 2024-05-07 | 2024-06-10
PO100916 | 2 | PAC-3 | Propulsion | Precision Metals Inc | 5400 | CC611 | 146 | 42635.47 | 6224778.62 | 2024-08-06 | 2024-09-15
PO100917 | 4 | PAC-3 | Hardware | Precision Metals Inc | 5100 | CC801 | 175 | 46251.77 | 8094059.75 | 2024-12-22 | 2025-01-12
PO100918 | 2 | THAAD | Guidance | Precision Metals Inc | 5200 | CC280 | 243 | 20439.15 | 4966713.45 | 2024-10-29 | 2024-11-08
PO100919 | 1 | HIMARS | Guidance | RayTech Components | 5100 | CC495 | 237 | 15121.58 | 3583814.46 | 2024-11-06 | 2024-11-11
PO100920 | 5 | HIMARS | Warhead | DefenseCo Supplies | 5400 | CC635 | 55 | 1535.49 | 84451.95 | 2024-05-06 | 2024-05-27
PO100921 | 1 | Javelin | Electronics | AeroDynamics Ltd | 5400 | CC110 | 73 | 4467.12 | 326099.76 | 2024-08-15 | 2024-09-16
PO100922 | 3 | THAAD | Guidance | AeroDynamics Ltd | 5100 | CC443 | 80 | 43736.93 | 3498954.4 | 2024-10-16 | 2024-10-27
PO100923 | 4 | PAC-3 | Warhead | DefenseCo Supplies | 5300 | CC997 | 103 | 49042.87 | 5051415.61 | 2024-03-15 | 2024-04-22
PO100924 | 4 | PAC-3 | Warhead | AeroDynamics Ltd | 5100 | CC115 | 167 | 3566.33 | 595577.11 | 2024-03-21 | 2024-04-15
PO100925 | 1 | HIMARS | Guidance | DefenseCo Supplies | 5100 | CC396 | 203 | 46328.1 | 9404604.3 | 2024-03-01 | 2024-03-31
PO100926 | 1 | PAC-3 | Guidance | Precision Metals Inc | 5100 | CC974 | 103 | 35799.48 | 3687346.44 | 2024-11-19 | 2024-11-29
PO100927 | 3 | THAAD | Warhead | DefenseCo Supplies | 5400 | CC897 | 199 | 48968.35 | 9744701.65 | 2024-08-12 | 2024-08-17
PO100928 | 1 | Javelin | Propulsion | AeroDynamics Ltd | 5400 | CC238 | 225 | 16035.13 | 3607904.25 | 2024-12-22 | 2025-01-15
PO100929 | 5 | HIMARS | Guidance | AeroDynamics Ltd | 5100 | CC817 | 31 | 18472.75 | 572655.25 | 2024-04-02 | 2024-05-12
PO100930 | 4 | Javelin | Warhead | RayTech Components | 5200 | CC608 | 153 | 20317.37 | 3108557.61 | 2024-12-07 | 2024-12-16
PO100931 | 4 | HIMARS | Hardware | Orbital Systems | 5100 | CC816 | 118 | 19476.51 | 2298228.18 | 2024-03-29 | 2024-04-28
PO100932 | 5 | THAAD | Hardware | Orbital Systems | 5100 | CC248 | 46 | 35413.48 | 1629020.08 | 2024-09-28 | 2024-10-22
PO100933 | 2 | HIMARS | Guidance | RayTech Components | 5300 | CC452 | 66 | 37043.27 | 2444855.82 | 2024-05-03 | 2024-05-17
PO100934 | 1 | Javelin | Hardware | RayTech Components | 5300 | CC240 | 33 | 14527.59 | 479410.47 | 2024-03-17 | 2024-04-17
PO100935 | 4 | HIMARS | Hardware | Precision Metals Inc | 5300 | CC726 | 63 | 24273.21 | 1529212.23 | 2024-02-17 | 2024-03-06
PO100936 | 4 | HIMARS | Composites | DefenseCo Supplies | 5300 | CC500 | 40 | 26790.64 | 1071625.6 | 2024-02-26 | 2024-03-24
PO100937 | 4 | HIMARS | Guidance | RayTech Components | 5100 | CC837 | 202 | 13105.03 | 2647216.06 | 2024-12-21 | 2025-01-18
PO100938 | 1 | PAC-3 | Guidance | AeroDynamics Ltd | 5100 | CC848 | 37 | 2057.95 | 76144.15 | 2024-01-22 | 2024-02-19
PO100939 | 2 | THAAD | Propulsion | Precision Metals Inc | 5400 | CC275 | 102 | 20466.73 | 2087606.46 | 2024-09-02 | 2024-10-11
PO100940 | 3 | THAAD | Composites | Orbital Systems | 5200 | CC815 | 166 | 34720.7 | 5763636.2 | 2024-06-18 | 2024-07-31
PO100941 | 5 | HIMARS | Composites | RayTech Components | 5100 | CC245 | 169 | 32058.9 | 5417954.1 | 2024-05-31 | 2024-06-13
PO100942 | 3 | THAAD | Propulsion | Orbital Systems | 5200 | CC329 | 15 | 39758.19 | 596372.85 | 2024-07-16 | 2024-07-23
PO100943 | 2 | PAC-3 | Warhead | Orbital Systems | 5400 | CC237 | 166 | 34364.21 | 5704458.86 | 2024-02-19 | 2024-03-01
PO100944 | 2 | Javelin | Composites | RayTech Components | 5400 | CC613 | 104 | 29381.67 | 3055693.68 | 2024-02-12 | 2024-03-13
PO100945 | 5 | THAAD | Guidance | RayTech Components | 5200 | CC475 | 1 | 40465.8 | 40465.8 | 2024-07-31 | 2024-08-24
PO100946 | 1 | PAC-3 | Warhead | Orbital Systems | 5300 | CC495 | 22 | 19878.92 | 437336.24 | 2024-05-08 | 2024-06-11
PO100947 | 5 | HIMARS | Hardware | Orbital Systems | 5100 | CC814 | 24 | 41574.13 | 997779.12 | 2024-11-06 | 2024-11-23
PO100948 | 3 | HIMARS | Hardware | AeroDynamics Ltd | 5200 | CC435 | 166 | 32857.94 | 5454418.04 | 2024-03-15 | 2024-04-23
PO100949 | 4 | THAAD | Warhead | RayTech Components | 5200 | CC665 | 39 | 15045.32 | 586767.48 | 2024-10-11 | 2024-10-18
PO100950 | 2 | Javelin | Guidance | AeroDynamics Ltd | 5200 | CC815 | 175 | 14356.51 | 2512389.25 | 2024-10-14 | 2024-11-19
PO100951 | 4 | PAC-3 | Electronics | DefenseCo Supplies | 5200 | CC205 | 130 | 15400.03 | 2002003.9 | 2024-08-18 | 2024-08-29
PO100952 | 4 | PAC-3 | Electronics | AeroDynamics Ltd | 5200 | CC660 | 129 | 46513.61 | 6000255.69 | 2024-02-22 | 2024-03-16
PO100953 | 1 | HIMARS | Warhead | Orbital Systems | 5100 | CC204 | 150 | 11109.09 | 1666363.5 | 2024-12-27 | 2025-02-08
PO100954 | 5 | Javelin | Guidance | DefenseCo Supplies | 5400 | CC996 | 115 | 4007.47 | 460859.05 | 2024-07-29 | 2024-09-08
PO100955 | 3 | THAAD | Propulsion | DefenseCo Supplies | 5100 | CC772 | 66 | 40411.27 | 2667143.82 | 2024-01-20 | 2024-02-11
PO100956 | 2 | THAAD | Propulsion | Orbital Systems | 5100 | CC743 | 77 | 47202.76 | 3634612.52 | 2024-09-09 | 2024-10-07
PO100957 | 1 | HIMARS | Electronics | AeroDynamics Ltd | 5300 | CC300 | 28 | 32054.95 | 897538.6 | 2024-05-04 | 2024-05-18
PO100958 | 1 | Javelin | Warhead | RayTech Components | 5400 | CC722 | 15 | 49987.64 | 749814.6 | 2024-11-20 | 2024-12-16
PO100959 | 4 | PAC-3 | Composites | RayTech Components | 5300 | CC716 | 134 | 28722.68 | 3848839.12 | 2024-07-09 | 2024-07-22
PO100960 | 2 | THAAD | Electronics | RayTech Components | 5300 | CC799 | 70 | 3458.91 | 242123.7 | 2024-06-17 | 2024-07-20
PO100961 | 4 | Javelin | Composites | Orbital Systems | 5100 | CC946 | 8 | 16580.69 | 132645.52 | 2024-02-17 | 2024-03-13
PO100962 | 2 | HIMARS | Hardware | Orbital Systems | 5400 | CC918 | 104 | 8056.63 | 837889.52 | 2024-04-10 | 2024-05-13
PO100963 | 2 | Javelin | Propulsion | AeroDynamics Ltd | 5100 | CC906 | 21 | 25280.89 | 530898.69 | 2024-07-06 | 2024-07-30
PO100964 | 4 | PAC-3 | Electronics | AeroDynamics Ltd | 5400 | CC209 | 176 | 28323.1 | 4984865.6 | 2024-08-18 | 2024-09-01
PO100965 | 5 | THAAD | Warhead | RayTech Components | 5100 | CC691 | 15 | 14457.59 | 216863.85 | 2024-08-10 | 2024-09-06
PO100966 | 1 | PAC-3 | Electronics | RayTech Components | 5200 | CC750 | 28 | 11164.62 | 312609.36 | 2024-04-08 | 2024-05-13
PO100967 | 1 | PAC-3 | Electronics | AeroDynamics Ltd | 5400 | CC816 | 59 | 9187.93 | 542087.87 | 2024-07-16 | 2024-08-19
PO100968 | 3 | PAC-3 | Composites | RayTech Components | 5200 | CC392 | 129 | 11969.41 | 1544053.89 | 2024-02-23 | 2024-03-23
PO100969 | 2 | THAAD | Hardware | Orbital Systems | 5200 | CC901 | 43 | 38568.88 | 1658461.84 | 2024-10-04 | 2024-10-14
PO100970 | 2 | Javelin | Hardware | AeroDynamics Ltd | 5400 | CC205 | 144 | 33885.63 | 4879530.72 | 2024-09-01 | 2024-09-13
PO100971 | 3 | THAAD | Warhead | Orbital Systems | 5400 | CC429 | 46 | 18325.3 | 842963.8 | 2024-05-26 | 2024-07-07
PO100972 | 2 | PAC-3 | Warhead | Precision Metals Inc | 5400 | CC888 | 82 | 8555.77 | 701573.14 | 2024-11-25 | 2025-01-02
PO100973 | 4 | Javelin | Electronics | Precision Metals Inc | 5300 | CC653 | 247 | 22580.36 | 5577348.92 | 2024-11-21 | 2024-12-09
PO100974 | 1 | Javelin | Electronics | Precision Metals Inc | 5100 | CC278 | 241 | 5585.53 | 1346112.73 | 2024-11-26 | 2024-12-16
PO100975 | 5 | HIMARS | Guidance | AeroDynamics Ltd | 5400 | CC889 | 89 | 47898.89 | 4263001.21 | 2024-01-26 | 2024-03-06
PO100976 | 5 | THAAD | Propulsion | AeroDynamics Ltd | 5400 | CC684 | 156 | 13382.78 | 2087713.68 | 2024-06-17 | 2024-07-04
PO100977 | 2 | HIMARS | Hardware | AeroDynamics Ltd | 5400 | CC926 | 41 | 24044.61 | 985829.01 | 2024-08-17 | 2024-09-22
PO100978 | 4 | HIMARS | Warhead | RayTech Components | 5100 | CC429 | 183 | 26899.09 | 4922533.47 | 2024-05-17 | 2024-06-01
PO100979 | 2 | THAAD | Electronics | Precision Metals Inc | 5200 | CC430 | 169 | 45062.82 | 7615616.58 | 2024-09-30 | 2024-10-24
PO100980 | 4 | THAAD | Hardware | AeroDynamics Ltd | 5400 | CC781 | 186 | 16172.96 | 3008170.56 | 2024-10-07 | 2024-10-30
PO100981 | 5 | HIMARS | Guidance | Precision Metals Inc | 5400 | CC953 | 209 | 13885.64 | 2902098.76 | 2024-05-21 | 2024-06-03
PO100982 | 4 | HIMARS | Warhead | Precision Metals Inc | 5400 | CC390 | 53 | 14770.39 | 782830.67 | 2024-07-21 | 2024-08-02
PO100983 | 3 | PAC-3 | Composites | Orbital Systems | 5400 | CC851 | 91 | 10711.24 | 974722.84 | 2024-12-05 | 2024-12-13
PO100984 | 2 | THAAD | Warhead | RayTech Components | 5400 | CC175 | 73 | 34979.01 | 2553467.73 | 2024-09-12 | 2024-10-12
PO100985 | 5 | THAAD | Composites | AeroDynamics Ltd | 5300 | CC187 | 211 | 22423.17 | 4731288.87 | 2024-03-17 | 2024-04-18
PO100986 | 1 | Javelin | Propulsion | DefenseCo Supplies | 5200 | CC812 | 225 | 26999.76 | 6074946 | 2024-03-24 | 2024-04-12
PO100987 | 3 | THAAD | Hardware | DefenseCo Supplies | 5200 | CC862 | 47 | 1251.06 | 58799.82 | 2024-07-27 | 2024-09-01
PO100988 | 3 | HIMARS | Composites | Precision Metals Inc | 5100 | CC367 | 84 | 18151.29 | 1524708.36 | 2024-02-28 | 2024-04-05
PO100989 | 4 | HIMARS | Propulsion | Orbital Systems | 5200 | CC890 | 206 | 45165.76 | 9304146.56 | 2024-10-27 | 2024-11-15
PO100990 | 1 | Javelin | Hardware | RayTech Components | 5200 | CC686 | 157 | 37496.44 | 5886941.08 | 2024-02-21 | 2024-03-20
PO100991 | 5 | PAC-3 | Propulsion | Orbital Systems | 5100 | CC939 | 25 | 41789.1 | 1044727.5 | 2024-12-19 | 2025-01-15
PO100992 | 1 | PAC-3 | Warhead | RayTech Components | 5400 | CC371 | 246 | 1795.64 | 441727.44 | 2024-04-25 | 2024-05-14
PO100993 | 1 | Javelin | Guidance | Orbital Systems | 5200 | CC594 | 105 | 22917.37 | 2406323.85 | 2024-01-10 | 2024-02-22
PO100994 | 3 | PAC-3 | Electronics | Precision Metals Inc | 5300 | CC724 | 133 | 38396.73 | 5106765.09 | 2024-02-26 | 2024-03-30
PO100995 | 2 | PAC-3 | Warhead | Orbital Systems | 5200 | CC631 | 165 | 12711.53 | 2097402.45 | 2024-05-01 | 2024-06-13
PO100996 | 4 | Javelin | Guidance | DefenseCo Supplies | 5400 | CC108 | 13 | 4157.18 | 54043.34 | 2024-11-02 | 2024-11-23
PO100997 | 1 | THAAD | Propulsion | Precision Metals Inc | 5100 | CC752 | 168 | 20240.22 | 3400356.96 | 2024-07-25 | 2024-08-02
PO100998 | 4 | HIMARS | Composites | Precision Metals Inc | 5400 | CC716 | 10 | 13155.14 | 131551.4 | 2024-12-30 | 2025-01-14
PO100999 | 1 | Javelin | Propulsion | Orbital Systems | 5400 | CC328 | 63 | 33265.33 | 2095715.79 | 2024-09-24 | 2024-10-19
PO101000 | 1 | PAC-3 | Electronics | AeroDynamics Ltd | 5200 | CC610 | 89 | 34488.89 | 3069511.21 | 2024-12-17 | 2025-01-04
PO101001 | 1 | THAAD | Electronics | Precision Metals Inc | 5400 | CC936 | 133 | 15308.29 | 2036002.57 | 2024-05-26 | 2024-06-22
PO101002 | 2 | Javelin | Hardware | AeroDynamics Ltd | 5400 | CC388 | 130 | 12536.53 | 1629748.9 | 2024-09-13 | 2024-10-13
PO101003 | 3 | THAAD | Propulsion | Orbital Systems | 5400 | CC369 | 221 | 6767.98 | 1495723.58 | 2024-07-01 | 2024-07-20
PO101004 | 4 | HIMARS | Propulsion | AeroDynamics Ltd | 5300 | CC173 | 99 | 26206.73 | 2594466.27 | 2024-11-23 | 2024-12-25
PO101005 | 1 | Javelin | Warhead | AeroDynamics Ltd | 5100 | CC420 | 68 | 28805.26 | 1958757.68 | 2024-08-11 | 2024-09-17
PO101006 | 3 | Javelin | Electronics | Orbital Systems | 5300 | CC880 | 194 | 32493.08 | 6303657.52 | 2024-05-31 | 2024-06-28
PO101007 | 1 | PAC-3 | Hardware | AeroDynamics Ltd | 5100 | CC510 | 188 | 24228.81 | 4555016.28 | 2024-05-07 | 2024-06-08
PO101008 | 1 | THAAD | Composites | AeroDynamics Ltd | 5300 | CC328 | 221 | 2422.13 | 535290.73 | 2024-10-20 | 2024-12-02
PO101009 | 2 | Javelin | Composites | DefenseCo Supplies | 5200 | CC474 | 74 | 9762.72 | 722441.28 | 2024-11-30 | 2025-01-04
PO101010 | 2 | THAAD | Propulsion | AeroDynamics Ltd | 5400 | CC352 | 39 | 36268.46 | 1414469.94 | 2024-02-06 | 2024-02-13
PO101011 | 5 | PAC-3 | Warhead | Orbital Systems | 5100 | CC155 | 76 | 40267.63 | 3060339.88 | 2024-08-18 | 2024-09-19
PO101012 | 2 | THAAD | Composites | Precision Metals Inc | 5200 | CC317 | 222 | 38341.2 | 8511746.4 | 2024-10-04 | 2024-10-26
PO101013 | 5 | Javelin | Hardware | AeroDynamics Ltd | 5300 | CC412 | 109 | 31406.4 | 3423297.6 | 2024-11-22 | 2024-12-05
PO101014 | 1 | Javelin | Guidance | Precision Metals Inc | 5100 | CC888 | 64 | 28688.48 | 1836062.72 | 2024-10-16 | 2024-11-21
PO101015 | 5 | PAC-3 | Hardware | DefenseCo Supplies | 5100 | CC452 | 32 | 38556.19 | 1233798.08 | 2024-08-12 | 2024-09-13
PO101016 | 4 | Javelin | Propulsion | Precision Metals Inc | 5300 | CC481 | 15 | 36613.67 | 549205.05 | 2024-03-13 | 2024-04-23
PO101017 | 3 | Javelin | Hardware | AeroDynamics Ltd | 5200 | CC703 | 125 | 35040.82 | 4380102.5 | 2024-03-13 | 2024-04-18
PO101018 | 5 | THAAD | Guidance | Orbital Systems | 5200 | CC955 | 13 | 40938.07 | 532194.91 | 2024-02-20 | 2024-03-14
PO101019 | 2 | PAC-3 | Propulsion | Precision Metals Inc | 5400 | CC637 | 173 | 49586.39 | 8578445.47 | 2024-03-22 | 2024-05-01
PO101020 | 3 | THAAD | Electronics | Orbital Systems | 5400 | CC672 | 123 | 38618.43 | 4750066.89 | 2024-11-25 | 2024-12-24
PO101021 | 1 | PAC-3 | Propulsion | RayTech Components | 5100 | CC532 | 198 | 30352.29 | 6009753.42 | 2024-04-08 | 2024-05-09
PO101022 | 3 | Javelin | Hardware | RayTech Components | 5100 | CC339 | 103 | 44359.12 | 4568989.36 | 2024-07-14 | 2024-08-24
PO101023 | 1 | PAC-3 | Hardware | AeroDynamics Ltd | 5300 | CC667 | 175 | 6991.96 | 1223593 | 2024-05-17 | 2024-06-28
PO101024 | 2 | THAAD | Guidance | DefenseCo Supplies | 5300 | CC834 | 199 | 38075.5 | 7577024.5 | 2024-06-28 | 2024-08-10
PO101025 | 3 | THAAD | Warhead | RayTech Components | 5400 | CC894 | 203 | 5593.86 | 1135553.58 | 2024-09-29 | 2024-10-10
PO101026 | 5 | PAC-3 | Electronics | DefenseCo Supplies | 5300 | CC479 | 109 | 48406.5 | 5276308.5 | 2024-12-13 | 2025-01-10
PO101027 | 5 | THAAD | Propulsion | Orbital Systems | 5100 | CC145 | 248 | 21312.06 | 5285390.88 | 2024-07-26 | 2024-09-01
PO101028 | 2 | PAC-3 | Composites | AeroDynamics Ltd | 5100 | CC286 | 31 | 18550.57 | 575067.67 | 2024-09-05 | 2024-09-12
PO101029 | 2 | THAAD | Propulsion | Orbital Systems | 5200 | CC891 | 155 | 41316.55 | 6404065.25 | 2024-08-09 | 2024-09-09
PO101030 | 4 | THAAD | Composites | DefenseCo Supplies | 5100 | CC868 | 235 | 13447.93 | 3160263.55 | 2024-03-14 | 2024-04-04
PO101031 | 5 | HIMARS | Propulsion | DefenseCo Supplies | 5100 | CC364 | 139 | 16457.53 | 2287596.67 | 2024-04-27 | 2024-05-07
PO101032 | 2 | Javelin | Hardware | DefenseCo Supplies | 5300 | CC958 | 114 | 22535.7 | 2569069.8 | 2024-05-07 | 2024-05-16
PO101033 | 1 | HIMARS | Propulsion | AeroDynamics Ltd | 5400 | CC813 | 242 | 33078.53 | 8005004.26 | 2024-02-29 | 2024-03-17
PO101034 | 1 | THAAD | Electronics | RayTech Components | 5200 | CC560 | 59 | 44079.95 | 2600717.05 | 2024-12-22 | 2025-01-25
PO101035 | 1 | THAAD | Electronics | RayTech Components | 5400 | CC168 | 216 | 4130.19 | 892121.04 | 2024-03-29 | 2024-04-03
PO101036 | 1 | THAAD | Propulsion | AeroDynamics Ltd | 5300 | CC148 | 147 | 24501.52 | 3601723.44 | 2024-01-02 | 2024-01-15
PO101037 | 1 | HIMARS | Hardware | Orbital Systems | 5100 | CC884 | 49 | 2269.14 | 111187.86 | 2024-05-10 | 2024-05-18
PO101038 | 5 | Javelin | Warhead | AeroDynamics Ltd | 5300 | CC516 | 80 | 13384.64 | 1070771.2 | 2024-05-27 | 2024-07-08
PO101039 | 1 | HIMARS | Hardware | AeroDynamics Ltd | 5100 | CC187 | 88 | 43415.17 | 3820534.96 | 2024-07-22 | 2024-08-12
PO101040 | 4 | HIMARS | Warhead | Precision Metals Inc | 5300 | CC313 | 74 | 33164.16 | 2454147.84 | 2024-01-31 | 2024-03-02
PO101041 | 4 | Javelin | Electronics | Precision Metals Inc | 5100 | CC838 | 181 | 4265.25 | 772010.25 | 2024-12-06 | 2024-12-20
PO101042 | 5 | PAC-3 | Composites | RayTech Components | 5300 | CC814 | 112 | 25576.82 | 2864603.84 | 2024-11-05 | 2024-11-26
PO101043 | 5 | PAC-3 | Hardware | Precision Metals Inc | 5100 | CC585 | 150 | 33857.74 | 5078661 | 2024-04-24 | 2024-05-25
PO101044 | 2 | Javelin | Electronics | Precision Metals Inc | 5400 | CC435 | 80 | 49249.51 | 3939960.8 | 2024-08-15 | 2024-09-07
PO101045 | 4 | THAAD | Warhead | AeroDynamics Ltd | 5200 | CC474 | 58 | 11901.4 | 690281.2 | 2024-06-04 | 2024-06-09
PO101046 | 3 | HIMARS | Guidance | DefenseCo Supplies | 5200 | CC779 | 166 | 7918.84 | 1314527.44 | 2024-05-16 | 2024-06-02
PO101047 | 1 | THAAD | Guidance | AeroDynamics Ltd | 5200 | CC463 | 72 | 5199.94 | 374395.68 | 2024-06-18 | 2024-07-05
PO101048 | 2 | THAAD | Guidance | Orbital Systems | 5100 | CC374 | 7 | 4688.8 | 32821.6 | 2024-02-23 | 2024-04-07
PO101049 | 1 | THAAD | Propulsion | AeroDynamics Ltd | 5200 | CC302 | 31 | 4963.26 | 153861.06 | 2024-03-20 | 2024-04-04
PO101050 | 3 | Javelin | Warhead | Orbital Systems | 5100 | CC718 | 208 | 8334.3 | 1733534.4 | 2024-05-02 | 2024-06-01
PO101051 | 3 | THAAD | Electronics | AeroDynamics Ltd | 5100 | CC706 | 12 | 28727.28 | 344727.36 | 2024-09-10 | 2024-09-19
PO101052 | 2 | HIMARS | Guidance | Orbital Systems | 5300 | CC925 | 216 | 8991.83 | 1942235.28 | 2024-05-24 | 2024-07-06
PO101053 | 5 | HIMARS | Warhead | Orbital Systems | 5100 | CC632 | 211 | 24391.47 | 5146600.17 | 2024-12-03 | 2024-12-10
PO101054 | 1 | THAAD | Composites | AeroDynamics Ltd | 5400 | CC331 | 207 | 34581.25 | 7158318.75 | 2024-01-28 | 2024-02-05
PO101055 | 3 | HIMARS | Guidance | AeroDynamics Ltd | 5300 | CC283 | 23 | 14489.66 | 333262.18 | 2024-10-17 | 2024-11-21
PO101056 | 2 | HIMARS | Electronics | Precision Metals Inc | 5300 | CC904 | 211 | 11569.81 | 2441229.91 | 2024-04-09 | 2024-05-12
PO101057 | 4 | Javelin | Composites | RayTech Components | 5200 | CC830 | 161 | 17148.12 | 2760847.32 | 2024-12-06 | 2025-01-02
PO101058 | 3 | THAAD | Warhead | Precision Metals Inc | 5300 | CC312 | 26 | 21998.12 | 571951.12 | 2024-08-14 | 2024-09-25
PO101059 | 1 | THAAD | Warhead | Orbital Systems | 5300 | CC548 | 244 | 11454.05 | 2794788.2 | 2024-05-26 | 2024-06-21
PO101060 | 1 | THAAD | Guidance | Orbital Systems | 5400 | CC964 | 77 | 43456.69 | 3346165.13 | 2024-02-24 | 2024-04-06
PO101061 | 5 | THAAD | Warhead | DefenseCo Supplies | 5200 | CC770 | 80 | 1247.29 | 99783.2 | 2024-04-21 | 2024-05-28
PO101062 | 1 | HIMARS | Propulsion | AeroDynamics Ltd | 5100 | CC578 | 77 | 22475.29 | 1730597.33 | 2024-02-21 | 2024-03-30
PO101063 | 5 | HIMARS | Guidance | DefenseCo Supplies | 5400 | CC836 | 226 | 21189.6 | 4788849.6 | 2024-03-09 | 2024-03-16
PO101064 | 1 | HIMARS | Hardware | DefenseCo Supplies | 5100 | CC762 | 30 | 13767.45 | 413023.5 | 2024-04-05 | 2024-04-16
PO101065 | 2 | THAAD | Electronics | Orbital Systems | 5100 | CC555 | 207 | 27258.19 | 5642445.33 | 2024-04-30 | 2024-05-09
PO101066 | 4 | Javelin | Propulsion | RayTech Components | 5400 | CC138 | 54 | 44215.74 | 2387649.96 | 2024-06-09 | 2024-07-16
PO101067 | 4 | HIMARS | Warhead | DefenseCo Supplies | 5300 | CC347 | 127 | 38539.7 | 4894541.9 | 2024-03-22 | 2024-04-26
PO101068 | 2 | Javelin | Composites | RayTech Components | 5200 | CC940 | 131 | 16399.29 | 2148306.99 | 2024-08-05 | 2024-08-18
PO101069 | 5 | PAC-3 | Propulsion | DefenseCo Supplies | 5300 | CC325 | 225 | 13883.57 | 3123803.25 | 2024-05-20 | 2024-05-26
PO101070 | 2 | PAC-3 | Electronics | Precision Metals Inc | 5100 | CC515 | 192 | 35139.34 | 6746753.28 | 2024-06-15 | 2024-07-09
PO101071 | 1 | THAAD | Electronics | RayTech Components | 5100 | CC357 | 19 | 29648.08 | 563313.52 | 2024-08-20 | 2024-09-22
PO101072 | 4 | HIMARS | Electronics | Orbital Systems | 5200 | CC183 | 131 | 5486.94 | 718789.14 | 2024-12-03 | 2025-01-02
PO101073 | 2 | HIMARS | Electronics | DefenseCo Supplies | 5100 | CC732 | 225 | 27243.13 | 6129704.25 | 2024-01-04 | 2024-01-30
PO101074 | 1 | HIMARS | Hardware | Precision Metals Inc | 5100 | CC682 | 33 | 14810.4 | 488743.2 | 2024-09-24 | 2024-10-09
PO101075 | 4 | Javelin | Composites | AeroDynamics Ltd | 5300 | CC727 | 212 | 31210.25 | 6616573 | 2024-02-02 | 2024-02-16
PO101076 | 1 | PAC-3 | Composites | DefenseCo Supplies | 5300 | CC947 | 59 | 35348.46 | 2085559.14 | 2024-10-01 | 2024-10-26
PO101077 | 1 | THAAD | Electronics | Precision Metals Inc | 5100 | CC912 | 8 | 11298.59 | 90388.72 | 2024-05-04 | 2024-06-10
PO101078 | 1 | HIMARS | Hardware | RayTech Components | 5300 | CC616 | 187 | 42546.05 | 7956111.35 | 2024-06-25 | 2024-07-17
PO101079 | 3 | PAC-3 | Hardware | DefenseCo Supplies | 5400 | CC486 | 25 | 36808.81 | 920220.25 | 2024-07-01 | 2024-08-14
PO101080 | 1 | Javelin | Propulsion | DefenseCo Supplies | 5300 | CC644 | 111 | 16179.01 | 1795870.11 | 2024-08-18 | 2024-09-07
PO101081 | 3 | PAC-3 | Hardware | Precision Metals Inc | 5100 | CC930 | 112 | 45120.33 | 5053476.96 | 2024-02-07 | 2024-03-04
PO101082 | 5 | HIMARS | Composites | DefenseCo Supplies | 5400 | CC687 | 145 | 46332.43 | 6718202.35 | 2024-12-12 | 2025-01-10
PO101083 | 1 | HIMARS | Warhead | Orbital Systems | 5100 | CC870 | 227 | 17527.56 | 3978756.12 | 2024-08-01 | 2024-08-14
PO101084 | 3 | Javelin | Propulsion | DefenseCo Supplies | 5300 | CC958 | 100 | 2287.34 | 228734 | 2024-02-25 | 2024-04-03
PO101085 | 1 | THAAD | Hardware | Precision Metals Inc | 5300 | CC705 | 242 | 31259.89 | 7564893.38 | 2024-02-23 | 2024-03-08
PO101086 | 4 | THAAD | Electronics | AeroDynamics Ltd | 5300 | CC739 | 229 | 8444.71 | 1933838.59 | 2024-09-12 | 2024-10-03
PO101087 | 3 | THAAD | Electronics | Orbital Systems | 5200 | CC579 | 120 | 1247.62 | 149714.4 | 2024-05-02 | 2024-05-28
PO101088 | 5 | THAAD | Guidance | RayTech Components | 5100 | CC879 | 4 | 5731.06 | 22924.24 | 2024-04-04 | 2024-04-15
PO101089 | 5 | THAAD | Electronics | RayTech Components | 5200 | CC188 | 147 | 32229.4 | 4737721.8 | 2024-11-17 | 2024-12-01
PO101090 | 2 | PAC-3 | Warhead | DefenseCo Supplies | 5400 | CC146 | 110 | 48721.67 | 5359383.7 | 2024-07-28 | 2024-09-06
PO101091 | 4 | Javelin | Electronics | DefenseCo Supplies | 5100 | CC176 | 1 | 2908.37 | 2908.37 | 2024-05-10 | 2024-05-17
PO101092 | 1 | PAC-3 | Guidance | DefenseCo Supplies | 5200 | CC458 | 82 | 37424.43 | 3068803.26 | 2024-11-11 | 2024-12-23
PO101093 | 1 | THAAD | Propulsion | Orbital Systems | 5100 | CC246 | 3 | 29750.99 | 89252.97 | 2024-05-22 | 2024-06-28
PO101094 | 5 | PAC-3 | Guidance | DefenseCo Supplies | 5200 | CC819 | 164 | 13416.31 | 2200274.84 | 2024-03-17 | 2024-04-23
PO101095 | 3 | THAAD | Hardware | Precision Metals Inc | 5300 | CC881 | 104 | 2695.75 | 280358 | 2024-12-04 | 2024-12-12
PO101096 | 5 | PAC-3 | Electronics | DefenseCo Supplies | 5100 | CC817 | 247 | 12044.25 | 2974929.75 | 2024-11-05 | 2024-11-19
PO101097 | 1 | PAC-3 | Guidance | AeroDynamics Ltd | 5200 | CC464 | 189 | 49279.83 | 9313887.87 | 2024-11-01 | 2024-11-24
PO101098 | 3 | HIMARS | Hardware | DefenseCo Supplies | 5200 | CC651 | 38 | 5032.26 | 191225.88 | 2024-03-15 | 2024-04-05
PO101099 | 5 | PAC-3 | Composites | Orbital Systems | 5300 | CC555 | 137 | 40554.47 | 5555962.39 | 2024-12-01 | 2025-01-05
PO101100 | 2 | THAAD | Propulsion | Precision Metals Inc | 5300 | CC639 | 72 | 4165.25 | 299898 | 2024-04-21 | 2024-06-01

## Labor_Hours
Week_Ending | Employee_ID | Program | Department | Labor_Category | Planned_Hours | Actual_Hours | OT_Hours | Standard_Rate | OT_Rate | Labor_Cost | GL_Account
2024-01-07 | E1094 | HIMARS | Test | Analyst | 31 | 34 | 0 | 75.58 | 113.37 | 2569.72 | 6200
2024-01-07 | E1107 | THAAD | Manufacturing | Technician | 30 | 28 | 0 | 52.66 | 78.99 | 1474.48 | 6100
2024-01-07 | E1035 | THAAD | Test | Analyst | 35 | 30 | 0 | 85.2 | 127.8 | 2556 | 6200
2024-01-07 | E1085 | THAAD | Engineering | Technician | 35 | 31 | 0 | 55.72 | 83.58 | 1727.32 | 6100
2024-01-07 | E1047 | HIMARS | Engineering | Assembler | 40 | 43 | 3 | 118.61 | 177.91 | 5278.13 | 6200
2024-01-07 | E1031 | Javelin | Test | Assembler | 38 | 39 | 0 | 80.31 | 120.47 | 3132.09 | 6100
2024-01-07 | E1021 | THAAD | Engineering | Analyst | 34 | 38 | 0 | 58.38 | 87.57 | 2218.44 | 6200
2024-01-07 | E1082 | THAAD | Test | Technician | 32 | 36 | 0 | 76.44 | 114.66 | 2751.84 | 6200
2024-01-07 | E1099 | THAAD | Program Control | Analyst | 44 | 46 | 6 | 63.49 | 95.23 | 3110.98 | 6100
2024-01-07 | E1082 | Javelin | Manufacturing | Engineer | 42 | 41 | 1 | 86.51 | 129.77 | 3590.17 | 6100
2024-01-07 | E1059 | THAAD | Program Control | Technician | 32 | 37 | 0 | 98.17 | 147.25 | 3632.29 | 6100
2024-01-07 | E1027 | Javelin | Manufacturing | Assembler | 38 | 39 | 0 | 61.08 | 91.62 | 2382.12 | 6200
2024-01-07 | E1023 | THAAD | Engineering | Technician | 42 | 41 | 1 | 48.56 | 72.84 | 2015.24 | 6200
2024-01-07 | E1091 | Javelin | Manufacturing | Analyst | 40 | 37 | 0 | 59.14 | 88.71 | 2188.18 | 6100
2024-01-07 | E1112 | PAC-3 | Program Control | Technician | 30 | 33 | 0 | 58.39 | 87.59 | 1926.87 | 6100
2024-01-14 | E1058 | HIMARS | Manufacturing | Engineer | 36 | 41 | 1 | 85.34 | 128.01 | 3541.61 | 6200
2024-01-14 | E1017 | THAAD | Manufacturing | Assembler | 36 | 40 | 0 | 84.54 | 126.81 | 3381.6 | 6100
2024-01-14 | E1093 | HIMARS | Test | Assembler | 42 | 45 | 5 | 71.39 | 107.09 | 3391.05 | 6200
2024-01-14 | E1031 | HIMARS | Manufacturing | Assembler | 33 | 33 | 0 | 110.12 | 165.18 | 3633.96 | 6100
2024-01-14 | E1046 | THAAD | Test | Engineer | 35 | 30 | 0 | 77.69 | 116.53 | 2330.7 | 6100
2024-01-14 | E1061 | PAC-3 | Manufacturing | Engineer | 32 | 37 | 0 | 77.18 | 115.77 | 2855.66 | 6100
2024-01-14 | E1076 | HIMARS | Program Control | Assembler | 35 | 31 | 0 | 49.48 | 74.22 | 1533.88 | 6200
2024-01-14 | E1040 | Javelin | Manufacturing | Engineer | 36 | 38 | 0 | 80.98 | 121.47 | 3077.24 | 6100
2024-01-14 | E1065 | Javelin | Program Control | Assembler | 42 | 44 | 4 | 50.91 | 76.36 | 2341.84 | 6100
2024-01-14 | E1118 | Javelin | Test | Analyst | 39 | 41 | 1 | 90.18 | 135.27 | 3742.47 | 6200
2024-01-14 | E1091 | HIMARS | Program Control | Technician | 31 | 27 | 0 | 118.76 | 178.14 | 3206.52 | 6100
2024-01-14 | E1006 | Javelin | Program Control | Analyst | 40 | 41 | 1 | 115.21 | 172.81 | 4781.21 | 6100
2024-01-14 | E1016 | Javelin | Test | Technician | 42 | 38 | 0 | 74.86 | 112.29 | 2844.68 | 6200
2024-01-14 | E1003 | THAAD | Program Control | Technician | 35 | 39 | 0 | 76.58 | 114.87 | 2986.62 | 6100
2024-01-14 | E1087 | HIMARS | Test | Assembler | 42 | 42 | 2 | 98.55 | 147.82 | 4237.64 | 6100
2024-01-21 | E1106 | Javelin | Test | Engineer | 43 | 38 | 0 | 80.29 | 120.44 | 3051.02 | 6100
2024-01-21 | E1034 | HIMARS | Engineering | Technician | 32 | 33 | 0 | 96.48 | 144.72 | 3183.84 | 6100
2024-01-21 | E1075 | PAC-3 | Engineering | Analyst | 32 | 36 | 0 | 65.96 | 98.94 | 2374.56 | 6100
2024-01-21 | E1054 | PAC-3 | Engineering | Assembler | 41 | 36 | 0 | 119.37 | 179.06 | 4297.32 | 6200
2024-01-21 | E1079 | THAAD | Test | Assembler | 41 | 46 | 6 | 93.53 | 140.3 | 4583 | 6100
2024-01-21 | E1066 | PAC-3 | Engineering | Assembler | 30 | 25 | 0 | 59.58 | 89.37 | 1489.5 | 6100
2024-01-21 | E1025 | PAC-3 | Engineering | Assembler | 42 | 40 | 0 | 48.65 | 72.97 | 1946 | 6100
2024-01-21 | E1011 | PAC-3 | Program Control | Technician | 33 | 34 | 0 | 115.23 | 172.84 | 3917.82 | 6200
2024-01-21 | E1066 | THAAD | Manufacturing | Assembler | 34 | 36 | 0 | 53.51 | 80.27 | 1926.36 | 6200
2024-01-21 | E1099 | THAAD | Test | Engineer | 41 | 43 | 3 | 42.99 | 64.48 | 1913.04 | 6100
2024-01-21 | E1054 | PAC-3 | Test | Engineer | 42 | 42 | 2 | 111.11 | 166.66 | 4777.72 | 6200
2024-01-21 | E1022 | HIMARS | Manufacturing | Technician | 38 | 41 | 1 | 53.11 | 79.66 | 2204.06 | 6100
2024-01-21 | E1055 | HIMARS | Engineering | Technician | 41 | 45 | 5 | 114.55 | 171.82 | 5441.1 | 6100
2024-01-21 | E1001 | HIMARS | Test | Assembler | 39 | 41 | 1 | 102.78 | 154.17 | 4265.37 | 6200
2024-01-21 | E1079 | Javelin | Test | Analyst | 36 | 41 | 1 | 43.09 | 64.64 | 1788.24 | 6100
2024-01-28 | E1099 | THAAD | Program Control | Analyst | 36 | 34 | 0 | 111.83 | 167.75 | 3802.22 | 6200
2024-01-28 | E1004 | PAC-3 | Engineering | Technician | 43 | 47 | 7 | 114.87 | 172.31 | 5800.97 | 6100
2024-01-28 | E1090 | Javelin | Test | Engineer | 43 | 40 | 0 | 112.47 | 168.7 | 4498.8 | 6100
2024-01-28 | E1006 | THAAD | Engineering | Engineer | 38 | 37 | 0 | 41.47 | 62.2 | 1534.39 | 6100
2024-01-28 | E1078 | Javelin | Test | Engineer | 42 | 39 | 0 | 95.06 | 142.59 | 3707.34 | 6200
2024-01-28 | E1031 | HIMARS | Program Control | Technician | 42 | 39 | 0 | 63.81 | 95.72 | 2488.59 | 6200
2024-01-28 | E1028 | PAC-3 | Engineering | Technician | 35 | 34 | 0 | 61.92 | 92.88 | 2105.28 | 6200
2024-01-28 | E1049 | THAAD | Manufacturing | Technician | 32 | 29 | 0 | 76.43 | 114.65 | 2216.47 | 6100
2024-01-28 | E1113 | HIMARS | Engineering | Technician | 31 | 35 | 0 | 67.63 | 101.44 | 2367.05 | 6100
2024-01-28 | E1025 | HIMARS | Engineering | Assembler | 37 | 35 | 0 | 100.52 | 150.78 | 3518.2 | 6100
2024-01-28 | E1001 | HIMARS | Test | Assembler | 31 | 34 | 0 | 93.83 | 140.75 | 3190.22 | 6100
2024-01-28 | E1012 | HIMARS | Test | Analyst | 35 | 36 | 0 | 64.04 | 96.06 | 2305.44 | 6200
2024-01-28 | E1030 | Javelin | Manufacturing | Analyst | 34 | 38 | 0 | 79.83 | 119.75 | 3033.54 | 6100
2024-01-28 | E1031 | HIMARS | Manufacturing | Engineer | 38 | 36 | 0 | 99.61 | 149.41 | 3585.96 | 6200
2024-01-28 | E1100 | HIMARS | Engineering | Engineer | 37 | 38 | 0 | 104.49 | 156.73 | 3970.62 | 6200
2024-02-04 | E1107 | Javelin | Test | Technician | 38 | 41 | 1 | 103.55 | 155.32 | 4297.32 | 6200
2024-02-04 | E1002 | Javelin | Program Control | Assembler | 35 | 39 | 0 | 82.68 | 124.02 | 3224.52 | 6100
2024-02-04 | E1016 | THAAD | Program Control | Technician | 31 | 35 | 0 | 96.41 | 144.62 | 3374.35 | 6200
2024-02-04 | E1032 | Javelin | Engineering | Assembler | 44 | 41 | 1 | 77.73 | 116.59 | 3225.79 | 6200
2024-02-04 | E1117 | THAAD | Test | Engineer | 38 | 33 | 0 | 68.67 | 103 | 2266.11 | 6200
2024-02-04 | E1067 | THAAD | Engineering | Technician | 41 | 42 | 2 | 90.54 | 135.81 | 3893.22 | 6200
2024-02-04 | E1003 | Javelin | Test | Assembler | 34 | 33 | 0 | 52.25 | 78.38 | 1724.25 | 6200
2024-02-04 | E1058 | PAC-3 | Engineering | Analyst | 30 | 28 | 0 | 85.65 | 128.48 | 2398.2 | 6200
2024-02-04 | E1074 | Javelin | Engineering | Technician | 31 | 32 | 0 | 62.6 | 93.9 | 2003.2 | 6200
2024-02-04 | E1097 | HIMARS | Test | Technician | 44 | 48 | 8 | 78.88 | 118.32 | 4101.76 | 6100
2024-02-04 | E1016 | HIMARS | Engineering | Technician | 33 | 36 | 0 | 94.65 | 141.98 | 3407.4 | 6200
2024-02-04 | E1050 | THAAD | Test | Assembler | 35 | 39 | 0 | 58.38 | 87.57 | 2276.82 | 6200
2024-02-04 | E1021 | THAAD | Program Control | Analyst | 43 | 43 | 3 | 50.76 | 76.14 | 2258.82 | 6200
2024-02-04 | E1092 | PAC-3 | Program Control | Technician | 42 | 37 | 0 | 59.81 | 89.72 | 2212.97 | 6200
2024-02-04 | E1075 | Javelin | Engineering | Analyst | 40 | 38 | 0 | 112.85 | 169.27 | 4288.3 | 6200
2024-02-11 | E1114 | THAAD | Manufacturing | Analyst | 31 | 35 | 0 | 101.63 | 152.44 | 3557.05 | 6200
2024-02-11 | E1015 | Javelin | Test | Technician | 30 | 30 | 0 | 66.48 | 99.72 | 1994.4 | 6200
2024-02-11 | E1038 | THAAD | Program Control | Assembler | 35 | 38 | 0 | 103.51 | 155.27 | 3933.38 | 6100
2024-02-11 | E1116 | THAAD | Test | Assembler | 38 | 36 | 0 | 62.66 | 93.99 | 2255.76 | 6200
2024-02-11 | E1029 | THAAD | Test | Technician | 38 | 36 | 0 | 58.69 | 88.03 | 2112.84 | 6100
2024-02-11 | E1075 | Javelin | Manufacturing | Engineer | 43 | 42 | 2 | 103.25 | 154.88 | 4439.76 | 6200
2024-02-11 | E1004 | PAC-3 | Program Control | Engineer | 38 | 38 | 0 | 72.33 | 108.5 | 2748.54 | 6200
2024-02-11 | E1105 | THAAD | Manufacturing | Engineer | 32 | 36 | 0 | 69.92 | 104.88 | 2517.12 | 6100
2024-02-11 | E1004 | Javelin | Manufacturing | Assembler | 40 | 42 | 2 | 102.5 | 153.75 | 4407.5 | 6100
2024-02-11 | E1088 | PAC-3 | Test | Technician | 42 | 40 | 0 | 48.25 | 72.38 | 1930 | 6200
2024-02-11 | E1031 | HIMARS | Test | Analyst | 32 | 36 | 0 | 109.59 | 164.38 | 3945.24 | 6200
2024-02-11 | E1042 | Javelin | Program Control | Assembler | 34 | 31 | 0 | 50.13 | 75.2 | 1554.03 | 6100
2024-02-11 | E1112 | THAAD | Engineering | Assembler | 43 | 44 | 4 | 41.56 | 62.34 | 1911.76 | 6100
2024-02-11 | E1018 | Javelin | Test | Engineer | 40 | 35 | 0 | 105.28 | 157.92 | 3684.8 | 6200
2024-02-11 | E1025 | HIMARS | Test | Assembler | 36 | 39 | 0 | 63.05 | 94.57 | 2458.95 | 6200
2024-02-18 | E1096 | PAC-3 | Test | Engineer | 37 | 40 | 0 | 109.46 | 164.19 | 4378.4 | 6200
2024-02-18 | E1106 | PAC-3 | Engineering | Engineer | 39 | 41 | 1 | 119.28 | 178.92 | 4950.12 | 6200
2024-02-18 | E1070 | THAAD | Engineering | Engineer | 39 | 43 | 3 | 41.58 | 62.37 | 1850.31 | 6200
2024-02-18 | E1016 | Javelin | Engineering | Technician | 43 | 47 | 7 | 70.22 | 105.33 | 3546.11 | 6200
2024-02-18 | E1071 | HIMARS | Engineering | Engineer | 37 | 42 | 2 | 94.69 | 142.03 | 4071.66 | 6100
2024-02-18 | E1034 | THAAD | Manufacturing | Engineer | 42 | 46 | 6 | 93.13 | 139.69 | 4563.34 | 6200
2024-02-18 | E1080 | HIMARS | Engineering | Assembler | 38 | 34 | 0 | 110 | 165 | 3740 | 6200
2024-02-18 | E1083 | PAC-3 | Program Control | Analyst | 34 | 29 | 0 | 69.36 | 104.04 | 2011.44 | 6200
2024-02-18 | E1111 | PAC-3 | Manufacturing | Assembler | 41 | 40 | 0 | 98.67 | 148 | 3946.8 | 6200
2024-02-18 | E1053 | Javelin | Test | Engineer | 32 | 27 | 0 | 53.46 | 80.19 | 1443.42 | 6100
2024-02-18 | E1105 | PAC-3 | Test | Assembler | 35 | 40 | 0 | 82.01 | 123.02 | 3280.4 | 6100
2024-02-18 | E1087 | THAAD | Test | Engineer | 42 | 41 | 1 | 96.22 | 144.33 | 3993.13 | 6100
2024-02-18 | E1061 | HIMARS | Manufacturing | Technician | 32 | 27 | 0 | 66.25 | 99.38 | 1788.75 | 6200
2024-02-18 | E1023 | Javelin | Engineering | Technician | 35 | 34 | 0 | 68.79 | 103.19 | 2338.86 | 6100
2024-02-18 | E1100 | PAC-3 | Test | Assembler | 33 | 34 | 0 | 113.72 | 170.58 | 3866.48 | 6200
2024-02-25 | E1093 | Javelin | Manufacturing | Analyst | 33 | 28 | 0 | 119.69 | 179.53 | 3351.32 | 6200
2024-02-25 | E1039 | THAAD | Program Control | Assembler | 38 | 40 | 0 | 103.48 | 155.22 | 4139.2 | 6200
2024-02-25 | E1030 | PAC-3 | Manufacturing | Analyst | 44 | 41 | 1 | 41.12 | 61.68 | 1706.48 | 6100
2024-02-25 | E1075 | HIMARS | Engineering | Analyst | 38 | 39 | 0 | 45.02 | 67.53 | 1755.78 | 6200
2024-02-25 | E1077 | PAC-3 | Test | Engineer | 39 | 42 | 2 | 91.94 | 137.91 | 3953.42 | 6200
2024-02-25 | E1082 | HIMARS | Test | Engineer | 38 | 33 | 0 | 54.34 | 81.51 | 1793.22 | 6200
2024-02-25 | E1008 | PAC-3 | Program Control | Assembler | 36 | 36 | 0 | 87.02 | 130.53 | 3132.72 | 6100
2024-02-25 | E1075 | THAAD | Manufacturing | Technician | 42 | 41 | 1 | 117.56 | 176.34 | 4878.74 | 6200
2024-02-25 | E1035 | HIMARS | Program Control | Engineer | 34 | 38 | 0 | 89.42 | 134.13 | 3397.96 | 6200
2024-02-25 | E1053 | Javelin | Manufacturing | Engineer | 42 | 43 | 3 | 78.35 | 117.52 | 3486.56 | 6200
2024-02-25 | E1085 | PAC-3 | Engineering | Analyst | 30 | 30 | 0 | 54.29 | 81.44 | 1628.7 | 6100
2024-02-25 | E1079 | PAC-3 | Test | Assembler | 36 | 40 | 0 | 118.87 | 178.31 | 4754.8 | 6200
2024-02-25 | E1012 | Javelin | Manufacturing | Assembler | 39 | 40 | 0 | 70.51 | 105.77 | 2820.4 | 6100
2024-02-25 | E1090 | Javelin | Program Control | Assembler | 40 | 38 | 0 | 50.47 | 75.7 | 1917.86 | 6200
2024-02-25 | E1023 | HIMARS | Engineering | Technician | 34 | 33 | 0 | 106.02 | 159.03 | 3498.66 | 6200
2024-03-03 | E1023 | HIMARS | Engineering | Analyst | 37 | 38 | 0 | 48.88 | 73.32 | 1857.44 | 6200
2024-03-03 | E1069 | THAAD | Manufacturing | Engineer | 42 | 46 | 6 | 102.86 | 154.29 | 5040.14 | 6100
2024-03-03 | E1003 | HIMARS | Program Control | Assembler | 30 | 26 | 0 | 88.64 | 132.96 | 2304.64 | 6200
2024-03-03 | E1106 | HIMARS | Program Control | Engineer | 40 | 41 | 1 | 40.99 | 61.48 | 1701.08 | 6100
2024-03-03 | E1030 | HIMARS | Test | Technician | 41 | 43 | 3 | 77.43 | 116.15 | 3445.65 | 6200
2024-03-03 | E1052 | Javelin | Program Control | Assembler | 33 | 36 | 0 | 79.18 | 118.77 | 2850.48 | 6100
2024-03-03 | E1011 | HIMARS | Manufacturing | Assembler | 40 | 43 | 3 | 82.47 | 123.7 | 3669.9 | 6200
2024-03-03 | E1058 | THAAD | Engineering | Analyst | 37 | 40 | 0 | 68.94 | 103.41 | 2757.6 | 6200
2024-03-03 | E1005 | THAAD | Engineering | Analyst | 31 | 31 | 0 | 117.43 | 176.15 | 3640.33 | 6100
2024-03-03 | E1013 | PAC-3 | Manufacturing | Assembler | 30 | 28 | 0 | 95.14 | 142.71 | 2663.92 | 6100
2024-03-03 | E1078 | Javelin | Test | Technician | 43 | 39 | 0 | 53.66 | 80.49 | 2092.74 | 6100
2024-03-03 | E1023 | PAC-3 | Test | Analyst | 32 | 28 | 0 | 65.92 | 98.88 | 1845.76 | 6200
2024-03-03 | E1114 | PAC-3 | Program Control | Engineer | 43 | 43 | 3 | 118.04 | 177.06 | 5252.78 | 6200
2024-03-03 | E1076 | THAAD | Program Control | Assembler | 43 | 44 | 4 | 101.34 | 152.01 | 4661.64 | 6200
2024-03-03 | E1018 | PAC-3 | Program Control | Assembler | 38 | 43 | 3 | 86.21 | 129.31 | 3836.33 | 6200
2024-03-10 | E1092 | HIMARS | Program Control | Assembler | 34 | 33 | 0 | 65.36 | 98.04 | 2156.88 | 6100
2024-03-10 | E1044 | THAAD | Manufacturing | Technician | 36 | 34 | 0 | 108.06 | 162.09 | 3674.04 | 6100
2024-03-10 | E1052 | Javelin | Test | Analyst | 35 | 40 | 0 | 75.88 | 113.82 | 3035.2 | 6100
2024-03-10 | E1043 | PAC-3 | Test | Assembler | 40 | 44 | 4 | 43.84 | 65.76 | 2016.64 | 6200
2024-03-10 | E1007 | HIMARS | Test | Analyst | 38 | 35 | 0 | 70.26 | 105.39 | 2459.1 | 6200
2024-03-10 | E1013 | HIMARS | Program Control | Technician | 44 | 44 | 4 | 50.43 | 75.64 | 2319.76 | 6200
2024-03-10 | E1039 | PAC-3 | Test | Engineer | 42 | 37 | 0 | 42.43 | 63.64 | 1569.91 | 6200
2024-03-10 | E1010 | THAAD | Program Control | Engineer | 37 | 39 | 0 | 73.6 | 110.4 | 2870.4 | 6100
2024-03-10 | E1002 | HIMARS | Program Control | Assembler | 40 | 38 | 0 | 73.11 | 109.66 | 2778.18 | 6200
2024-03-10 | E1026 | THAAD | Engineering | Engineer | 41 | 44 | 4 | 60.81 | 91.22 | 2797.28 | 6200
2024-03-10 | E1109 | THAAD | Manufacturing | Technician | 37 | 32 | 0 | 102.85 | 154.27 | 3291.2 | 6100
2024-03-10 | E1078 | HIMARS | Engineering | Assembler | 32 | 33 | 0 | 113.44 | 170.16 | 3743.52 | 6200
2024-03-10 | E1055 | PAC-3 | Engineering | Technician | 32 | 34 | 0 | 116.55 | 174.82 | 3962.7 | 6200
2024-03-10 | E1092 | PAC-3 | Engineering | Assembler | 37 | 32 | 0 | 82.61 | 123.91 | 2643.52 | 6200
2024-03-10 | E1058 | THAAD | Manufacturing | Engineer | 36 | 41 | 1 | 88.91 | 133.37 | 3689.77 | 6100
2024-03-17 | E1005 | PAC-3 | Engineering | Analyst | 31 | 29 | 0 | 53.69 | 80.53 | 1557.01 | 6200
2024-03-17 | E1058 | THAAD | Manufacturing | Technician | 35 | 30 | 0 | 102.56 | 153.84 | 3076.8 | 6100
2024-03-17 | E1046 | THAAD | Manufacturing | Engineer | 42 | 45 | 5 | 73.56 | 110.34 | 3494.1 | 6200
2024-03-17 | E1012 | PAC-3 | Program Control | Engineer | 36 | 38 | 0 | 81.11 | 121.66 | 3082.18 | 6200
2024-03-17 | E1075 | HIMARS | Program Control | Engineer | 37 | 32 | 0 | 77.49 | 116.23 | 2479.68 | 6100
2024-03-17 | E1026 | THAAD | Program Control | Technician | 33 | 35 | 0 | 84.45 | 126.68 | 2955.75 | 6100
2024-03-17 | E1064 | THAAD | Test | Analyst | 32 | 32 | 0 | 114.16 | 171.24 | 3653.12 | 6200
2024-03-17 | E1092 | PAC-3 | Test | Technician | 42 | 37 | 0 | 87.69 | 131.53 | 3244.53 | 6200
2024-03-17 | E1023 | THAAD | Engineering | Engineer | 32 | 28 | 0 | 76.17 | 114.25 | 2132.76 | 6100
2024-03-17 | E1041 | PAC-3 | Engineering | Analyst | 42 | 45 | 5 | 78.67 | 118 | 3736.8 | 6100
2024-03-17 | E1019 | PAC-3 | Engineering | Engineer | 32 | 33 | 0 | 52.54 | 78.81 | 1733.82 | 6200
2024-03-17 | E1070 | Javelin | Manufacturing | Analyst | 37 | 40 | 0 | 82.39 | 123.59 | 3295.6 | 6100
2024-03-17 | E1030 | THAAD | Program Control | Engineer | 36 | 35 | 0 | 71.2 | 106.8 | 2492 | 6100
2024-03-17 | E1040 | THAAD | Engineering | Technician | 44 | 42 | 2 | 116.47 | 174.7 | 5008.2 | 6200
2024-03-17 | E1075 | THAAD | Program Control | Analyst | 34 | 34 | 0 | 104.34 | 156.51 | 3547.56 | 6100
2024-03-24 | E1103 | PAC-3 | Program Control | Technician | 33 | 34 | 0 | 71.05 | 106.57 | 2415.7 | 6200
2024-03-24 | E1111 | PAC-3 | Engineering | Engineer | 40 | 35 | 0 | 73.06 | 109.59 | 2557.1 | 6200
2024-03-24 | E1041 | HIMARS | Program Control | Assembler | 39 | 37 | 0 | 101.76 | 152.64 | 3765.12 | 6100
2024-03-24 | E1104 | THAAD | Program Control | Assembler | 38 | 37 | 0 | 94.71 | 142.06 | 3504.27 | 6200
2024-03-24 | E1106 | PAC-3 | Test | Engineer | 39 | 37 | 0 | 111.99 | 167.98 | 4143.63 | 6100
2024-03-24 | E1104 | HIMARS | Program Control | Engineer | 35 | 33 | 0 | 55.89 | 83.84 | 1844.37 | 6200
2024-03-24 | E1066 | Javelin | Engineering | Technician | 40 | 39 | 0 | 53.83 | 80.75 | 2099.37 | 6100
2024-03-24 | E1008 | HIMARS | Program Control | Technician | 31 | 28 | 0 | 65.01 | 97.52 | 1820.28 | 6200
2024-03-24 | E1094 | THAAD | Engineering | Assembler | 36 | 37 | 0 | 102.08 | 153.12 | 3776.96 | 6100
2024-03-24 | E1068 | PAC-3 | Test | Assembler | 32 | 29 | 0 | 98.94 | 148.41 | 2869.26 | 6200
2024-03-24 | E1030 | THAAD | Test | Engineer | 40 | 45 | 5 | 82.37 | 123.56 | 3912.6 | 6100
2024-03-24 | E1016 | Javelin | Engineering | Assembler | 44 | 48 | 8 | 79.77 | 119.66 | 4148.08 | 6200
2024-03-24 | E1022 | Javelin | Manufacturing | Analyst | 41 | 44 | 4 | 72.64 | 108.96 | 3341.44 | 6100
2024-03-24 | E1104 | HIMARS | Engineering | Technician | 33 | 36 | 0 | 73.45 | 110.18 | 2644.2 | 6100
2024-03-24 | E1052 | THAAD | Manufacturing | Technician | 32 | 34 | 0 | 118.49 | 177.73 | 4028.66 | 6200
2024-03-31 | E1026 | THAAD | Test | Technician | 34 | 29 | 0 | 107.56 | 161.34 | 3119.24 | 6200
2024-03-31 | E1056 | PAC-3 | Test | Technician | 33 | 29 | 0 | 103.98 | 155.97 | 3015.42 | 6100
2024-03-31 | E1059 | Javelin | Test | Analyst | 32 | 32 | 0 | 93.94 | 140.91 | 3006.08 | 6200
2024-03-31 | E1092 | THAAD | Manufacturing | Analyst | 42 | 39 | 0 | 104.72 | 157.08 | 4084.08 | 6100
2024-03-31 | E1082 | Javelin | Test | Assembler | 40 | 44 | 4 | 106.17 | 159.25 | 4883.8 | 6100
2024-03-31 | E1095 | THAAD | Program Control | Engineer | 38 | 41 | 1 | 79.71 | 119.56 | 3307.96 | 6200
2024-03-31 | E1036 | HIMARS | Test | Engineer | 41 | 45 | 5 | 57.1 | 85.65 | 2712.25 | 6100
2024-03-31 | E1043 | PAC-3 | Manufacturing | Analyst | 41 | 37 | 0 | 69.72 | 104.58 | 2579.64 | 6100
2024-03-31 | E1003 | HIMARS | Program Control | Assembler | 39 | 43 | 3 | 110.43 | 165.65 | 4914.15 | 6100
2024-03-31 | E1082 | Javelin | Test | Assembler | 34 | 32 | 0 | 114.49 | 171.73 | 3663.68 | 6200
2024-03-31 | E1009 | PAC-3 | Manufacturing | Engineer | 44 | 45 | 5 | 60.18 | 90.27 | 2858.55 | 6200
2024-03-31 | E1082 | HIMARS | Manufacturing | Technician | 44 | 42 | 2 | 83.67 | 125.5 | 3597.8 | 6100
2024-03-31 | E1006 | PAC-3 | Program Control | Assembler | 39 | 36 | 0 | 96.79 | 145.19 | 3484.44 | 6200
2024-03-31 | E1018 | THAAD | Test | Analyst | 42 | 47 | 7 | 54.1 | 81.15 | 2732.05 | 6100
2024-03-31 | E1016 | Javelin | Manufacturing | Analyst | 32 | 30 | 0 | 91.88 | 137.82 | 2756.4 | 6100
2024-04-07 | E1100 | PAC-3 | Manufacturing | Engineer | 41 | 45 | 5 | 92.66 | 138.99 | 4401.35 | 6200
2024-04-07 | E1001 | PAC-3 | Program Control | Technician | 35 | 30 | 0 | 70.1 | 105.15 | 2103 | 6100
2024-04-07 | E1107 | HIMARS | Program Control | Analyst | 32 | 27 | 0 | 114.23 | 171.34 | 3084.21 | 6200
2024-04-07 | E1085 | HIMARS | Manufacturing | Engineer | 30 | 30 | 0 | 99.86 | 149.79 | 2995.8 | 6100
2024-04-07 | E1090 | HIMARS | Test | Technician | 43 | 48 | 8 | 97.89 | 146.84 | 5090.32 | 6200
2024-04-07 | E1107 | HIMARS | Manufacturing | Technician | 34 | 31 | 0 | 111.13 | 166.69 | 3445.03 | 6200
2024-04-07 | E1102 | THAAD | Program Control | Engineer | 41 | 40 | 0 | 112.05 | 168.07 | 4482 | 6200
2024-04-07 | E1080 | HIMARS | Engineering | Technician | 44 | 39 | 0 | 115.41 | 173.12 | 4500.99 | 6200
2024-04-07 | E1011 | PAC-3 | Engineering | Engineer | 33 | 35 | 0 | 68.48 | 102.72 | 2396.8 | 6200
2024-04-07 | E1010 | THAAD | Test | Analyst | 39 | 41 | 1 | 76.33 | 114.5 | 3167.7 | 6200
2024-04-07 | E1072 | PAC-3 | Manufacturing | Analyst | 31 | 34 | 0 | 49.66 | 74.49 | 1688.44 | 6100
2024-04-07 | E1084 | PAC-3 | Program Control | Assembler | 36 | 32 | 0 | 98.73 | 148.09 | 3159.36 | 6200
2024-04-07 | E1063 | THAAD | Program Control | Analyst | 32 | 31 | 0 | 49.89 | 74.84 | 1546.59 | 6100
2024-04-07 | E1082 | Javelin | Program Control | Engineer | 35 | 30 | 0 | 53.89 | 80.84 | 1616.7 | 6100
2024-04-07 | E1053 | Javelin | Test | Analyst | 35 | 37 | 0 | 99.17 | 148.75 | 3669.29 | 6200
2024-04-14 | E1047 | PAC-3 | Test | Technician | 34 | 37 | 0 | 59.91 | 89.86 | 2216.67 | 6100
2024-04-14 | E1021 | THAAD | Engineering | Engineer | 42 | 41 | 1 | 71.88 | 107.82 | 2983.02 | 6100
2024-04-14 | E1046 | THAAD | Test | Assembler | 40 | 40 | 0 | 42.96 | 64.44 | 1718.4 | 6200
2024-04-14 | E1118 | Javelin | Engineering | Analyst | 39 | 38 | 0 | 58.45 | 87.68 | 2221.1 | 6200
2024-04-14 | E1013 | HIMARS | Test | Technician | 43 | 41 | 1 | 65.56 | 98.34 | 2720.74 | 6100
2024-04-14 | E1108 | THAAD | Test | Assembler | 37 | 38 | 0 | 79.67 | 119.5 | 3027.46 | 6100
2024-04-14 | E1094 | THAAD | Test | Analyst | 39 | 38 | 0 | 117.17 | 175.75 | 4452.46 | 6200
2024-04-14 | E1101 | Javelin | Program Control | Analyst | 33 | 31 | 0 | 72.28 | 108.42 | 2240.68 | 6200
2024-04-14 | E1083 | PAC-3 | Manufacturing | Engineer | 39 | 36 | 0 | 79.41 | 119.11 | 2858.76 | 6200
2024-04-14 | E1107 | PAC-3 | Manufacturing | Technician | 43 | 45 | 5 | 107.31 | 160.97 | 5097.25 | 6200
2024-04-14 | E1013 | THAAD | Engineering | Analyst | 31 | 32 | 0 | 72.16 | 108.24 | 2309.12 | 6100
2024-04-14 | E1077 | Javelin | Program Control | Engineer | 30 | 28 | 0 | 86.89 | 130.34 | 2432.92 | 6200
2024-04-14 | E1006 | HIMARS | Program Control | Assembler | 36 | 38 | 0 | 119.42 | 179.13 | 4537.96 | 6200
2024-04-14 | E1087 | HIMARS | Test | Technician | 35 | 39 | 0 | 73.34 | 110.01 | 2860.26 | 6200
2024-04-14 | E1044 | THAAD | Manufacturing | Analyst | 30 | 29 | 0 | 67.44 | 101.16 | 1955.76 | 6200
2024-04-21 | E1055 | PAC-3 | Manufacturing | Technician | 31 | 32 | 0 | 64.7 | 97.05 | 2070.4 | 6100
2024-04-21 | E1116 | HIMARS | Manufacturing | Engineer | 30 | 33 | 0 | 85.88 | 128.82 | 2834.04 | 6200
2024-04-21 | E1099 | Javelin | Engineering | Engineer | 31 | 29 | 0 | 98.6 | 147.9 | 2859.4 | 6100
2024-04-21 | E1041 | Javelin | Manufacturing | Engineer | 34 | 38 | 0 | 113.61 | 170.41 | 4317.18 | 6200
2024-04-21 | E1012 | PAC-3 | Engineering | Engineer | 37 | 39 | 0 | 57.14 | 85.71 | 2228.46 | 6100
2024-04-21 | E1062 | HIMARS | Manufacturing | Engineer | 43 | 44 | 4 | 59.1 | 88.65 | 2718.6 | 6200
2024-04-21 | E1103 | Javelin | Manufacturing | Analyst | 43 | 48 | 8 | 95.62 | 143.43 | 4972.24 | 6100
2024-04-21 | E1071 | PAC-3 | Program Control | Engineer | 42 | 43 | 3 | 90.99 | 136.48 | 4049.04 | 6100
2024-04-21 | E1076 | HIMARS | Test | Technician | 34 | 35 | 0 | 113.97 | 170.95 | 3988.95 | 6100
2024-04-21 | E1074 | PAC-3 | Test | Technician | 44 | 39 | 0 | 114.66 | 171.99 | 4471.74 | 6100
2024-04-21 | E1032 | THAAD | Manufacturing | Assembler | 41 | 45 | 5 | 40.58 | 60.87 | 1927.55 | 6200
2024-04-21 | E1107 | THAAD | Test | Analyst | 37 | 35 | 0 | 71.64 | 107.46 | 2507.4 | 6100
2024-04-21 | E1094 | HIMARS | Program Control | Analyst | 36 | 34 | 0 | 51.2 | 76.8 | 1740.8 | 6100
2024-04-21 | E1071 | Javelin | Engineering | Assembler | 34 | 35 | 0 | 66 | 99 | 2310 | 6200
2024-04-21 | E1012 | Javelin | Test | Analyst | 33 | 29 | 0 | 88.54 | 132.81 | 2567.66 | 6100
2024-04-28 | E1077 | Javelin | Engineering | Analyst | 41 | 44 | 4 | 51.82 | 77.73 | 2383.72 | 6200
2024-04-28 | E1001 | PAC-3 | Program Control | Analyst | 43 | 43 | 3 | 57.25 | 85.88 | 2547.64 | 6200
2024-04-28 | E1094 | THAAD | Engineering | Engineer | 41 | 36 | 0 | 98.8 | 148.2 | 3556.8 | 6200
2024-04-28 | E1111 | THAAD | Test | Assembler | 34 | 37 | 0 | 106.24 | 159.36 | 3930.88 | 6200
2024-04-28 | E1042 | THAAD | Manufacturing | Assembler | 43 | 43 | 3 | 107.79 | 161.69 | 4796.67 | 6200
2024-04-28 | E1059 | PAC-3 | Program Control | Engineer | 33 | 34 | 0 | 53.71 | 80.56 | 1826.14 | 6100
2024-04-28 | E1037 | HIMARS | Manufacturing | Technician | 33 | 35 | 0 | 45.03 | 67.55 | 1576.05 | 6200
2024-04-28 | E1103 | THAAD | Manufacturing | Analyst | 44 | 42 | 2 | 71.21 | 106.81 | 3062.02 | 6100
2024-04-28 | E1045 | Javelin | Test | Analyst | 42 | 43 | 3 | 57.21 | 85.81 | 2545.83 | 6100
2024-04-28 | E1094 | THAAD | Program Control | Technician | 33 | 28 | 0 | 61.96 | 92.94 | 1734.88 | 6100
2024-04-28 | E1086 | HIMARS | Manufacturing | Assembler | 35 | 34 | 0 | 110.01 | 165.02 | 3740.34 | 6200
2024-04-28 | E1041 | Javelin | Engineering | Analyst | 31 | 35 | 0 | 108.25 | 162.38 | 3788.75 | 6200
2024-04-28 | E1014 | PAC-3 | Test | Engineer | 40 | 44 | 4 | 116.33 | 174.5 | 5351.2 | 6100
2024-04-28 | E1112 | THAAD | Engineering | Assembler | 35 | 35 | 0 | 45.34 | 68.01 | 1586.9 | 6100
2024-04-28 | E1067 | THAAD | Test | Engineer | 35 | 33 | 0 | 53.46 | 80.19 | 1764.18 | 6200
2024-05-05 | E1099 | HIMARS | Manufacturing | Engineer | 36 | 38 | 0 | 66.63 | 99.94 | 2531.94 | 6100
2024-05-05 | E1072 | THAAD | Program Control | Analyst | 39 | 44 | 4 | 88.95 | 133.43 | 4091.72 | 6200
2024-05-05 | E1094 | Javelin | Test | Analyst | 31 | 30 | 0 | 87.02 | 130.53 | 2610.6 | 6100
2024-05-05 | E1028 | PAC-3 | Program Control | Engineer | 33 | 34 | 0 | 90 | 135 | 3060 | 6100
2024-05-05 | E1075 | THAAD | Engineering | Engineer | 30 | 32 | 0 | 48.63 | 72.95 | 1556.16 | 6200
2024-05-05 | E1095 | THAAD | Manufacturing | Assembler | 41 | 36 | 0 | 74.88 | 112.32 | 2695.68 | 6200
2024-05-05 | E1069 | THAAD | Program Control | Engineer | 38 | 36 | 0 | 52.93 | 79.39 | 1905.48 | 6100
2024-05-05 | E1086 | THAAD | Manufacturing | Analyst | 43 | 38 | 0 | 46.71 | 70.06 | 1774.98 | 6100
2024-05-05 | E1000 | THAAD | Manufacturing | Assembler | 35 | 40 | 0 | 89.35 | 134.02 | 3574 | 6200
2024-05-05 | E1109 | PAC-3 | Test | Technician | 32 | 29 | 0 | 109.72 | 164.58 | 3181.88 | 6100
2024-05-05 | E1067 | HIMARS | Test | Technician | 40 | 43 | 3 | 80.61 | 120.91 | 3587.13 | 6200
2024-05-05 | E1037 | Javelin | Test | Analyst | 42 | 43 | 3 | 67.86 | 101.79 | 3019.77 | 6200
2024-05-05 | E1025 | Javelin | Test | Engineer | 42 | 40 | 0 | 81.65 | 122.48 | 3266 | 6200
2024-05-05 | E1079 | Javelin | Engineering | Technician | 42 | 46 | 6 | 118.77 | 178.16 | 5819.76 | 6200
2024-05-05 | E1007 | THAAD | Manufacturing | Technician | 31 | 34 | 0 | 42.4 | 63.6 | 1441.6 | 6200
2024-05-12 | E1084 | Javelin | Program Control | Analyst | 39 | 35 | 0 | 114.2 | 171.3 | 3997 | 6200
2024-05-12 | E1054 | PAC-3 | Manufacturing | Technician | 43 | 45 | 5 | 86.04 | 129.06 | 4086.9 | 6100
2024-05-12 | E1116 | Javelin | Program Control | Technician | 36 | 37 | 0 | 86.48 | 129.72 | 3199.76 | 6100
2024-05-12 | E1052 | HIMARS | Program Control | Assembler | 41 | 43 | 3 | 77.15 | 115.73 | 3433.19 | 6200
2024-05-12 | E1117 | THAAD | Program Control | Assembler | 40 | 43 | 3 | 108.61 | 162.91 | 4833.13 | 6100
2024-05-12 | E1090 | THAAD | Engineering | Assembler | 35 | 32 | 0 | 69.6 | 104.4 | 2227.2 | 6100
2024-05-12 | E1033 | HIMARS | Program Control | Assembler | 44 | 39 | 0 | 56.36 | 84.54 | 2198.04 | 6100
2024-05-12 | E1101 | HIMARS | Engineering | Technician | 32 | 27 | 0 | 75.29 | 112.94 | 2032.83 | 6100
2024-05-12 | E1004 | THAAD | Engineering | Technician | 34 | 31 | 0 | 88.97 | 133.45 | 2758.07 | 6200
2024-05-12 | E1017 | THAAD | Manufacturing | Technician | 37 | 39 | 0 | 81.06 | 121.59 | 3161.34 | 6100
2024-05-12 | E1115 | HIMARS | Engineering | Assembler | 36 | 36 | 0 | 70.26 | 105.39 | 2529.36 | 6200
2024-05-12 | E1069 | HIMARS | Test | Assembler | 36 | 40 | 0 | 55.07 | 82.61 | 2202.8 | 6200
2024-05-12 | E1001 | HIMARS | Engineering | Engineer | 30 | 30 | 0 | 57.81 | 86.72 | 1734.3 | 6100
2024-05-12 | E1059 | PAC-3 | Manufacturing | Engineer | 41 | 42 | 2 | 59.11 | 88.66 | 2541.72 | 6200
2024-05-12 | E1064 | PAC-3 | Program Control | Analyst | 43 | 40 | 0 | 91.51 | 137.27 | 3660.4 | 6100
2024-05-19 | E1107 | PAC-3 | Manufacturing | Engineer | 43 | 38 | 0 | 110.42 | 165.63 | 4195.96 | 6200
2024-05-19 | E1064 | Javelin | Engineering | Assembler | 39 | 44 | 4 | 95.14 | 142.71 | 4376.44 | 6100
2024-05-19 | E1019 | THAAD | Engineering | Analyst | 34 | 35 | 0 | 94.34 | 141.51 | 3301.9 | 6200
2024-05-19 | E1045 | HIMARS | Engineering | Assembler | 39 | 40 | 0 | 65.83 | 98.75 | 2633.2 | 6100
2024-05-19 | E1026 | Javelin | Program Control | Analyst | 39 | 43 | 3 | 87.68 | 131.52 | 3901.76 | 6200
2024-05-19 | E1113 | THAAD | Program Control | Technician | 32 | 34 | 0 | 68.41 | 102.61 | 2325.94 | 6100
2024-05-19 | E1100 | THAAD | Manufacturing | Technician | 36 | 31 | 0 | 54.83 | 82.25 | 1699.73 | 6200
2024-05-19 | E1041 | HIMARS | Engineering | Analyst | 42 | 47 | 7 | 92.49 | 138.73 | 4670.71 | 6100
2024-05-19 | E1004 | THAAD | Engineering | Analyst | 34 | 30 | 0 | 112.72 | 169.08 | 3381.6 | 6200
2024-05-19 | E1077 | PAC-3 | Manufacturing | Analyst | 30 | 27 | 0 | 105.64 | 158.46 | 2852.28 | 6100
2024-05-19 | E1106 | HIMARS | Engineering | Engineer | 34 | 32 | 0 | 61.67 | 92.5 | 1973.44 | 6100
2024-05-19 | E1023 | HIMARS | Manufacturing | Assembler | 30 | 29 | 0 | 88.11 | 132.16 | 2555.19 | 6100
2024-05-19 | E1089 | PAC-3 | Test | Analyst | 37 | 34 | 0 | 74.35 | 111.52 | 2527.9 | 6100
2024-05-19 | E1104 | Javelin | Manufacturing | Engineer | 37 | 33 | 0 | 76.76 | 115.14 | 2533.08 | 6200
2024-05-19 | E1114 | THAAD | Engineering | Engineer | 42 | 37 | 0 | 105.14 | 157.71 | 3890.18 | 6100
2024-05-26 | E1003 | HIMARS | Test | Analyst | 39 | 42 | 2 | 106.98 | 160.47 | 4600.14 | 6100
2024-05-26 | E1119 | HIMARS | Manufacturing | Analyst | 32 | 27 | 0 | 73.06 | 109.59 | 1972.62 | 6100
2024-05-26 | E1070 | HIMARS | Manufacturing | Analyst | 43 | 40 | 0 | 72.35 | 108.52 | 2894 | 6200
2024-05-26 | E1113 | PAC-3 | Manufacturing | Technician | 32 | 29 | 0 | 86.64 | 129.96 | 2512.56 | 6100
2024-05-26 | E1009 | THAAD | Engineering | Engineer | 32 | 29 | 0 | 41.88 | 62.82 | 1214.52 | 6200
2024-05-26 | E1101 | HIMARS | Test | Assembler | 35 | 37 | 0 | 103.19 | 154.78 | 3818.03 | 6200
2024-05-26 | E1061 | Javelin | Test | Analyst | 30 | 32 | 0 | 105.82 | 158.73 | 3386.24 | 6100
2024-05-26 | E1018 | PAC-3 | Program Control | Assembler | 35 | 40 | 0 | 98.95 | 148.43 | 3958 | 6200
2024-05-26 | E1002 | PAC-3 | Program Control | Analyst | 36 | 33 | 0 | 98.76 | 148.14 | 3259.08 | 6100
2024-05-26 | E1039 | Javelin | Program Control | Assembler | 41 | 46 | 6 | 95.2 | 142.8 | 4664.8 | 6200
2024-05-26 | E1113 | THAAD | Manufacturing | Assembler | 44 | 44 | 4 | 51.13 | 76.7 | 2352 | 6200
2024-05-26 | E1017 | PAC-3 | Program Control | Engineer | 43 | 42 | 2 | 55.95 | 83.93 | 2405.86 | 6100
2024-05-26 | E1090 | HIMARS | Program Control | Analyst | 36 | 33 | 0 | 100.59 | 150.88 | 3319.47 | 6200
2024-05-26 | E1082 | PAC-3 | Engineering | Analyst | 35 | 33 | 0 | 76.3 | 114.45 | 2517.9 | 6100
2024-05-26 | E1058 | PAC-3 | Manufacturing | Assembler | 37 | 32 | 0 | 43.58 | 65.37 | 1394.56 | 6100
2024-06-02 | E1047 | THAAD | Engineering | Analyst | 39 | 35 | 0 | 64.78 | 97.17 | 2267.3 | 6100
2024-06-02 | E1006 | PAC-3 | Program Control | Assembler | 43 | 42 | 2 | 104.84 | 157.26 | 4508.12 | 6200
2024-06-02 | E1099 | HIMARS | Program Control | Engineer | 44 | 42 | 2 | 46.38 | 69.57 | 1994.34 | 6100
2024-06-02 | E1099 | Javelin | Engineering | Analyst | 43 | 46 | 6 | 114.78 | 172.17 | 5624.22 | 6100
2024-06-02 | E1035 | THAAD | Manufacturing | Analyst | 41 | 43 | 3 | 72.33 | 108.5 | 3218.7 | 6200
2024-06-02 | E1113 | THAAD | Engineering | Technician | 44 | 40 | 0 | 85.89 | 128.84 | 3435.6 | 6200
2024-06-02 | E1078 | Javelin | Engineering | Engineer | 42 | 42 | 2 | 104.11 | 156.16 | 4476.72 | 6200
2024-06-02 | E1075 | HIMARS | Engineering | Analyst | 30 | 29 | 0 | 107.72 | 161.58 | 3123.88 | 6200
2024-06-02 | E1119 | THAAD | Manufacturing | Analyst | 39 | 35 | 0 | 98.54 | 147.81 | 3448.9 | 6100
2024-06-02 | E1006 | PAC-3 | Program Control | Analyst | 34 | 34 | 0 | 97.02 | 145.53 | 3298.68 | 6100
2024-06-02 | E1024 | Javelin | Program Control | Analyst | 34 | 39 | 0 | 104.4 | 156.6 | 4071.6 | 6100
2024-06-02 | E1007 | PAC-3 | Engineering | Assembler | 33 | 29 | 0 | 89.3 | 133.95 | 2589.7 | 6200
2024-06-02 | E1065 | THAAD | Manufacturing | Assembler | 40 | 40 | 0 | 115.38 | 173.07 | 4615.2 | 6200
2024-06-02 | E1114 | PAC-3 | Manufacturing | Technician | 35 | 37 | 0 | 67.25 | 100.88 | 2488.25 | 6100
2024-06-02 | E1111 | THAAD | Test | Assembler | 42 | 45 | 5 | 69.52 | 104.28 | 3302.2 | 6100
2024-06-09 | E1095 | HIMARS | Engineering | Technician | 31 | 31 | 0 | 76.88 | 115.32 | 2383.28 | 6200
2024-06-09 | E1055 | THAAD | Test | Engineer | 38 | 40 | 0 | 70.63 | 105.94 | 2825.2 | 6200
2024-06-09 | E1042 | PAC-3 | Program Control | Analyst | 30 | 33 | 0 | 92.1 | 138.15 | 3039.3 | 6200
2024-06-09 | E1050 | HIMARS | Test | Technician | 37 | 38 | 0 | 56.13 | 84.2 | 2132.94 | 6200
2024-06-09 | E1052 | Javelin | Engineering | Analyst | 40 | 40 | 0 | 108.35 | 162.52 | 4334 | 6100
2024-06-09 | E1041 | PAC-3 | Test | Assembler | 38 | 38 | 0 | 96.74 | 145.11 | 3676.12 | 6200
2024-06-09 | E1059 | PAC-3 | Manufacturing | Assembler | 31 | 30 | 0 | 103.31 | 154.97 | 3099.3 | 6200
2024-06-09 | E1091 | HIMARS | Test | Analyst | 39 | 41 | 1 | 109.89 | 164.84 | 4560.44 | 6200
2024-06-09 | E1078 | Javelin | Program Control | Assembler | 32 | 37 | 0 | 110.11 | 165.16 | 4074.07 | 6200
2024-06-09 | E1062 | THAAD | Test | Assembler | 38 | 39 | 0 | 97.21 | 145.81 | 3791.19 | 6100
2024-06-09 | E1089 | PAC-3 | Program Control | Assembler | 37 | 34 | 0 | 93.18 | 139.77 | 3168.12 | 6200
2024-06-09 | E1070 | THAAD | Engineering | Technician | 34 | 35 | 0 | 47.54 | 71.31 | 1663.9 | 6200
2024-06-09 | E1085 | PAC-3 | Engineering | Technician | 40 | 40 | 0 | 76.85 | 115.27 | 3074 | 6200
2024-06-09 | E1022 | HIMARS | Test | Technician | 32 | 37 | 0 | 107.32 | 160.98 | 3970.84 | 6100
2024-06-09 | E1080 | PAC-3 | Manufacturing | Engineer | 35 | 30 | 0 | 82.78 | 124.17 | 2483.4 | 6100
2024-06-16 | E1086 | Javelin | Program Control | Engineer | 35 | 38 | 0 | 44.21 | 66.31 | 1679.98 | 6100
2024-06-16 | E1105 | PAC-3 | Engineering | Analyst | 42 | 39 | 0 | 101.61 | 152.41 | 3962.79 | 6200
2024-06-16 | E1101 | Javelin | Engineering | Assembler | 34 | 36 | 0 | 83.93 | 125.9 | 3021.48 | 6100
2024-06-16 | E1031 | THAAD | Engineering | Technician | 38 | 37 | 0 | 119.89 | 179.84 | 4435.93 | 6100
2024-06-16 | E1027 | HIMARS | Manufacturing | Analyst | 31 | 30 | 0 | 105.83 | 158.75 | 3174.9 | 6100
2024-06-16 | E1042 | THAAD | Engineering | Assembler | 35 | 30 | 0 | 61.05 | 91.57 | 1831.5 | 6200
2024-06-16 | E1036 | HIMARS | Program Control | Analyst | 35 | 35 | 0 | 97.22 | 145.83 | 3402.7 | 6200
2024-06-16 | E1005 | Javelin | Test | Technician | 36 | 34 | 0 | 41.14 | 61.71 | 1398.76 | 6200
2024-06-16 | E1104 | HIMARS | Manufacturing | Technician | 34 | 32 | 0 | 103.41 | 155.12 | 3309.12 | 6200
2024-06-16 | E1039 | Javelin | Manufacturing | Analyst | 40 | 42 | 2 | 108.75 | 163.12 | 4676.24 | 6200
2024-06-16 | E1009 | THAAD | Test | Engineer | 40 | 35 | 0 | 119.21 | 178.81 | 4172.35 | 6200
2024-06-16 | E1105 | Javelin | Engineering | Analyst | 30 | 28 | 0 | 78.96 | 118.44 | 2210.88 | 6200
2024-06-16 | E1112 | THAAD | Manufacturing | Assembler | 42 | 40 | 0 | 62.59 | 93.89 | 2503.6 | 6100
2024-06-16 | E1022 | HIMARS | Manufacturing | Engineer | 37 | 32 | 0 | 56.56 | 84.84 | 1809.92 | 6200
2024-06-16 | E1106 | HIMARS | Engineering | Analyst | 36 | 33 | 0 | 46.23 | 69.34 | 1525.59 | 6200
2024-06-23 | E1044 | Javelin | Test | Assembler | 37 | 41 | 1 | 40.62 | 60.93 | 1685.73 | 6200
2024-06-23 | E1034 | Javelin | Test | Assembler | 30 | 31 | 0 | 74.61 | 111.91 | 2312.91 | 6100
2024-06-23 | E1039 | HIMARS | Test | Analyst | 37 | 36 | 0 | 53.55 | 80.32 | 1927.8 | 6200
2024-06-23 | E1068 | THAAD | Test | Technician | 31 | 36 | 0 | 116.48 | 174.72 | 4193.28 | 6100
2024-06-23 | E1039 | THAAD | Test | Technician | 35 | 30 | 0 | 70.24 | 105.36 | 2107.2 | 6200
2024-06-23 | E1014 | PAC-3 | Manufacturing | Technician | 30 | 30 | 0 | 87 | 130.5 | 2610 | 6200
2024-06-23 | E1030 | PAC-3 | Engineering | Analyst | 44 | 40 | 0 | 95.86 | 143.79 | 3834.4 | 6100
2024-06-23 | E1060 | PAC-3 | Program Control | Technician | 42 | 38 | 0 | 82.35 | 123.52 | 3129.3 | 6200
2024-06-23 | E1115 | Javelin | Engineering | Analyst | 44 | 45 | 5 | 106.58 | 159.87 | 5062.55 | 6200
2024-06-23 | E1052 | Javelin | Program Control | Engineer | 41 | 37 | 0 | 119.11 | 178.66 | 4407.07 | 6100
2024-06-23 | E1033 | PAC-3 | Manufacturing | Technician | 33 | 30 | 0 | 58.06 | 87.09 | 1741.8 | 6100
2024-06-23 | E1114 | PAC-3 | Engineering | Technician | 44 | 47 | 7 | 42.7 | 64.05 | 2156.35 | 6100
2024-06-23 | E1092 | PAC-3 | Program Control | Analyst | 36 | 37 | 0 | 102.92 | 154.38 | 3808.04 | 6200
2024-06-23 | E1081 | HIMARS | Test | Engineer | 36 | 37 | 0 | 42.68 | 64.02 | 1579.16 | 6200
2024-06-23 | E1075 | HIMARS | Test | Assembler | 30 | 27 | 0 | 67.04 | 100.56 | 1810.08 | 6200
2024-06-30 | E1029 | Javelin | Manufacturing | Engineer | 42 | 37 | 0 | 48.55 | 72.82 | 1796.35 | 6200
2024-06-30 | E1105 | THAAD | Manufacturing | Engineer | 39 | 37 | 0 | 45.78 | 68.67 | 1693.86 | 6100
2024-06-30 | E1011 | THAAD | Manufacturing | Technician | 40 | 44 | 4 | 89.67 | 134.5 | 4124.8 | 6200
2024-06-30 | E1099 | HIMARS | Engineering | Assembler | 44 | 40 | 0 | 109.74 | 164.61 | 4389.6 | 6100
2024-06-30 | E1001 | THAAD | Test | Analyst | 35 | 35 | 0 | 97.04 | 145.56 | 3396.4 | 6100
2024-06-30 | E1080 | Javelin | Manufacturing | Assembler | 39 | 38 | 0 | 72.43 | 108.65 | 2752.34 | 6100
2024-06-30 | E1040 | PAC-3 | Engineering | Engineer | 31 | 35 | 0 | 104.34 | 156.51 | 3651.9 | 6200
2024-06-30 | E1026 | Javelin | Program Control | Technician | 37 | 39 | 0 | 92.78 | 139.17 | 3618.42 | 6200
2024-06-30 | E1039 | Javelin | Program Control | Technician | 30 | 30 | 0 | 61.03 | 91.55 | 1830.9 | 6200
2024-06-30 | E1029 | Javelin | Engineering | Technician | 39 | 41 | 1 | 54.99 | 82.48 | 2282.08 | 6200
2024-06-30 | E1008 | HIMARS | Test | Analyst | 42 | 42 | 2 | 43.51 | 65.27 | 1870.94 | 6100
2024-06-30 | E1040 | THAAD | Test | Technician | 33 | 30 | 0 | 59.51 | 89.27 | 1785.3 | 6100
2024-06-30 | E1007 | THAAD | Engineering | Analyst | 34 | 35 | 0 | 48.35 | 72.53 | 1692.25 | 6100
2024-06-30 | E1033 | THAAD | Engineering | Technician | 43 | 43 | 3 | 53.21 | 79.81 | 2367.83 | 6200
2024-06-30 | E1038 | HIMARS | Engineering | Technician | 44 | 41 | 1 | 71.17 | 106.75 | 2953.55 | 6100
2024-07-07 | E1100 | PAC-3 | Program Control | Assembler | 32 | 32 | 0 | 58.68 | 88.02 | 1877.76 | 6200
2024-07-07 | E1044 | HIMARS | Test | Analyst | 34 | 30 | 0 | 48.46 | 72.69 | 1453.8 | 6100
2024-07-07 | E1044 | PAC-3 | Manufacturing | Assembler | 34 | 31 | 0 | 113.46 | 170.19 | 3517.26 | 6200
2024-07-07 | E1082 | HIMARS | Manufacturing | Assembler | 37 | 39 | 0 | 80.08 | 120.12 | 3123.12 | 6200
2024-07-07 | E1065 | HIMARS | Test | Technician | 31 | 30 | 0 | 73.31 | 109.97 | 2199.3 | 6100
2024-07-07 | E1112 | THAAD | Test | Engineer | 34 | 33 | 0 | 62.99 | 94.48 | 2078.67 | 6200
2024-07-07 | E1075 | Javelin | Program Control | Technician | 44 | 43 | 3 | 113.74 | 170.61 | 5061.43 | 6100
2024-07-07 | E1105 | THAAD | Program Control | Assembler | 39 | 36 | 0 | 105.38 | 158.07 | 3793.68 | 6100
2024-07-07 | E1072 | Javelin | Program Control | Assembler | 32 | 35 | 0 | 88.02 | 132.03 | 3080.7 | 6100
2024-07-07 | E1077 | Javelin | Engineering | Analyst | 40 | 35 | 0 | 96.5 | 144.75 | 3377.5 | 6100
2024-07-07 | E1082 | PAC-3 | Manufacturing | Engineer | 32 | 37 | 0 | 52.79 | 79.19 | 1953.23 | 6100
2024-07-07 | E1099 | HIMARS | Manufacturing | Assembler | 41 | 46 | 6 | 80.59 | 120.89 | 3948.94 | 6200
2024-07-07 | E1094 | PAC-3 | Engineering | Engineer | 33 | 36 | 0 | 113.16 | 169.74 | 4073.76 | 6200
2024-07-07 | E1012 | PAC-3 | Manufacturing | Technician | 31 | 28 | 0 | 40.81 | 61.22 | 1142.68 | 6200
2024-07-07 | E1112 | PAC-3 | Manufacturing | Assembler | 42 | 38 | 0 | 101.37 | 152.06 | 3852.06 | 6200
2024-07-14 | E1002 | PAC-3 | Program Control | Analyst | 33 | 30 | 0 | 82.56 | 123.84 | 2476.8 | 6200
2024-07-14 | E1110 | THAAD | Test | Engineer | 33 | 31 | 0 | 93.75 | 140.62 | 2906.25 | 6100
2024-07-14 | E1013 | Javelin | Program Control | Technician | 41 | 36 | 0 | 109.21 | 163.81 | 3931.56 | 6200
2024-07-14 | E1060 | Javelin | Manufacturing | Technician | 38 | 33 | 0 | 60.62 | 90.93 | 2000.46 | 6200
2024-07-14 | E1057 | THAAD | Manufacturing | Engineer | 35 | 34 | 0 | 98.71 | 148.06 | 3356.14 | 6100
2024-07-14 | E1099 | THAAD | Test | Analyst | 43 | 47 | 7 | 97.13 | 145.69 | 4905.03 | 6100
2024-07-14 | E1071 | Javelin | Engineering | Technician | 41 | 43 | 3 | 84.38 | 126.57 | 3754.91 | 6200
2024-07-14 | E1005 | HIMARS | Program Control | Analyst | 41 | 46 | 6 | 99.85 | 149.77 | 4892.62 | 6200
2024-07-14 | E1063 | Javelin | Engineering | Technician | 32 | 28 | 0 | 98.13 | 147.19 | 2747.64 | 6100
2024-07-14 | E1100 | THAAD | Test | Assembler | 43 | 45 | 5 | 74.02 | 111.03 | 3515.95 | 6200
2024-07-14 | E1043 | PAC-3 | Engineering | Engineer | 44 | 48 | 8 | 67.93 | 101.9 | 3532.4 | 6200
2024-07-14 | E1076 | THAAD | Test | Analyst | 34 | 30 | 0 | 48.52 | 72.78 | 1455.6 | 6100
2024-07-14 | E1043 | PAC-3 | Program Control | Technician | 41 | 38 | 0 | 59.42 | 89.13 | 2257.96 | 6100
2024-07-14 | E1016 | HIMARS | Engineering | Engineer | 34 | 37 | 0 | 40.15 | 60.22 | 1485.55 | 6100
2024-07-14 | E1011 | PAC-3 | Engineering | Assembler | 31 | 36 | 0 | 57.16 | 85.74 | 2057.76 | 6100
2024-07-21 | E1095 | Javelin | Engineering | Analyst | 36 | 33 | 0 | 78.15 | 117.23 | 2578.95 | 6100
2024-07-21 | E1106 | Javelin | Engineering | Engineer | 40 | 42 | 2 | 103.51 | 155.27 | 4450.94 | 6100
2024-07-21 | E1081 | HIMARS | Manufacturing | Assembler | 41 | 40 | 0 | 72.82 | 109.23 | 2912.8 | 6200
2024-07-21 | E1080 | THAAD | Program Control | Engineer | 39 | 37 | 0 | 115.03 | 172.55 | 4256.11 | 6200
2024-07-21 | E1049 | HIMARS | Engineering | Analyst | 34 | 39 | 0 | 42.64 | 63.96 | 1662.96 | 6100
2024-07-21 | E1016 | THAAD | Engineering | Analyst | 42 | 38 | 0 | 43.05 | 64.57 | 1635.9 | 6100
2024-07-21 | E1029 | HIMARS | Manufacturing | Analyst | 30 | 33 | 0 | 66.2 | 99.3 | 2184.6 | 6100
2024-07-21 | E1035 | THAAD | Manufacturing | Engineer | 43 | 45 | 5 | 50.47 | 75.7 | 2397.3 | 6200
2024-07-21 | E1088 | HIMARS | Engineering | Technician | 32 | 33 | 0 | 60.52 | 90.78 | 1997.16 | 6100
2024-07-21 | E1067 | Javelin | Test | Engineer | 33 | 35 | 0 | 106.26 | 159.39 | 3719.1 | 6200
2024-07-21 | E1095 | PAC-3 | Program Control | Technician | 34 | 35 | 0 | 101.19 | 151.78 | 3541.65 | 6100
2024-07-21 | E1066 | Javelin | Program Control | Technician | 33 | 37 | 0 | 109.03 | 163.55 | 4034.11 | 6200
2024-07-21 | E1015 | PAC-3 | Test | Engineer | 33 | 30 | 0 | 78.06 | 117.09 | 2341.8 | 6200
2024-07-21 | E1015 | THAAD | Program Control | Technician | 37 | 38 | 0 | 97.5 | 146.25 | 3705 | 6100
2024-07-21 | E1105 | Javelin | Engineering | Analyst | 43 | 38 | 0 | 103.14 | 154.71 | 3919.32 | 6100
2024-07-28 | E1085 | HIMARS | Program Control | Analyst | 32 | 36 | 0 | 72.7 | 109.05 | 2617.2 | 6200
2024-07-28 | E1116 | PAC-3 | Program Control | Analyst | 30 | 29 | 0 | 107.84 | 161.76 | 3127.36 | 6200
2024-07-28 | E1054 | PAC-3 | Engineering | Technician | 41 | 42 | 2 | 112.32 | 168.48 | 4829.76 | 6200
2024-07-28 | E1116 | HIMARS | Test | Technician | 44 | 44 | 4 | 109.55 | 164.32 | 5039.28 | 6200
2024-07-28 | E1071 | PAC-3 | Engineering | Assembler | 35 | 34 | 0 | 107.92 | 161.88 | 3669.28 | 6100
2024-07-28 | E1104 | Javelin | Program Control | Technician | 43 | 44 | 4 | 40.4 | 60.6 | 1858.4 | 6200
2024-07-28 | E1036 | HIMARS | Test | Engineer | 42 | 44 | 4 | 101.48 | 152.22 | 4668.08 | 6200
2024-07-28 | E1017 | THAAD | Test | Technician | 35 | 31 | 0 | 60.93 | 91.39 | 1888.83 | 6100
2024-07-28 | E1024 | HIMARS | Manufacturing | Assembler | 30 | 32 | 0 | 84.38 | 126.57 | 2700.16 | 6100
2024-07-28 | E1103 | Javelin | Manufacturing | Assembler | 35 | 34 | 0 | 57.38 | 86.07 | 1950.92 | 6100
2024-07-28 | E1079 | THAAD | Manufacturing | Assembler | 33 | 34 | 0 | 54.72 | 82.08 | 1860.48 | 6100
2024-07-28 | E1047 | THAAD | Program Control | Technician | 37 | 33 | 0 | 104.14 | 156.21 | 3436.62 | 6200
2024-07-28 | E1079 | HIMARS | Program Control | Engineer | 39 | 42 | 2 | 57.62 | 86.43 | 2477.66 | 6100
2024-07-28 | E1076 | THAAD | Program Control | Engineer | 44 | 41 | 1 | 72.9 | 109.35 | 3025.35 | 6200
2024-07-28 | E1056 | HIMARS | Manufacturing | Assembler | 39 | 42 | 2 | 40.02 | 60.03 | 1720.86 | 6200
2024-08-04 | E1061 | HIMARS | Program Control | Analyst | 36 | 31 | 0 | 50.21 | 75.31 | 1556.51 | 6200
2024-08-04 | E1082 | Javelin | Engineering | Technician | 31 | 31 | 0 | 115.83 | 173.75 | 3590.73 | 6200
2024-08-04 | E1014 | Javelin | Program Control | Analyst | 42 | 41 | 1 | 41.64 | 62.46 | 1728.06 | 6100
2024-08-04 | E1056 | Javelin | Test | Assembler | 41 | 37 | 0 | 119.96 | 179.94 | 4438.52 | 6100
2024-08-04 | E1047 | PAC-3 | Program Control | Analyst | 30 | 25 | 0 | 118.53 | 177.8 | 2963.25 | 6200
2024-08-04 | E1022 | HIMARS | Test | Assembler | 44 | 48 | 8 | 77.82 | 116.73 | 4046.64 | 6100
2024-08-04 | E1079 | PAC-3 | Program Control | Engineer | 43 | 38 | 0 | 55.91 | 83.86 | 2124.58 | 6200
2024-08-04 | E1055 | HIMARS | Program Control | Engineer | 37 | 35 | 0 | 60.28 | 90.42 | 2109.8 | 6100
2024-08-04 | E1067 | Javelin | Manufacturing | Analyst | 31 | 27 | 0 | 85.53 | 128.3 | 2309.31 | 6200
2024-08-04 | E1025 | PAC-3 | Test | Technician | 33 | 37 | 0 | 53.3 | 79.95 | 1972.1 | 6200
2024-08-04 | E1074 | Javelin | Manufacturing | Engineer | 36 | 35 | 0 | 103.34 | 155.01 | 3616.9 | 6100
2024-08-04 | E1108 | Javelin | Engineering | Assembler | 35 | 39 | 0 | 84 | 126 | 3276 | 6200
2024-08-04 | E1027 | HIMARS | Engineering | Engineer | 31 | 32 | 0 | 54.21 | 81.31 | 1734.72 | 6200
2024-08-04 | E1068 | Javelin | Test | Technician | 40 | 45 | 5 | 116.56 | 174.84 | 5536.6 | 6100
2024-08-04 | E1104 | THAAD | Test | Analyst | 31 | 28 | 0 | 71.18 | 106.77 | 1993.04 | 6200
2024-08-11 | E1030 | PAC-3 | Test | Assembler | 33 | 35 | 0 | 88.27 | 132.41 | 3089.45 | 6200
2024-08-11 | E1053 | PAC-3 | Engineering | Assembler | 35 | 32 | 0 | 65.98 | 98.97 | 2111.36 | 6200
2024-08-11 | E1046 | HIMARS | Program Control | Technician | 36 | 39 | 0 | 86.67 | 130 | 3380.13 | 6100
2024-08-11 | E1041 | PAC-3 | Engineering | Technician | 41 | 36 | 0 | 108.61 | 162.91 | 3909.96 | 6200
2024-08-11 | E1056 | Javelin | Engineering | Engineer | 42 | 44 | 4 | 94.96 | 142.44 | 4368.16 | 6200
2024-08-11 | E1035 | Javelin | Engineering | Analyst | 43 | 48 | 8 | 78.13 | 117.19 | 4062.72 | 6100
2024-08-11 | E1109 | THAAD | Manufacturing | Engineer | 32 | 30 | 0 | 100.76 | 151.14 | 3022.8 | 6100
2024-08-11 | E1021 | HIMARS | Engineering | Analyst | 43 | 48 | 8 | 42.57 | 63.86 | 2213.68 | 6100
2024-08-11 | E1010 | HIMARS | Manufacturing | Analyst | 35 | 34 | 0 | 48.06 | 72.09 | 1634.04 | 6200
2024-08-11 | E1009 | Javelin | Test | Analyst | 36 | 38 | 0 | 87.33 | 131 | 3318.54 | 6100
2024-08-11 | E1033 | PAC-3 | Test | Analyst | 38 | 39 | 0 | 86.35 | 129.52 | 3367.65 | 6100
2024-08-11 | E1021 | HIMARS | Engineering | Engineer | 30 | 35 | 0 | 110.23 | 165.34 | 3858.05 | 6100
2024-08-11 | E1096 | Javelin | Program Control | Assembler | 40 | 39 | 0 | 63.32 | 94.98 | 2469.48 | 6200
2024-08-11 | E1108 | HIMARS | Manufacturing | Engineer | 30 | 25 | 0 | 57.99 | 86.98 | 1449.75 | 6200
2024-08-11 | E1094 | HIMARS | Test | Assembler | 43 | 45 | 5 | 69.42 | 104.13 | 3297.45 | 6100
2024-08-18 | E1091 | PAC-3 | Program Control | Engineer | 42 | 40 | 0 | 95.96 | 143.94 | 3838.4 | 6100
2024-08-18 | E1100 | HIMARS | Program Control | Analyst | 31 | 35 | 0 | 75.81 | 113.72 | 2653.35 | 6200
2024-08-18 | E1053 | Javelin | Test | Engineer | 34 | 37 | 0 | 98.22 | 147.33 | 3634.14 | 6100
2024-08-18 | E1052 | Javelin | Program Control | Assembler | 44 | 44 | 4 | 110.19 | 165.28 | 5068.72 | 6200
2024-08-18 | E1065 | PAC-3 | Test | Assembler | 32 | 31 | 0 | 55.37 | 83.05 | 1716.47 | 6200
2024-08-18 | E1013 | HIMARS | Manufacturing | Assembler | 36 | 37 | 0 | 56.21 | 84.31 | 2079.77 | 6100
2024-08-18 | E1006 | PAC-3 | Test | Engineer | 31 | 35 | 0 | 41.69 | 62.53 | 1459.15 | 6200
2024-08-18 | E1078 | HIMARS | Test | Assembler | 43 | 43 | 3 | 88.98 | 133.47 | 3959.61 | 6200
2024-08-18 | E1080 | Javelin | Program Control | Assembler | 43 | 38 | 0 | 92.02 | 138.03 | 3496.76 | 6100
2024-08-18 | E1051 | HIMARS | Program Control | Analyst | 38 | 43 | 3 | 106.23 | 159.34 | 4727.22 | 6100
2024-08-18 | E1062 | Javelin | Test | Engineer | 30 | 25 | 0 | 61.5 | 92.25 | 1537.5 | 6200
2024-08-18 | E1115 | PAC-3 | Manufacturing | Analyst | 42 | 43 | 3 | 67.02 | 100.53 | 2982.39 | 6200
2024-08-18 | E1019 | Javelin | Test | Analyst | 36 | 39 | 0 | 94.02 | 141.03 | 3666.78 | 6200
2024-08-18 | E1032 | Javelin | Engineering | Engineer | 32 | 33 | 0 | 41.94 | 62.91 | 1384.02 | 6100
2024-08-18 | E1077 | Javelin | Test | Engineer | 31 | 31 | 0 | 113.27 | 169.91 | 3511.37 | 6100
2024-08-25 | E1039 | HIMARS | Test | Technician | 30 | 31 | 0 | 91.48 | 137.22 | 2835.88 | 6100
2024-08-25 | E1110 | THAAD | Manufacturing | Analyst | 31 | 33 | 0 | 88.06 | 132.09 | 2905.98 | 6200
2024-08-25 | E1063 | PAC-3 | Manufacturing | Analyst | 37 | 40 | 0 | 75.21 | 112.81 | 3008.4 | 6100
2024-08-25 | E1099 | HIMARS | Program Control | Engineer | 43 | 45 | 5 | 91.93 | 137.9 | 4366.7 | 6200
2024-08-25 | E1030 | HIMARS | Test | Technician | 42 | 42 | 2 | 113.2 | 169.8 | 4867.6 | 6100
2024-08-25 | E1043 | THAAD | Engineering | Analyst | 43 | 39 | 0 | 81.54 | 122.31 | 3180.06 | 6100
2024-08-25 | E1051 | HIMARS | Engineering | Technician | 36 | 35 | 0 | 62.42 | 93.63 | 2184.7 | 6200
2024-08-25 | E1087 | HIMARS | Program Control | Engineer | 41 | 41 | 1 | 58.54 | 87.81 | 2429.41 | 6100
2024-08-25 | E1072 | THAAD | Test | Analyst | 42 | 43 | 3 | 106.24 | 159.36 | 4727.68 | 6100
2024-08-25 | E1047 | Javelin | Test | Analyst | 44 | 39 | 0 | 73.48 | 110.22 | 2865.72 | 6100
2024-08-25 | E1065 | HIMARS | Program Control | Technician | 38 | 34 | 0 | 41.7 | 62.55 | 1417.8 | 6100
2024-08-25 | E1072 | THAAD | Manufacturing | Technician | 44 | 41 | 1 | 45.19 | 67.78 | 1875.38 | 6200
2024-08-25 | E1070 | Javelin | Test | Analyst | 35 | 37 | 0 | 75.7 | 113.55 | 2800.9 | 6200
2024-08-25 | E1038 | Javelin | Program Control | Engineer | 36 | 36 | 0 | 91.2 | 136.8 | 3283.2 | 6200
2024-08-25 | E1034 | PAC-3 | Test | Analyst | 44 | 47 | 7 | 50.9 | 76.35 | 2570.45 | 6200
2024-09-01 | E1020 | HIMARS | Engineering | Analyst | 31 | 33 | 0 | 46.86 | 70.29 | 1546.38 | 6100
2024-09-01 | E1042 | HIMARS | Engineering | Engineer | 34 | 39 | 0 | 56.12 | 84.18 | 2188.68 | 6100
2024-09-01 | E1049 | PAC-3 | Test | Assembler | 37 | 35 | 0 | 108.09 | 162.13 | 3783.15 | 6200
2024-09-01 | E1068 | HIMARS | Engineering | Analyst | 40 | 41 | 1 | 98.27 | 147.41 | 4078.21 | 6100
2024-09-01 | E1084 | HIMARS | Test | Engineer | 35 | 37 | 0 | 111.78 | 167.67 | 4135.86 | 6200
2024-09-01 | E1076 | Javelin | Test | Engineer | 35 | 34 | 0 | 53.3 | 79.95 | 1812.2 | 6100
2024-09-01 | E1113 | PAC-3 | Test | Technician | 32 | 31 | 0 | 117.2 | 175.8 | 3633.2 | 6100
2024-09-01 | E1007 | Javelin | Engineering | Engineer | 31 | 34 | 0 | 93.77 | 140.66 | 3188.18 | 6200
2024-09-01 | E1108 | THAAD | Program Control | Analyst | 33 | 32 | 0 | 66.45 | 99.68 | 2126.4 | 6100
2024-09-01 | E1046 | PAC-3 | Test | Technician | 41 | 38 | 0 | 67.76 | 101.64 | 2574.88 | 6200
2024-09-01 | E1064 | THAAD | Test | Assembler | 41 | 45 | 5 | 57.12 | 85.68 | 2713.2 | 6200
2024-09-01 | E1106 | HIMARS | Test | Technician | 38 | 41 | 1 | 52.81 | 79.22 | 2191.62 | 6100
2024-09-01 | E1026 | THAAD | Engineering | Analyst | 31 | 27 | 0 | 65.8 | 98.7 | 1776.6 | 6200
2024-09-01 | E1116 | HIMARS | Manufacturing | Technician | 41 | 44 | 4 | 40.94 | 61.41 | 1883.24 | 6200
2024-09-01 | E1029 | Javelin | Manufacturing | Assembler | 36 | 41 | 1 | 61.69 | 92.53 | 2560.13 | 6100
2024-09-08 | E1070 | HIMARS | Engineering | Engineer | 30 | 35 | 0 | 105.85 | 158.77 | 3704.75 | 6100
2024-09-08 | E1107 | PAC-3 | Engineering | Engineer | 39 | 43 | 3 | 68.83 | 103.25 | 3062.95 | 6200
2024-09-08 | E1091 | PAC-3 | Manufacturing | Assembler | 34 | 38 | 0 | 47.09 | 70.64 | 1789.42 | 6100
2024-09-08 | E1027 | Javelin | Test | Analyst | 30 | 34 | 0 | 88.3 | 132.45 | 3002.2 | 6200
2024-09-08 | E1091 | HIMARS | Manufacturing | Technician | 44 | 45 | 5 | 114.04 | 171.06 | 5416.9 | 6200
2024-09-08 | E1024 | THAAD | Engineering | Engineer | 37 | 36 | 0 | 53.12 | 79.68 | 1912.32 | 6200
2024-09-08 | E1029 | Javelin | Manufacturing | Assembler | 40 | 40 | 0 | 110.65 | 165.98 | 4426 | 6100
2024-09-08 | E1011 | Javelin | Manufacturing | Engineer | 32 | 33 | 0 | 109.93 | 164.9 | 3627.69 | 6200
2024-09-08 | E1091 | Javelin | Manufacturing | Assembler | 44 | 49 | 9 | 105.65 | 158.48 | 5652.32 | 6100
2024-09-08 | E1029 | Javelin | Manufacturing | Technician | 42 | 45 | 5 | 112.64 | 168.96 | 5350.4 | 6200
2024-09-08 | E1094 | PAC-3 | Engineering | Technician | 41 | 37 | 0 | 62.5 | 93.75 | 2312.5 | 6100
2024-09-08 | E1047 | THAAD | Engineering | Analyst | 37 | 42 | 2 | 74.17 | 111.25 | 3189.3 | 6200
2024-09-08 | E1107 | THAAD | Test | Engineer | 36 | 36 | 0 | 104.04 | 156.06 | 3745.44 | 6200
2024-09-08 | E1077 | HIMARS | Engineering | Technician | 39 | 40 | 0 | 44.77 | 67.16 | 1790.8 | 6100
2024-09-08 | E1031 | THAAD | Test | Analyst | 34 | 30 | 0 | 96.97 | 145.45 | 2909.1 | 6200
2024-09-15 | E1012 | HIMARS | Manufacturing | Technician | 32 | 35 | 0 | 60 | 90 | 2100 | 6200
2024-09-15 | E1075 | HIMARS | Test | Technician | 43 | 43 | 3 | 99.16 | 148.74 | 4412.62 | 6100
2024-09-15 | E1093 | THAAD | Manufacturing | Analyst | 30 | 26 | 0 | 109.88 | 164.82 | 2856.88 | 6200
2024-09-15 | E1089 | HIMARS | Manufacturing | Assembler | 31 | 29 | 0 | 56.1 | 84.15 | 1626.9 | 6200
2024-09-15 | E1077 | HIMARS | Engineering | Analyst | 38 | 35 | 0 | 89.81 | 134.72 | 3143.35 | 6200
2024-09-15 | E1025 | HIMARS | Manufacturing | Technician | 33 | 34 | 0 | 110.41 | 165.62 | 3753.94 | 6200
2024-09-15 | E1018 | PAC-3 | Test | Analyst | 30 | 25 | 0 | 66.43 | 99.65 | 1660.75 | 6200
2024-09-15 | E1056 | HIMARS | Manufacturing | Analyst | 35 | 34 | 0 | 69.2 | 103.8 | 2352.8 | 6100
2024-09-15 | E1005 | THAAD | Test | Assembler | 41 | 38 | 0 | 87.32 | 130.98 | 3318.16 | 6100
2024-09-15 | E1013 | Javelin | Engineering | Analyst | 39 | 36 | 0 | 102.15 | 153.23 | 3677.4 | 6100
2024-09-15 | E1034 | HIMARS | Manufacturing | Analyst | 35 | 38 | 0 | 67.71 | 101.56 | 2572.98 | 6100
2024-09-15 | E1034 | HIMARS | Manufacturing | Engineer | 34 | 33 | 0 | 109.47 | 164.2 | 3612.51 | 6200
2024-09-15 | E1118 | THAAD | Test | Engineer | 34 | 30 | 0 | 77.64 | 116.46 | 2329.2 | 6200
2024-09-15 | E1115 | Javelin | Manufacturing | Assembler | 38 | 41 | 1 | 91.82 | 137.73 | 3810.53 | 6200
2024-09-15 | E1119 | HIMARS | Program Control | Engineer | 35 | 38 | 0 | 52.71 | 79.06 | 2002.98 | 6100
2024-09-22 | E1112 | Javelin | Test | Assembler | 31 | 32 | 0 | 85.43 | 128.15 | 2733.76 | 6100
2024-09-22 | E1081 | HIMARS | Test | Engineer | 44 | 45 | 5 | 102.82 | 154.23 | 4883.95 | 6100
2024-09-22 | E1064 | HIMARS | Program Control | Analyst | 33 | 31 | 0 | 84.31 | 126.47 | 2613.61 | 6200
2024-09-22 | E1025 | PAC-3 | Test | Analyst | 40 | 40 | 0 | 54.99 | 82.48 | 2199.6 | 6200
2024-09-22 | E1034 | HIMARS | Manufacturing | Technician | 34 | 37 | 0 | 63.43 | 95.14 | 2346.91 | 6100
2024-09-22 | E1115 | PAC-3 | Test | Assembler | 31 | 29 | 0 | 107.02 | 160.53 | 3103.58 | 6200
2024-09-22 | E1044 | HIMARS | Engineering | Technician | 40 | 36 | 0 | 92.8 | 139.2 | 3340.8 | 6200
2024-09-22 | E1023 | PAC-3 | Test | Technician | 40 | 38 | 0 | 67.55 | 101.32 | 2566.9 | 6200
2024-09-22 | E1101 | PAC-3 | Program Control | Technician | 31 | 33 | 0 | 61.33 | 92 | 2023.89 | 6100
2024-09-22 | E1070 | PAC-3 | Engineering | Analyst | 43 | 46 | 6 | 43.86 | 65.79 | 2149.14 | 6200
2024-09-22 | E1017 | HIMARS | Test | Assembler | 42 | 43 | 3 | 112.23 | 168.34 | 4994.22 | 6200
2024-09-22 | E1073 | Javelin | Manufacturing | Engineer | 35 | 35 | 0 | 41.62 | 62.43 | 1456.7 | 6100
2024-09-22 | E1062 | THAAD | Engineering | Technician | 34 | 37 | 0 | 41.34 | 62.01 | 1529.58 | 6200
2024-09-22 | E1053 | PAC-3 | Test | Analyst | 44 | 46 | 6 | 68.84 | 103.26 | 3373.16 | 6100
2024-09-22 | E1018 | Javelin | Manufacturing | Technician | 43 | 45 | 5 | 94.61 | 141.91 | 4493.95 | 6200
2024-09-29 | E1050 | Javelin | Test | Technician | 30 | 30 | 0 | 44 | 66 | 1320 | 6100
2024-09-29 | E1047 | HIMARS | Engineering | Assembler | 30 | 27 | 0 | 60.19 | 90.28 | 1625.13 | 6100
2024-09-29 | E1042 | THAAD | Manufacturing | Engineer | 40 | 42 | 2 | 40.8 | 61.2 | 1754.4 | 6200
2024-09-29 | E1075 | Javelin | Engineering | Technician | 31 | 35 | 0 | 42.05 | 63.07 | 1471.75 | 6100
2024-09-29 | E1083 | HIMARS | Engineering | Assembler | 43 | 48 | 8 | 53.32 | 79.98 | 2772.64 | 6200
2024-09-29 | E1097 | THAAD | Manufacturing | Analyst | 36 | 41 | 1 | 103.18 | 154.77 | 4281.97 | 6200
2024-09-29 | E1114 | Javelin | Engineering | Engineer | 36 | 39 | 0 | 74.54 | 111.81 | 2907.06 | 6100
2024-09-29 | E1109 | PAC-3 | Engineering | Analyst | 44 | 46 | 6 | 60.25 | 90.38 | 2952.28 | 6100
2024-09-29 | E1025 | THAAD | Test | Engineer | 38 | 39 | 0 | 66.41 | 99.61 | 2589.99 | 6100
2024-09-29 | E1055 | THAAD | Program Control | Technician | 41 | 45 | 5 | 115.3 | 172.95 | 5476.75 | 6100
2024-09-29 | E1005 | PAC-3 | Manufacturing | Analyst | 40 | 39 | 0 | 73.02 | 109.53 | 2847.78 | 6200
2024-09-29 | E1098 | PAC-3 | Manufacturing | Analyst | 40 | 39 | 0 | 109.4 | 164.1 | 4266.6 | 6200
2024-09-29 | E1084 | HIMARS | Manufacturing | Analyst | 44 | 40 | 0 | 44.33 | 66.5 | 1773.2 | 6200
2024-09-29 | E1101 | HIMARS | Engineering | Engineer | 38 | 35 | 0 | 116.77 | 175.16 | 4086.95 | 6100
2024-09-29 | E1036 | HIMARS | Manufacturing | Analyst | 40 | 38 | 0 | 53.67 | 80.5 | 2039.46 | 6100
2024-10-06 | E1000 | Javelin | Test | Assembler | 44 | 43 | 3 | 109.23 | 163.84 | 4860.72 | 6200
2024-10-06 | E1082 | THAAD | Test | Assembler | 43 | 41 | 1 | 77.44 | 116.16 | 3213.76 | 6100
2024-10-06 | E1090 | PAC-3 | Test | Analyst | 41 | 42 | 2 | 48.39 | 72.59 | 2080.78 | 6200
2024-10-06 | E1032 | HIMARS | Test | Analyst | 31 | 29 | 0 | 40.71 | 61.06 | 1180.59 | 6100
2024-10-06 | E1057 | PAC-3 | Manufacturing | Technician | 42 | 45 | 5 | 96.41 | 144.62 | 4579.5 | 6100
2024-10-06 | E1062 | PAC-3 | Engineering | Analyst | 35 | 31 | 0 | 67.47 | 101.2 | 2091.57 | 6100
2024-10-06 | E1037 | Javelin | Program Control | Analyst | 34 | 36 | 0 | 112.08 | 168.12 | 4034.88 | 6200
2024-10-06 | E1091 | Javelin | Program Control | Analyst | 35 | 33 | 0 | 54.7 | 82.05 | 1805.1 | 6200
2024-10-06 | E1070 | HIMARS | Engineering | Technician | 30 | 28 | 0 | 82.38 | 123.57 | 2306.64 | 6200
2024-10-06 | E1043 | THAAD | Engineering | Technician | 32 | 33 | 0 | 78.55 | 117.82 | 2592.15 | 6200
2024-10-06 | E1050 | THAAD | Test | Technician | 38 | 41 | 1 | 108.78 | 163.17 | 4514.37 | 6100
2024-10-06 | E1085 | HIMARS | Manufacturing | Analyst | 33 | 29 | 0 | 44.54 | 66.81 | 1291.66 | 6200
2024-10-06 | E1044 | Javelin | Manufacturing | Engineer | 43 | 38 | 0 | 112.9 | 169.35 | 4290.2 | 6100
2024-10-06 | E1031 | Javelin | Test | Engineer | 44 | 44 | 4 | 99.87 | 149.81 | 4594.04 | 6200
2024-10-06 | E1054 | THAAD | Test | Assembler | 32 | 37 | 0 | 114.44 | 171.66 | 4234.28 | 6100
2024-10-13 | E1106 | HIMARS | Program Control | Engineer | 37 | 35 | 0 | 112.9 | 169.35 | 3951.5 | 6200
2024-10-13 | E1088 | PAC-3 | Program Control | Technician | 36 | 40 | 0 | 89.18 | 133.77 | 3567.2 | 6200
2024-10-13 | E1083 | PAC-3 | Test | Technician | 30 | 30 | 0 | 82.02 | 123.03 | 2460.6 | 6200
2024-10-13 | E1011 | Javelin | Program Control | Technician | 44 | 43 | 3 | 64.35 | 96.52 | 2863.56 | 6200
2024-10-13 | E1115 | HIMARS | Engineering | Engineer | 35 | 40 | 0 | 97.38 | 146.07 | 3895.2 | 6200
2024-10-13 | E1046 | PAC-3 | Engineering | Technician | 42 | 37 | 0 | 78.02 | 117.03 | 2886.74 | 6200
2024-10-13 | E1027 | Javelin | Manufacturing | Technician | 38 | 35 | 0 | 76.7 | 115.05 | 2684.5 | 6100
2024-10-13 | E1068 | PAC-3 | Manufacturing | Assembler | 40 | 44 | 4 | 107.55 | 161.32 | 4947.28 | 6100
2024-10-13 | E1100 | PAC-3 | Program Control | Analyst | 33 | 37 | 0 | 61.97 | 92.95 | 2292.89 | 6100
2024-10-13 | E1089 | Javelin | Manufacturing | Technician | 39 | 34 | 0 | 110.56 | 165.84 | 3759.04 | 6200
2024-10-13 | E1111 | THAAD | Test | Engineer | 36 | 40 | 0 | 59.62 | 89.43 | 2384.8 | 6100
2024-10-13 | E1085 | PAC-3 | Test | Analyst | 38 | 43 | 3 | 98.22 | 147.33 | 4370.79 | 6100
2024-10-13 | E1083 | PAC-3 | Test | Analyst | 36 | 33 | 0 | 96.42 | 144.63 | 3181.86 | 6200
2024-10-13 | E1038 | HIMARS | Test | Technician | 38 | 41 | 1 | 116.35 | 174.52 | 4828.52 | 6100
2024-10-13 | E1103 | Javelin | Engineering | Engineer | 35 | 31 | 0 | 76.47 | 114.7 | 2370.57 | 6100
2024-10-20 | E1044 | Javelin | Program Control | Analyst | 41 | 41 | 1 | 43.09 | 64.64 | 1788.24 | 6200
2024-10-20 | E1065 | PAC-3 | Manufacturing | Analyst | 36 | 35 | 0 | 104.76 | 157.14 | 3666.6 | 6200
2024-10-20 | E1095 | HIMARS | Test | Analyst | 43 | 46 | 6 | 50.64 | 75.96 | 2481.36 | 6200
2024-10-20 | E1049 | PAC-3 | Engineering | Engineer | 36 | 35 | 0 | 106.62 | 159.93 | 3731.7 | 6200
2024-10-20 | E1033 | PAC-3 | Engineering | Analyst | 37 | 33 | 0 | 84.4 | 126.6 | 2785.2 | 6100
2024-10-20 | E1104 | Javelin | Manufacturing | Technician | 38 | 42 | 2 | 59.41 | 89.11 | 2554.62 | 6200
2024-10-20 | E1077 | THAAD | Program Control | Analyst | 44 | 40 | 0 | 94.3 | 141.45 | 3772 | 6100
2024-10-20 | E1105 | THAAD | Program Control | Technician | 39 | 44 | 4 | 108.1 | 162.15 | 4972.6 | 6100
2024-10-20 | E1091 | PAC-3 | Program Control | Engineer | 44 | 39 | 0 | 90.72 | 136.08 | 3538.08 | 6100
2024-10-20 | E1015 | THAAD | Manufacturing | Analyst | 36 | 41 | 1 | 103.88 | 155.82 | 4311.02 | 6100
2024-10-20 | E1050 | THAAD | Program Control | Analyst | 40 | 38 | 0 | 57.98 | 86.97 | 2203.24 | 6100
2024-10-20 | E1012 | Javelin | Test | Analyst | 30 | 34 | 0 | 100.17 | 150.25 | 3405.78 | 6200
2024-10-20 | E1092 | HIMARS | Test | Technician | 41 | 42 | 2 | 53.98 | 80.97 | 2321.14 | 6100
2024-10-20 | E1085 | Javelin | Program Control | Technician | 39 | 37 | 0 | 92.11 | 138.16 | 3408.07 | 6100
2024-10-20 | E1016 | Javelin | Manufacturing | Engineer | 42 | 39 | 0 | 67.13 | 100.69 | 2618.07 | 6100
2024-10-27 | E1045 | HIMARS | Engineering | Engineer | 38 | 40 | 0 | 99.18 | 148.77 | 3967.2 | 6100
2024-10-27 | E1018 | HIMARS | Test | Engineer | 30 | 29 | 0 | 68.28 | 102.42 | 1980.12 | 6200
2024-10-27 | E1001 | PAC-3 | Program Control | Engineer | 35 | 34 | 0 | 74.7 | 112.05 | 2539.8 | 6200
2024-10-27 | E1098 | Javelin | Program Control | Technician | 44 | 42 | 2 | 103.53 | 155.3 | 4451.8 | 6200
2024-10-27 | E1045 | PAC-3 | Manufacturing | Analyst | 42 | 39 | 0 | 65.4 | 98.1 | 2550.6 | 6100
2024-10-27 | E1024 | Javelin | Manufacturing | Technician | 43 | 46 | 6 | 40.71 | 61.06 | 1994.76 | 6100
2024-10-27 | E1073 | Javelin | Engineering | Assembler | 38 | 37 | 0 | 96.58 | 144.87 | 3573.46 | 6100
2024-10-27 | E1116 | Javelin | Engineering | Technician | 43 | 43 | 3 | 67.9 | 101.85 | 3021.55 | 6200
2024-10-27 | E1004 | THAAD | Manufacturing | Technician | 34 | 34 | 0 | 82.05 | 123.07 | 2789.7 | 6100
2024-10-27 | E1009 | PAC-3 | Test | Assembler | 31 | 28 | 0 | 69.79 | 104.69 | 1954.12 | 6200
2024-10-27 | E1066 | Javelin | Program Control | Engineer | 40 | 44 | 4 | 68.51 | 102.77 | 3151.48 | 6100
2024-10-27 | E1021 | THAAD | Manufacturing | Assembler | 40 | 37 | 0 | 52.47 | 78.7 | 1941.39 | 6100
2024-10-27 | E1071 | HIMARS | Program Control | Technician | 31 | 29 | 0 | 44.42 | 66.63 | 1288.18 | 6200
2024-10-27 | E1019 | Javelin | Engineering | Analyst | 39 | 39 | 0 | 80.58 | 120.87 | 3142.62 | 6100
2024-10-27 | E1058 | THAAD | Engineering | Technician | 34 | 31 | 0 | 58.32 | 87.48 | 1807.92 | 6100
2024-11-03 | E1014 | PAC-3 | Engineering | Engineer | 31 | 34 | 0 | 86 | 129 | 2924 | 6200
2024-11-03 | E1005 | THAAD | Test | Analyst | 37 | 33 | 0 | 72.14 | 108.21 | 2380.62 | 6200
2024-11-03 | E1112 | PAC-3 | Engineering | Technician | 35 | 33 | 0 | 50.59 | 75.89 | 1669.47 | 6100
2024-11-03 | E1049 | Javelin | Manufacturing | Assembler | 43 | 39 | 0 | 79.46 | 119.19 | 3098.94 | 6200
2024-11-03 | E1004 | PAC-3 | Program Control | Engineer | 42 | 47 | 7 | 48.37 | 72.55 | 2442.65 | 6200
2024-11-03 | E1095 | HIMARS | Test | Assembler | 35 | 31 | 0 | 76.83 | 115.25 | 2381.73 | 6200
2024-11-03 | E1088 | HIMARS | Engineering | Technician | 41 | 44 | 4 | 55.7 | 83.55 | 2562.2 | 6200
2024-11-03 | E1044 | HIMARS | Manufacturing | Analyst | 31 | 35 | 0 | 98.16 | 147.24 | 3435.6 | 6100
2024-11-03 | E1080 | PAC-3 | Program Control | Technician | 39 | 38 | 0 | 64.33 | 96.5 | 2444.54 | 6100
2024-11-03 | E1108 | HIMARS | Test | Technician | 43 | 41 | 1 | 46.51 | 69.77 | 1930.17 | 6200
2024-11-03 | E1092 | PAC-3 | Program Control | Technician | 33 | 35 | 0 | 87.44 | 131.16 | 3060.4 | 6100
2024-11-03 | E1018 | HIMARS | Program Control | Engineer | 31 | 35 | 0 | 108.44 | 162.66 | 3795.4 | 6200
2024-11-03 | E1097 | Javelin | Test | Technician | 37 | 32 | 0 | 64.22 | 96.33 | 2055.04 | 6200
2024-11-03 | E1081 | PAC-3 | Test | Engineer | 32 | 34 | 0 | 93.44 | 140.16 | 3176.96 | 6200
2024-11-03 | E1086 | HIMARS | Program Control | Analyst | 35 | 33 | 0 | 72.94 | 109.41 | 2407.02 | 6200
2024-11-10 | E1086 | HIMARS | Engineering | Engineer | 42 | 47 | 7 | 54.4 | 81.6 | 2747.2 | 6100
2024-11-10 | E1013 | HIMARS | Program Control | Engineer | 44 | 40 | 0 | 89.6 | 134.4 | 3584 | 6200
2024-11-10 | E1081 | Javelin | Test | Analyst | 31 | 27 | 0 | 87.59 | 131.38 | 2364.93 | 6200
2024-11-10 | E1030 | HIMARS | Program Control | Engineer | 33 | 28 | 0 | 48.54 | 72.81 | 1359.12 | 6100
2024-11-10 | E1105 | THAAD | Manufacturing | Assembler | 32 | 30 | 0 | 109.09 | 163.63 | 3272.7 | 6100
2024-11-10 | E1066 | HIMARS | Program Control | Assembler | 42 | 43 | 3 | 44.49 | 66.73 | 1979.79 | 6200
2024-11-10 | E1091 | HIMARS | Manufacturing | Analyst | 42 | 46 | 6 | 59.42 | 89.13 | 2911.58 | 6100
2024-11-10 | E1074 | PAC-3 | Manufacturing | Assembler | 30 | 26 | 0 | 94.41 | 141.62 | 2454.66 | 6200
2024-11-10 | E1034 | Javelin | Test | Assembler | 40 | 43 | 3 | 54.97 | 82.45 | 2446.15 | 6100
2024-11-10 | E1074 | PAC-3 | Program Control | Engineer | 40 | 39 | 0 | 96.19 | 144.28 | 3751.41 | 6200
2024-11-10 | E1033 | HIMARS | Manufacturing | Technician | 42 | 39 | 0 | 99.53 | 149.3 | 3881.67 | 6200
2024-11-10 | E1074 | Javelin | Manufacturing | Analyst | 39 | 35 | 0 | 86.15 | 129.23 | 3015.25 | 6100
2024-11-10 | E1027 | Javelin | Manufacturing | Assembler | 30 | 30 | 0 | 72.92 | 109.38 | 2187.6 | 6100
2024-11-10 | E1087 | HIMARS | Program Control | Technician | 37 | 41 | 1 | 115 | 172.5 | 4772.5 | 6200
2024-11-10 | E1035 | HIMARS | Manufacturing | Technician | 33 | 33 | 0 | 100.7 | 151.05 | 3323.1 | 6100
2024-11-17 | E1063 | HIMARS | Engineering | Technician | 43 | 45 | 5 | 112.49 | 168.73 | 5343.25 | 6100
2024-11-17 | E1026 | Javelin | Engineering | Engineer | 34 | 34 | 0 | 92.84 | 139.26 | 3156.56 | 6100
2024-11-17 | E1007 | THAAD | Test | Analyst | 38 | 41 | 1 | 106.86 | 160.29 | 4434.69 | 6200
2024-11-17 | E1110 | PAC-3 | Test | Engineer | 32 | 33 | 0 | 85.13 | 127.69 | 2809.29 | 6100
2024-11-17 | E1056 | HIMARS | Engineering | Technician | 32 | 37 | 0 | 115.89 | 173.84 | 4287.93 | 6100
2024-11-17 | E1086 | PAC-3 | Manufacturing | Assembler | 31 | 34 | 0 | 47.37 | 71.05 | 1610.58 | 6200
2024-11-17 | E1092 | Javelin | Manufacturing | Engineer | 44 | 45 | 5 | 110 | 165 | 5225 | 6100
2024-11-17 | E1115 | THAAD | Program Control | Analyst | 39 | 40 | 0 | 96.22 | 144.33 | 3848.8 | 6100
2024-11-17 | E1003 | HIMARS | Engineering | Analyst | 32 | 31 | 0 | 42.72 | 64.08 | 1324.32 | 6200
2024-11-17 | E1064 | PAC-3 | Engineering | Engineer | 35 | 36 | 0 | 41.24 | 61.86 | 1484.64 | 6100
2024-11-17 | E1064 | PAC-3 | Test | Engineer | 39 | 39 | 0 | 47.53 | 71.3 | 1853.67 | 6200
2024-11-17 | E1085 | Javelin | Program Control | Analyst | 33 | 38 | 0 | 117.47 | 176.2 | 4463.86 | 6200
2024-11-17 | E1051 | HIMARS | Test | Engineer | 37 | 40 | 0 | 69.47 | 104.2 | 2778.8 | 6100
2024-11-17 | E1107 | THAAD | Engineering | Technician | 44 | 46 | 6 | 101.4 | 152.1 | 4968.6 | 6100
2024-11-17 | E1092 | HIMARS | Engineering | Engineer | 31 | 35 | 0 | 67.71 | 101.56 | 2369.85 | 6200
2024-11-24 | E1096 | PAC-3 | Program Control | Engineer | 31 | 33 | 0 | 48.65 | 72.97 | 1605.45 | 6100
2024-11-24 | E1080 | HIMARS | Manufacturing | Engineer | 35 | 34 | 0 | 92.1 | 138.15 | 3131.4 | 6200
2024-11-24 | E1024 | THAAD | Engineering | Assembler | 35 | 31 | 0 | 82.59 | 123.89 | 2560.29 | 6200
2024-11-24 | E1020 | HIMARS | Program Control | Assembler | 31 | 35 | 0 | 75.5 | 113.25 | 2642.5 | 6100
2024-11-24 | E1019 | Javelin | Program Control | Assembler | 38 | 39 | 0 | 50.51 | 75.77 | 1969.89 | 6100
2024-11-24 | E1062 | HIMARS | Test | Engineer | 44 | 46 | 6 | 89.44 | 134.16 | 4382.56 | 6100
2024-11-24 | E1117 | HIMARS | Engineering | Analyst | 32 | 28 | 0 | 48.42 | 72.63 | 1355.76 | 6100
2024-11-24 | E1103 | THAAD | Engineering | Assembler | 38 | 35 | 0 | 82.93 | 124.4 | 2902.55 | 6200
2024-11-24 | E1115 | Javelin | Program Control | Engineer | 43 | 40 | 0 | 119.15 | 178.73 | 4766 | 6200
2024-11-24 | E1015 | HIMARS | Program Control | Technician | 36 | 39 | 0 | 117.55 | 176.32 | 4584.45 | 6100
2024-11-24 | E1078 | THAAD | Test | Assembler | 32 | 36 | 0 | 111.82 | 167.73 | 4025.52 | 6200
2024-11-24 | E1079 | PAC-3 | Manufacturing | Engineer | 33 | 30 | 0 | 74.69 | 112.03 | 2240.7 | 6100
2024-11-24 | E1043 | THAAD | Program Control | Analyst | 38 | 37 | 0 | 49.19 | 73.78 | 1820.03 | 6100
2024-11-24 | E1110 | HIMARS | Test | Engineer | 41 | 38 | 0 | 41.45 | 62.18 | 1575.1 | 6200
2024-11-24 | E1116 | Javelin | Engineering | Engineer | 41 | 45 | 5 | 80.67 | 121 | 3831.8 | 6100
2024-12-01 | E1085 | Javelin | Program Control | Assembler | 32 | 36 | 0 | 94.31 | 141.47 | 3395.16 | 6200
2024-12-01 | E1062 | HIMARS | Engineering | Technician | 39 | 43 | 3 | 95.05 | 142.57 | 4229.71 | 6200
2024-12-01 | E1086 | Javelin | Manufacturing | Assembler | 41 | 36 | 0 | 56.36 | 84.54 | 2028.96 | 6200
2024-12-01 | E1036 | PAC-3 | Program Control | Engineer | 31 | 34 | 0 | 67.74 | 101.61 | 2303.16 | 6200
2024-12-01 | E1030 | PAC-3 | Engineering | Engineer | 33 | 38 | 0 | 69.43 | 104.15 | 2638.34 | 6200
2024-12-01 | E1018 | HIMARS | Program Control | Assembler | 34 | 39 | 0 | 100.55 | 150.82 | 3921.45 | 6200
2024-12-01 | E1044 | HIMARS | Engineering | Analyst | 36 | 33 | 0 | 100.94 | 151.41 | 3331.02 | 6200
2024-12-01 | E1101 | Javelin | Manufacturing | Assembler | 30 | 29 | 0 | 45.19 | 67.78 | 1310.51 | 6100
2024-12-01 | E1057 | PAC-3 | Engineering | Analyst | 36 | 37 | 0 | 67.1 | 100.65 | 2482.7 | 6200
2024-12-01 | E1105 | Javelin | Program Control | Engineer | 44 | 49 | 9 | 118.16 | 177.24 | 6321.56 | 6100
2024-12-01 | E1072 | PAC-3 | Manufacturing | Assembler | 44 | 47 | 7 | 90.71 | 136.06 | 4580.82 | 6100
2024-12-01 | E1117 | Javelin | Program Control | Analyst | 37 | 34 | 0 | 47.25 | 70.88 | 1606.5 | 6200
2024-12-01 | E1057 | Javelin | Test | Engineer | 39 | 43 | 3 | 106.75 | 160.12 | 4750.36 | 6100
2024-12-01 | E1047 | HIMARS | Engineering | Analyst | 30 | 30 | 0 | 85.52 | 128.28 | 2565.6 | 6100
2024-12-01 | E1074 | THAAD | Manufacturing | Analyst | 44 | 40 | 0 | 58.17 | 87.25 | 2326.8 | 6100
2024-12-08 | E1004 | Javelin | Engineering | Technician | 31 | 30 | 0 | 113.24 | 169.86 | 3397.2 | 6100
2024-12-08 | E1055 | THAAD | Engineering | Assembler | 41 | 41 | 1 | 51.32 | 76.98 | 2129.78 | 6200
2024-12-08 | E1081 | Javelin | Test | Engineer | 36 | 41 | 1 | 44.55 | 66.82 | 1848.82 | 6200
2024-12-08 | E1020 | Javelin | Program Control | Technician | 44 | 41 | 1 | 45.25 | 67.88 | 1877.88 | 6200
2024-12-08 | E1089 | PAC-3 | Manufacturing | Analyst | 37 | 38 | 0 | 73.89 | 110.84 | 2807.82 | 6100
2024-12-08 | E1071 | PAC-3 | Manufacturing | Engineer | 36 | 40 | 0 | 63.87 | 95.8 | 2554.8 | 6100
2024-12-08 | E1102 | THAAD | Test | Engineer | 32 | 29 | 0 | 80.82 | 121.23 | 2343.78 | 6100
2024-12-08 | E1010 | Javelin | Manufacturing | Analyst | 32 | 32 | 0 | 58.48 | 87.72 | 1871.36 | 6100
2024-12-08 | E1008 | HIMARS | Program Control | Assembler | 41 | 46 | 6 | 58.25 | 87.38 | 2854.28 | 6200
2024-12-08 | E1042 | THAAD | Engineering | Assembler | 43 | 43 | 3 | 87.65 | 131.48 | 3900.44 | 6100
2024-12-08 | E1110 | THAAD | Engineering | Engineer | 37 | 38 | 0 | 66.28 | 99.42 | 2518.64 | 6200
2024-12-08 | E1020 | THAAD | Engineering | Analyst | 40 | 43 | 3 | 71.99 | 107.98 | 3203.54 | 6200
2024-12-08 | E1114 | HIMARS | Engineering | Assembler | 41 | 46 | 6 | 75.07 | 112.6 | 3678.4 | 6100
2024-12-08 | E1035 | PAC-3 | Program Control | Assembler | 42 | 41 | 1 | 114.61 | 171.91 | 4756.31 | 6200
2024-12-08 | E1038 | PAC-3 | Engineering | Technician | 41 | 42 | 2 | 49.1 | 73.65 | 2111.3 | 6100
2024-12-15 | E1026 | THAAD | Engineering | Assembler | 32 | 29 | 0 | 101.24 | 151.86 | 2935.96 | 6200
2024-12-15 | E1109 | Javelin | Test | Technician | 33 | 33 | 0 | 90.7 | 136.05 | 2993.1 | 6200
2024-12-15 | E1025 | Javelin | Test | Analyst | 31 | 27 | 0 | 75.23 | 112.84 | 2031.21 | 6200
2024-12-15 | E1114 | Javelin | Engineering | Engineer | 31 | 33 | 0 | 57.92 | 86.88 | 1911.36 | 6200
2024-12-15 | E1022 | THAAD | Program Control | Assembler | 38 | 41 | 1 | 50.55 | 75.82 | 2097.82 | 6100
2024-12-15 | E1053 | THAAD | Manufacturing | Analyst | 43 | 41 | 1 | 83.88 | 125.82 | 3481.02 | 6200
2024-12-15 | E1114 | HIMARS | Manufacturing | Analyst | 38 | 42 | 2 | 115.6 | 173.4 | 4970.8 | 6200
2024-12-15 | E1062 | Javelin | Engineering | Assembler | 37 | 36 | 0 | 77.19 | 115.78 | 2778.84 | 6200
2024-12-15 | E1026 | HIMARS | Engineering | Technician | 32 | 27 | 0 | 93.15 | 139.73 | 2515.05 | 6100
2024-12-15 | E1052 | PAC-3 | Engineering | Analyst | 31 | 26 | 0 | 86.33 | 129.5 | 2244.58 | 6100
2024-12-15 | E1063 | THAAD | Engineering | Engineer | 31 | 27 | 0 | 90.85 | 136.27 | 2452.95 | 6100
2024-12-15 | E1002 | THAAD | Manufacturing | Technician | 43 | 43 | 3 | 106.72 | 160.08 | 4749.04 | 6200
2024-12-15 | E1111 | THAAD | Program Control | Engineer | 30 | 25 | 0 | 80.23 | 120.34 | 2005.75 | 6200
2024-12-15 | E1007 | Javelin | Test | Technician | 44 | 49 | 9 | 72.28 | 108.42 | 3866.98 | 6200
2024-12-15 | E1009 | HIMARS | Program Control | Technician | 41 | 46 | 6 | 69.05 | 103.57 | 3383.42 | 6100
2024-12-22 | E1026 | PAC-3 | Program Control | Technician | 38 | 37 | 0 | 87.73 | 131.59 | 3246.01 | 6100
2024-12-22 | E1064 | Javelin | Engineering | Analyst | 44 | 41 | 1 | 92.29 | 138.44 | 3830.04 | 6200
2024-12-22 | E1059 | PAC-3 | Test | Assembler | 44 | 45 | 5 | 100.09 | 150.13 | 4754.25 | 6200
2024-12-22 | E1057 | PAC-3 | Manufacturing | Technician | 33 | 38 | 0 | 69.74 | 104.61 | 2650.12 | 6100
2024-12-22 | E1098 | PAC-3 | Manufacturing | Engineer | 43 | 38 | 0 | 67.96 | 101.94 | 2582.48 | 6200
2024-12-22 | E1007 | Javelin | Program Control | Technician | 39 | 43 | 3 | 74.74 | 112.11 | 3325.93 | 6200
2024-12-22 | E1011 | HIMARS | Engineering | Technician | 43 | 40 | 0 | 77.36 | 116.04 | 3094.4 | 6200
2024-12-22 | E1081 | HIMARS | Manufacturing | Technician | 40 | 35 | 0 | 70.45 | 105.68 | 2465.75 | 6200
2024-12-22 | E1082 | Javelin | Engineering | Engineer | 37 | 35 | 0 | 87.85 | 131.77 | 3074.75 | 6200
2024-12-22 | E1030 | PAC-3 | Test | Technician | 32 | 31 | 0 | 53.58 | 80.37 | 1660.98 | 6100
2024-12-22 | E1108 | THAAD | Manufacturing | Technician | 36 | 34 | 0 | 50.14 | 75.21 | 1704.76 | 6200
2024-12-22 | E1002 | PAC-3 | Program Control | Engineer | 42 | 44 | 4 | 51.78 | 77.67 | 2381.88 | 6200
2024-12-22 | E1071 | Javelin | Engineering | Technician | 40 | 38 | 0 | 107.81 | 161.72 | 4096.78 | 6200
2024-12-22 | E1004 | PAC-3 | Manufacturing | Engineer | 36 | 39 | 0 | 71.89 | 107.84 | 2803.71 | 6200
2024-12-22 | E1025 | HIMARS | Manufacturing | Analyst | 43 | 46 | 6 | 94.04 | 141.06 | 4607.96 | 6100
2024-12-29 | E1023 | PAC-3 | Test | Engineer | 40 | 37 | 0 | 100.63 | 150.94 | 3723.31 | 6100
2024-12-29 | E1002 | PAC-3 | Engineering | Technician | 30 | 35 | 0 | 82.41 | 123.61 | 2884.35 | 6200
2024-12-29 | E1028 | PAC-3 | Program Control | Engineer | 42 | 40 | 0 | 94.74 | 142.11 | 3789.6 | 6100
2024-12-29 | E1100 | Javelin | Program Control | Analyst | 33 | 36 | 0 | 118.35 | 177.52 | 4260.6 | 6200
2024-12-29 | E1112 | THAAD | Engineering | Technician | 44 | 40 | 0 | 66.58 | 99.87 | 2663.2 | 6200
2024-12-29 | E1036 | HIMARS | Test | Technician | 32 | 31 | 0 | 57.91 | 86.86 | 1795.21 | 6100
2024-12-29 | E1080 | Javelin | Program Control | Analyst | 32 | 33 | 0 | 73.17 | 109.75 | 2414.61 | 6100
2024-12-29 | E1078 | THAAD | Manufacturing | Engineer | 39 | 40 | 0 | 42 | 63 | 1680 | 6100
2024-12-29 | E1115 | HIMARS | Manufacturing | Analyst | 33 | 29 | 0 | 84.88 | 127.32 | 2461.52 | 6100
2024-12-29 | E1115 | PAC-3 | Program Control | Analyst | 38 | 41 | 1 | 62.35 | 93.53 | 2587.53 | 6100
2024-12-29 | E1016 | THAAD | Test | Engineer | 36 | 40 | 0 | 56.99 | 85.48 | 2279.6 | 6200
2024-12-29 | E1074 | Javelin | Program Control | Assembler | 41 | 44 | 4 | 74.65 | 111.98 | 3433.92 | 6100
2024-12-29 | E1041 | HIMARS | Program Control | Engineer | 30 | 31 | 0 | 102.68 | 154.02 | 3183.08 | 6100
2024-12-29 | E1080 | PAC-3 | Program Control | Analyst | 44 | 43 | 3 | 86.14 | 129.21 | 3833.23 | 6100
2024-12-29 | E1003 | PAC-3 | Manufacturing | Analyst | 40 | 44 | 4 | 85.89 | 128.84 | 3950.96 | 6200

## GL_Transactions
Trans_ID | Trans_Date | Program | GL_Account | Debit | Credit | Description | Source
T200001 | 2024-11-04 | THAAD | 5100 | 0 | 106847.38 | AP posting for THAAD | AP
T200002 | 2024-08-20 | Javelin | 7200 | 18068.34 | 0 | Inventory posting for Javelin | Inventory
T200003 | 2024-10-04 | Javelin | 7100 | 0 | 80546.99 | Inventory posting for Javelin | Inventory
T200004 | 2024-05-22 | HIMARS | 7200 | 92040.47 | 0 | Inventory posting for HIMARS | Inventory
T200005 | 2024-06-09 | Javelin | 6100 | 0 | 128182.01 | Payroll posting for Javelin | Payroll
T200006 | 2024-01-02 | PAC-3 | 6200 | 93555.52 | 0 | Payroll posting for PAC-3 | Payroll
T200007 | 2024-11-18 | Javelin | 7100 | 0 | 39559.65 | Journal posting for Javelin | Journal
T200008 | 2024-08-15 | THAAD | 6100 | 0 | 129273.2 | Journal posting for THAAD | Journal
T200009 | 2024-07-11 | Javelin | 6200 | 87485.09 | 0 | Payroll posting for Javelin | Payroll
T200010 | 2024-01-15 | HIMARS | 5100 | 54016.35 | 0 | Inventory posting for HIMARS | Inventory
T200011 | 2024-01-08 | Javelin | 5200 | 90775.68 | 0 | AP posting for Javelin | AP
T200012 | 2024-09-16 | Javelin | 5200 | 0 | 138962.85 | Inventory posting for Javelin | Inventory
T200013 | 2024-01-26 | PAC-3 | 5400 | 29982.25 | 0 | AP posting for PAC-3 | AP
T200014 | 2024-05-08 | HIMARS | 5200 | 155136.14 | 0 | Inventory posting for HIMARS | Inventory
T200015 | 2024-09-18 | HIMARS | 6100 | 0 | 143746.35 | Payroll posting for HIMARS | Payroll
T200016 | 2024-02-14 | THAAD | 7200 | 0 | 191459.79 | Inventory posting for THAAD | Inventory
T200017 | 2024-06-26 | THAAD | 6100 | 125135.86 | 0 | Journal posting for THAAD | Journal
T200018 | 2024-07-03 | THAAD | 5300 | 35095.79 | 0 | AP posting for THAAD | AP
T200019 | 2024-09-16 | Javelin | 6100 | 0 | 89208.24 | Journal posting for Javelin | Journal
T200020 | 2024-09-27 | PAC-3 | 6100 | 0 | 203053.7 | Journal posting for PAC-3 | Journal
T200021 | 2024-09-04 | THAAD | 7100 | 0 | 14010.56 | Journal posting for THAAD | Journal
T200022 | 2024-02-21 | Javelin | 6200 | 0 | 126403.53 | Payroll posting for Javelin | Payroll
T200023 | 2024-06-15 | Javelin | 6100 | 0 | 161690.69 | Journal posting for Javelin | Journal
T200024 | 2024-05-21 | HIMARS | 6100 | 0 | 197188.18 | Journal posting for HIMARS | Journal
T200025 | 2024-11-04 | THAAD | 7200 | 87359.12 | 0 | AP posting for THAAD | AP
T200026 | 2024-07-10 | HIMARS | 5300 | 131170.05 | 0 | Inventory posting for HIMARS | Inventory
T200027 | 2024-11-21 | PAC-3 | 6100 | 0 | 99335.1 | Journal posting for PAC-3 | Journal
T200028 | 2024-06-10 | PAC-3 | 6100 | 0 | 223359.35 | Journal posting for PAC-3 | Journal
T200029 | 2024-03-26 | PAC-3 | 5300 | 0 | 26494.81 | Journal posting for PAC-3 | Journal
T200030 | 2024-07-08 | HIMARS | 5300 | 0 | 58278.21 | AP posting for HIMARS | AP
T200031 | 2024-03-27 | Javelin | 5100 | 72143.28 | 0 | Inventory posting for Javelin | Inventory
T200032 | 2024-02-15 | PAC-3 | 5200 | 191336.74 | 0 | AP posting for PAC-3 | AP
T200033 | 2024-01-16 | HIMARS | 6200 | 0 | 228134.19 | Payroll posting for HIMARS | Payroll
T200034 | 2024-07-16 | PAC-3 | 7200 | 0 | 98371.78 | AP posting for PAC-3 | AP
T200035 | 2024-02-14 | Javelin | 6100 | 0 | 35064.06 | Payroll posting for Javelin | Payroll
T200036 | 2024-07-02 | HIMARS | 5300 | 222213.72 | 0 | Journal posting for HIMARS | Journal
T200037 | 2024-12-24 | PAC-3 | 6200 | 171198.22 | 0 | Payroll posting for PAC-3 | Payroll
T200038 | 2024-11-25 | THAAD | 6200 | 0 | 127729.98 | Journal posting for THAAD | Journal
T200039 | 2024-02-19 | THAAD | 5100 | 249693.76 | 0 | AP posting for THAAD | AP
T200040 | 2024-11-11 | PAC-3 | 7100 | 0 | 223492.2 | Inventory posting for PAC-3 | Inventory
T200041 | 2024-10-27 | Javelin | 5200 | 0 | 79825.58 | Inventory posting for Javelin | Inventory
T200042 | 2024-11-02 | THAAD | 6100 | 0 | 11978.53 | Journal posting for THAAD | Journal
T200043 | 2024-09-13 | PAC-3 | 5100 | 102214.26 | 0 | AP posting for PAC-3 | AP
T200044 | 2024-07-05 | Javelin | 5300 | 135854.91 | 0 | AP posting for Javelin | AP
T200045 | 2024-12-16 | Javelin | 7200 | 0 | 71438.56 | AP posting for Javelin | AP
T200046 | 2024-12-23 | THAAD | 6200 | 183670.27 | 0 | Payroll posting for THAAD | Payroll
T200047 | 2024-11-08 | HIMARS | 7100 | 0 | 194177.36 | AP posting for HIMARS | AP
T200048 | 2024-12-24 | THAAD | 5300 | 0 | 232157.84 | AP posting for THAAD | AP
T200049 | 2024-12-06 | Javelin | 5300 | 126399.75 | 0 | Inventory posting for Javelin | Inventory
T200050 | 2024-03-27 | PAC-3 | 6200 | 0 | 160829.89 | Journal posting for PAC-3 | Journal
T200051 | 2024-11-07 | Javelin | 5100 | 0 | 151758.1 | Journal posting for Javelin | Journal
T200052 | 2024-06-04 | THAAD | 6200 | 105166.7 | 0 | Payroll posting for THAAD | Payroll
T200053 | 2024-02-24 | THAAD | 6200 | 0 | 132060.68 | Payroll posting for THAAD | Payroll
T200054 | 2024-10-08 | HIMARS | 6100 | 191394.65 | 0 | Payroll posting for HIMARS | Payroll
T200055 | 2024-09-30 | HIMARS | 7100 | 0 | 52169.83 | AP posting for HIMARS | AP
T200056 | 2024-05-08 | Javelin | 6100 | 178985.53 | 0 | Payroll posting for Javelin | Payroll
T200057 | 2024-07-31 | THAAD | 5200 | 0 | 115091.07 | AP posting for THAAD | AP
T200058 | 2024-04-25 | Javelin | 5100 | 179943.31 | 0 | AP posting for Javelin | AP
T200059 | 2024-07-29 | PAC-3 | 5100 | 0 | 81073.17 | AP posting for PAC-3 | AP
T200060 | 2024-12-02 | HIMARS | 7200 | 223672.88 | 0 | AP posting for HIMARS | AP
T200061 | 2024-10-31 | PAC-3 | 5400 | 0 | 215208.83 | Inventory posting for PAC-3 | Inventory
T200062 | 2024-12-18 | THAAD | 5100 | 0 | 129434.08 | Journal posting for THAAD | Journal
T200063 | 2024-06-23 | PAC-3 | 6200 | 0 | 129765.09 | Payroll posting for PAC-3 | Payroll
T200064 | 2024-12-28 | Javelin | 5300 | 65929.49 | 0 | AP posting for Javelin | AP
T200065 | 2024-05-24 | HIMARS | 6200 | 0 | 223792.34 | Payroll posting for HIMARS | Payroll
T200066 | 2024-11-20 | PAC-3 | 5200 | 63674.74 | 0 | Inventory posting for PAC-3 | Inventory
T200067 | 2024-08-26 | HIMARS | 6200 | 0 | 36218.09 | Payroll posting for HIMARS | Payroll
T200068 | 2024-08-01 | Javelin | 7200 | 0 | 79787.14 | Inventory posting for Javelin | Inventory
T200069 | 2024-04-01 | HIMARS | 5100 | 0 | 28197.92 | Inventory posting for HIMARS | Inventory
T200070 | 2024-06-24 | HIMARS | 7200 | 0 | 162184.72 | Inventory posting for HIMARS | Inventory
T200071 | 2024-12-21 | THAAD | 6100 | 49808.97 | 0 | Payroll posting for THAAD | Payroll
T200072 | 2024-01-11 | HIMARS | 6200 | 37482.63 | 0 | Payroll posting for HIMARS | Payroll
T200073 | 2024-08-07 | THAAD | 6200 | 0 | 96498.73 | Payroll posting for THAAD | Payroll
T200074 | 2024-03-03 | HIMARS | 5300 | 0 | 44294.11 | AP posting for HIMARS | AP
T200075 | 2024-03-10 | PAC-3 | 7100 | 235511.57 | 0 | Journal posting for PAC-3 | Journal
T200076 | 2024-06-28 | HIMARS | 5200 | 59388.79 | 0 | Inventory posting for HIMARS | Inventory
T200077 | 2024-04-09 | PAC-3 | 5400 | 165897.06 | 0 | AP posting for PAC-3 | AP
T200078 | 2024-07-01 | PAC-3 | 7100 | 76167.99 | 0 | AP posting for PAC-3 | AP
T200079 | 2024-08-25 | PAC-3 | 6200 | 15326.85 | 0 | Journal posting for PAC-3 | Journal
T200080 | 2024-04-15 | Javelin | 6200 | 0 | 210577.42 | Payroll posting for Javelin | Payroll
T200081 | 2024-01-07 | PAC-3 | 5100 | 211694.8 | 0 | AP posting for PAC-3 | AP
T200082 | 2024-09-20 | HIMARS | 6200 | 111499.15 | 0 | Payroll posting for HIMARS | Payroll
T200083 | 2024-06-24 | THAAD | 7200 | 158384.59 | 0 | Journal posting for THAAD | Journal
T200084 | 2024-04-30 | Javelin | 7200 | 0 | 75544.75 | Journal posting for Javelin | Journal
T200085 | 2024-10-27 | HIMARS | 6200 | 143050.27 | 0 | Payroll posting for HIMARS | Payroll
T200086 | 2024-09-26 | HIMARS | 5300 | 0 | 199093.17 | Inventory posting for HIMARS | Inventory
T200087 | 2024-09-13 | THAAD | 5200 | 0 | 203230.29 | AP posting for THAAD | AP
T200088 | 2024-11-07 | HIMARS | 5300 | 24913.38 | 0 | Inventory posting for HIMARS | Inventory
T200089 | 2024-01-30 | Javelin | 6200 | 116330.39 | 0 | Payroll posting for Javelin | Payroll
T200090 | 2024-10-07 | Javelin | 5400 | 0 | 42868.18 | Journal posting for Javelin | Journal
T200091 | 2024-12-02 | HIMARS | 6100 | 0 | 34342.9 | Payroll posting for HIMARS | Payroll
T200092 | 2024-07-23 | HIMARS | 7200 | 180968.31 | 0 | Inventory posting for HIMARS | Inventory
T200093 | 2024-12-05 | THAAD | 5100 | 142293.07 | 0 | Inventory posting for THAAD | Inventory
T200094 | 2024-03-28 | THAAD | 5300 | 35365.1 | 0 | Journal posting for THAAD | Journal
T200095 | 2024-05-28 | THAAD | 7100 | 0 | 21421.88 | Inventory posting for THAAD | Inventory
T200096 | 2024-09-19 | HIMARS | 6100 | 0 | 20936.26 | Payroll posting for HIMARS | Payroll
T200097 | 2024-05-04 | THAAD | 5200 | 0 | 176924.1 | Inventory posting for THAAD | Inventory
T200098 | 2024-11-03 | HIMARS | 6100 | 110321.28 | 0 | Payroll posting for HIMARS | Payroll
T200099 | 2024-05-28 | HIMARS | 5400 | 0 | 221553.6 | Journal posting for HIMARS | Journal
T200100 | 2024-04-17 | Javelin | 5300 | 0 | 16760.56 | Journal posting for Javelin | Journal
T200101 | 2024-10-16 | PAC-3 | 6100 | 173131.23 | 0 | Payroll posting for PAC-3 | Payroll
T200102 | 2024-08-09 | Javelin | 6100 | 218368.49 | 0 | Payroll posting for Javelin | Payroll
T200103 | 2024-06-23 | HIMARS | 5200 | 0 | 174011.11 | Inventory posting for HIMARS | Inventory
T200104 | 2024-01-07 | HIMARS | 7200 | 0 | 97928.2 | AP posting for HIMARS | AP
T200105 | 2024-02-11 | Javelin | 5200 | 123664.01 | 0 | AP posting for Javelin | AP
T200106 | 2024-03-31 | HIMARS | 7100 | 0 | 215584.29 | AP posting for HIMARS | AP
T200107 | 2024-12-26 | PAC-3 | 5300 | 0 | 71749.38 | Inventory posting for PAC-3 | Inventory
T200108 | 2024-10-30 | THAAD | 5300 | 0 | 17076.54 | AP posting for THAAD | AP
T200109 | 2024-01-03 | Javelin | 7200 | 0 | 171223.57 | Inventory posting for Javelin | Inventory
T200110 | 2024-10-13 | HIMARS | 6200 | 0 | 242113.97 | Payroll posting for HIMARS | Payroll
T200111 | 2024-02-02 | PAC-3 | 5300 | 139289.42 | 0 | Inventory posting for PAC-3 | Inventory
T200112 | 2024-04-17 | PAC-3 | 5100 | 113734.12 | 0 | Inventory posting for PAC-3 | Inventory
T200113 | 2024-04-04 | Javelin | 5100 | 157535.48 | 0 | Journal posting for Javelin | Journal
T200114 | 2024-07-16 | HIMARS | 7100 | 0 | 175343.33 | AP posting for HIMARS | AP
T200115 | 2024-09-09 | HIMARS | 7200 | 0 | 30306.9 | Journal posting for HIMARS | Journal
T200116 | 2024-12-06 | Javelin | 5400 | 0 | 242111.06 | AP posting for Javelin | AP
T200117 | 2024-01-07 | THAAD | 5400 | 0 | 13353.45 | Inventory posting for THAAD | Inventory
T200118 | 2024-01-13 | PAC-3 | 6200 | 0 | 12628.26 | Payroll posting for PAC-3 | Payroll
T200119 | 2024-08-18 | HIMARS | 6200 | 0 | 22314.39 | Payroll posting for HIMARS | Payroll
T200120 | 2024-07-11 | HIMARS | 5200 | 0 | 134528.03 | Journal posting for HIMARS | Journal
T200121 | 2024-12-27 | PAC-3 | 6200 | 0 | 114994.08 | Payroll posting for PAC-3 | Payroll
T200122 | 2024-01-01 | PAC-3 | 6200 | 0 | 222051.3 | Payroll posting for PAC-3 | Payroll
T200123 | 2024-01-01 | THAAD | 5100 | 0 | 22807.17 | Journal posting for THAAD | Journal
T200124 | 2024-05-09 | Javelin | 6200 | 0 | 103053.68 | Payroll posting for Javelin | Payroll
T200125 | 2024-12-14 | PAC-3 | 5300 | 0 | 129983.94 | Inventory posting for PAC-3 | Inventory
T200126 | 2024-12-16 | Javelin | 6200 | 0 | 80770.88 | Journal posting for Javelin | Journal
T200127 | 2024-01-15 | Javelin | 5300 | 16961.4 | 0 | AP posting for Javelin | AP
T200128 | 2024-03-07 | HIMARS | 6200 | 56165.9 | 0 | Payroll posting for HIMARS | Payroll
T200129 | 2024-02-08 | HIMARS | 5300 | 0 | 116058.44 | Inventory posting for HIMARS | Inventory
T200130 | 2024-02-12 | HIMARS | 5100 | 0 | 245894.15 | Inventory posting for HIMARS | Inventory
T200131 | 2024-11-14 | THAAD | 7200 | 0 | 85804.87 | Journal posting for THAAD | Journal
T200132 | 2024-10-28 | Javelin | 6200 | 203651.03 | 0 | Journal posting for Javelin | Journal
T200133 | 2024-06-14 | Javelin | 6200 | 57041.61 | 0 | Payroll posting for Javelin | Payroll
T200134 | 2024-03-13 | PAC-3 | 5300 | 0 | 12788.34 | Journal posting for PAC-3 | Journal
T200135 | 2024-07-28 | PAC-3 | 7200 | 0 | 161054.62 | Inventory posting for PAC-3 | Inventory
T200136 | 2024-12-07 | THAAD | 7100 | 239665.73 | 0 | Journal posting for THAAD | Journal
T200137 | 2024-04-25 | HIMARS | 7200 | 139228.35 | 0 | Inventory posting for HIMARS | Inventory
T200138 | 2024-06-30 | HIMARS | 6100 | 158269.45 | 0 | Payroll posting for HIMARS | Payroll
T200139 | 2024-01-24 | Javelin | 6100 | 0 | 75784.01 | Payroll posting for Javelin | Payroll
T200140 | 2024-04-26 | THAAD | 6100 | 139566.56 | 0 | Payroll posting for THAAD | Payroll
T200141 | 2024-11-02 | Javelin | 5200 | 0 | 213022.36 | AP posting for Javelin | AP
T200142 | 2024-07-15 | PAC-3 | 5300 | 0 | 218893.72 | AP posting for PAC-3 | AP
T200143 | 2024-12-17 | PAC-3 | 5200 | 0 | 69184.01 | AP posting for PAC-3 | AP
T200144 | 2024-11-02 | HIMARS | 5400 | 0 | 75874.19 | Journal posting for HIMARS | Journal
T200145 | 2024-12-06 | PAC-3 | 6100 | 0 | 238768.14 | Payroll posting for PAC-3 | Payroll
T200146 | 2024-02-08 | HIMARS | 6100 | 224417.88 | 0 | Payroll posting for HIMARS | Payroll
T200147 | 2024-04-29 | Javelin | 5300 | 0 | 109017.5 | Inventory posting for Javelin | Inventory
T200148 | 2024-03-15 | HIMARS | 6100 | 0 | 150767.25 | Payroll posting for HIMARS | Payroll
T200149 | 2024-04-08 | HIMARS | 7200 | 0 | 146920.62 | Inventory posting for HIMARS | Inventory
T200150 | 2024-02-25 | HIMARS | 6200 | 159752.9 | 0 | Payroll posting for HIMARS | Payroll
T200151 | 2024-09-20 | Javelin | 5300 | 209756.85 | 0 | AP posting for Javelin | AP
T200152 | 2024-10-27 | HIMARS | 5200 | 0 | 213797.95 | AP posting for HIMARS | AP
T200153 | 2024-05-19 | Javelin | 6200 | 47917.84 | 0 | Payroll posting for Javelin | Payroll
T200154 | 2024-12-10 | THAAD | 6200 | 8653.01 | 0 | Payroll posting for THAAD | Payroll
T200155 | 2024-03-10 | HIMARS | 7100 | 231204.19 | 0 | AP posting for HIMARS | AP
T200156 | 2024-10-09 | Javelin | 5100 | 0 | 84386.85 | Inventory posting for Javelin | Inventory
T200157 | 2024-12-07 | PAC-3 | 6200 | 0 | 97320.8 | Payroll posting for PAC-3 | Payroll
T200158 | 2024-09-26 | PAC-3 | 7200 | 0 | 89236.51 | Inventory posting for PAC-3 | Inventory
T200159 | 2024-09-02 | HIMARS | 5400 | 140583.01 | 0 | AP posting for HIMARS | AP
T200160 | 2024-12-24 | Javelin | 7200 | 0 | 155615.56 | Inventory posting for Javelin | Inventory
T200161 | 2024-03-17 | PAC-3 | 5300 | 0 | 101029.25 | Inventory posting for PAC-3 | Inventory
T200162 | 2024-03-25 | THAAD | 6200 | 139747.16 | 0 | Payroll posting for THAAD | Payroll
T200163 | 2024-03-07 | THAAD | 5100 | 0 | 177198.45 | Journal posting for THAAD | Journal
T200164 | 2024-05-30 | HIMARS | 5100 | 0 | 62181.89 | AP posting for HIMARS | AP
T200165 | 2024-03-17 | THAAD | 5400 | 0 | 115171.56 | Inventory posting for THAAD | Inventory
T200166 | 2024-05-07 | PAC-3 | 5200 | 0 | 242520.84 | AP posting for PAC-3 | AP
T200167 | 2024-04-02 | THAAD | 5400 | 0 | 243982.38 | AP posting for THAAD | AP
T200168 | 2024-05-16 | PAC-3 | 6100 | 91197.59 | 0 | Payroll posting for PAC-3 | Payroll
T200169 | 2024-01-07 | PAC-3 | 6200 | 0 | 247941.46 | Payroll posting for PAC-3 | Payroll
T200170 | 2024-01-10 | THAAD | 7200 | 0 | 125329.54 | AP posting for THAAD | AP
T200171 | 2024-02-07 | THAAD | 6100 | 22973.39 | 0 | Payroll posting for THAAD | Payroll
T200172 | 2024-07-02 | Javelin | 5100 | 123946.49 | 0 | Journal posting for Javelin | Journal
T200173 | 2024-10-22 | THAAD | 5100 | 0 | 71460.8 | AP posting for THAAD | AP
T200174 | 2024-04-24 | THAAD | 7100 | 56970.72 | 0 | Inventory posting for THAAD | Inventory
T200175 | 2024-11-19 | HIMARS | 6200 | 225066.15 | 0 | Payroll posting for HIMARS | Payroll
T200176 | 2024-10-18 | HIMARS | 6100 | 0 | 17978.36 | Payroll posting for HIMARS | Payroll
T200177 | 2024-12-26 | THAAD | 7100 | 32789.72 | 0 | Inventory posting for THAAD | Inventory
T200178 | 2024-08-19 | PAC-3 | 5100 | 164393.32 | 0 | Journal posting for PAC-3 | Journal
T200179 | 2024-06-06 | THAAD | 5100 | 150972.85 | 0 | Inventory posting for THAAD | Inventory
T200180 | 2024-01-04 | Javelin | 7100 | 0 | 206746 | Journal posting for Javelin | Journal
T200181 | 2024-03-14 | THAAD | 7100 | 186411.01 | 0 | Journal posting for THAAD | Journal
T200182 | 2024-11-16 | THAAD | 6200 | 0 | 198867.95 | Payroll posting for THAAD | Payroll
T200183 | 2024-03-26 | Javelin | 6200 | 0 | 210250.57 | Payroll posting for Javelin | Payroll
T200184 | 2024-04-16 | PAC-3 | 6200 | 0 | 221757.5 | Payroll posting for PAC-3 | Payroll
T200185 | 2024-03-15 | THAAD | 5300 | 0 | 57916.39 | Inventory posting for THAAD | Inventory
T200186 | 2024-06-15 | HIMARS | 5400 | 0 | 151481.81 | Inventory posting for HIMARS | Inventory
T200187 | 2024-09-02 | Javelin | 6100 | 222535.95 | 0 | Payroll posting for Javelin | Payroll
T200188 | 2024-04-26 | THAAD | 5200 | 0 | 56407.51 | Inventory posting for THAAD | Inventory
T200189 | 2024-09-29 | PAC-3 | 5200 | 0 | 110575.54 | Journal posting for PAC-3 | Journal
T200190 | 2024-05-31 | THAAD | 7200 | 80409.23 | 0 | Journal posting for THAAD | Journal
T200191 | 2024-12-19 | Javelin | 5400 | 85347.64 | 0 | Journal posting for Javelin | Journal
T200192 | 2024-11-04 | THAAD | 6200 | 0 | 205937.65 | Payroll posting for THAAD | Payroll
T200193 | 2024-01-30 | Javelin | 6100 | 118189.88 | 0 | Payroll posting for Javelin | Payroll
T200194 | 2024-07-07 | PAC-3 | 6100 | 0 | 227208.7 | Payroll posting for PAC-3 | Payroll
T200195 | 2024-01-02 | HIMARS | 6200 | 162157.91 | 0 | Payroll posting for HIMARS | Payroll
T200196 | 2024-04-03 | HIMARS | 7200 | 0 | 176650.39 | Journal posting for HIMARS | Journal
T200197 | 2024-12-08 | THAAD | 5400 | 36503.77 | 0 | AP posting for THAAD | AP
T200198 | 2024-04-24 | THAAD | 5100 | 0 | 51144.98 | Inventory posting for THAAD | Inventory
T200199 | 2024-01-19 | PAC-3 | 6100 | 166634.23 | 0 | Journal posting for PAC-3 | Journal
T200200 | 2024-06-09 | PAC-3 | 5300 | 0 | 21431.57 | Journal posting for PAC-3 | Journal
T200201 | 2024-08-07 | PAC-3 | 5100 | 0 | 17686.94 | AP posting for PAC-3 | AP
T200202 | 2024-04-06 | PAC-3 | 6200 | 0 | 139030 | Journal posting for PAC-3 | Journal
T200203 | 2024-06-28 | PAC-3 | 6100 | 0 | 123395.93 | Payroll posting for PAC-3 | Payroll
T200204 | 2024-08-05 | HIMARS | 6100 | 0 | 87645.74 | Payroll posting for HIMARS | Payroll
T200205 | 2024-09-21 | PAC-3 | 5400 | 0 | 42399.98 | Inventory posting for PAC-3 | Inventory
T200206 | 2024-08-20 | THAAD | 5300 | 17285.29 | 0 | AP posting for THAAD | AP
T200207 | 2024-12-01 | THAAD | 5200 | 0 | 20661.18 | AP posting for THAAD | AP
T200208 | 2024-10-03 | THAAD | 5200 | 0 | 145669.69 | Inventory posting for THAAD | Inventory
T200209 | 2024-08-03 | Javelin | 5100 | 0 | 8864.73 | Inventory posting for Javelin | Inventory
T200210 | 2024-05-27 | HIMARS | 5100 | 0 | 172272.24 | Inventory posting for HIMARS | Inventory
T200211 | 2024-03-14 | THAAD | 5100 | 207732.84 | 0 | Inventory posting for THAAD | Inventory
T200212 | 2024-12-25 | PAC-3 | 7100 | 136203.84 | 0 | AP posting for PAC-3 | AP
T200213 | 2024-07-27 | THAAD | 7100 | 105750.7 | 0 | Journal posting for THAAD | Journal
T200214 | 2024-09-08 | HIMARS | 5300 | 0 | 146258.17 | Journal posting for HIMARS | Journal
T200215 | 2024-03-09 | PAC-3 | 5400 | 143499.16 | 0 | Inventory posting for PAC-3 | Inventory
T200216 | 2024-03-03 | Javelin | 5200 | 48745.45 | 0 | Inventory posting for Javelin | Inventory
T200217 | 2024-08-27 | Javelin | 5100 | 0 | 174181.95 | AP posting for Javelin | AP
T200218 | 2024-04-18 | THAAD | 5100 | 168090.07 | 0 | AP posting for THAAD | AP
T200219 | 2024-01-10 | Javelin | 5400 | 150433.67 | 0 | AP posting for Javelin | AP
T200220 | 2024-10-06 | PAC-3 | 5200 | 20439.11 | 0 | Inventory posting for PAC-3 | Inventory
T200221 | 2024-08-27 | THAAD | 7100 | 0 | 97019.27 | Journal posting for THAAD | Journal
T200222 | 2024-08-16 | Javelin | 6200 | 0 | 155530.45 | Payroll posting for Javelin | Payroll
T200223 | 2024-01-16 | THAAD | 5200 | 0 | 146284.96 | AP posting for THAAD | AP
T200224 | 2024-04-28 | THAAD | 5200 | 0 | 117957 | Inventory posting for THAAD | Inventory
T200225 | 2024-04-17 | Javelin | 5200 | 78629.06 | 0 | AP posting for Javelin | AP
T200226 | 2024-04-06 | Javelin | 6200 | 109092.64 | 0 | Journal posting for Javelin | Journal
T200227 | 2024-03-31 | PAC-3 | 5300 | 0 | 247576.9 | AP posting for PAC-3 | AP
T200228 | 2024-07-16 | Javelin | 6200 | 90431.45 | 0 | Payroll posting for Javelin | Payroll
T200229 | 2024-07-30 | HIMARS | 5100 | 56979.51 | 0 | Journal posting for HIMARS | Journal
T200230 | 2024-09-30 | PAC-3 | 5300 | 138781.29 | 0 | AP posting for PAC-3 | AP
T200231 | 2024-05-22 | PAC-3 | 6200 | 0 | 116452.99 | Payroll posting for PAC-3 | Payroll
T200232 | 2024-01-22 | PAC-3 | 6200 | 8850.56 | 0 | Payroll posting for PAC-3 | Payroll
T200233 | 2024-02-24 | PAC-3 | 6100 | 0 | 210802.08 | Payroll posting for PAC-3 | Payroll
T200234 | 2024-08-30 | Javelin | 5400 | 176428.06 | 0 | Inventory posting for Javelin | Inventory
T200235 | 2024-02-24 | HIMARS | 5200 | 0 | 78286.92 | Inventory posting for HIMARS | Inventory
T200236 | 2024-04-20 | Javelin | 5300 | 202645.12 | 0 | Inventory posting for Javelin | Inventory
T200237 | 2024-11-20 | HIMARS | 5200 | 0 | 97061.04 | Journal posting for HIMARS | Journal
T200238 | 2024-06-14 | PAC-3 | 7200 | 216669.47 | 0 | AP posting for PAC-3 | AP
T200239 | 2024-09-05 | Javelin | 6100 | 0 | 93300.89 | Journal posting for Javelin | Journal
T200240 | 2024-12-01 | PAC-3 | 6100 | 0 | 109200.5 | Payroll posting for PAC-3 | Payroll
T200241 | 2024-11-12 | Javelin | 6200 | 163801.17 | 0 | Journal posting for Javelin | Journal
T200242 | 2024-06-20 | PAC-3 | 7100 | 0 | 5294.89 | Journal posting for PAC-3 | Journal
T200243 | 2024-12-26 | PAC-3 | 7100 | 165051.53 | 0 | Inventory posting for PAC-3 | Inventory
T200244 | 2024-06-06 | HIMARS | 5400 | 0 | 147143.21 | AP posting for HIMARS | AP
T200245 | 2024-06-21 | PAC-3 | 5400 | 26866.19 | 0 | Journal posting for PAC-3 | Journal
T200246 | 2024-10-14 | THAAD | 6200 | 0 | 106710.4 | Payroll posting for THAAD | Payroll
T200247 | 2024-01-25 | THAAD | 5400 | 184721.8 | 0 | AP posting for THAAD | AP
T200248 | 2024-04-24 | THAAD | 6100 | 247969.99 | 0 | Journal posting for THAAD | Journal
T200249 | 2024-01-11 | Javelin | 6200 | 190202.2 | 0 | Journal posting for Javelin | Journal
T200250 | 2024-11-16 | PAC-3 | 5300 | 0 | 99504.42 | Journal posting for PAC-3 | Journal
T200251 | 2024-06-30 | Javelin | 5100 | 147469.54 | 0 | AP posting for Javelin | AP
T200252 | 2024-08-28 | THAAD | 5300 | 128414.52 | 0 | Inventory posting for THAAD | Inventory
T200253 | 2024-10-27 | PAC-3 | 5300 | 145102.42 | 0 | AP posting for PAC-3 | AP
T200254 | 2024-08-27 | PAC-3 | 5400 | 0 | 211279.82 | AP posting for PAC-3 | AP
T200255 | 2024-04-05 | PAC-3 | 7200 | 0 | 192440.54 | AP posting for PAC-3 | AP
T200256 | 2024-03-12 | PAC-3 | 5200 | 100764.58 | 0 | Journal posting for PAC-3 | Journal
T200257 | 2024-03-22 | Javelin | 7200 | 0 | 112415.08 | AP posting for Javelin | AP
T200258 | 2024-02-02 | HIMARS | 5300 | 121593.67 | 0 | Inventory posting for HIMARS | Inventory
T200259 | 2024-09-16 | HIMARS | 6100 | 0 | 115535.18 | Payroll posting for HIMARS | Payroll
T200260 | 2024-10-02 | THAAD | 6200 | 223153.44 | 0 | Payroll posting for THAAD | Payroll
T200261 | 2024-04-03 | HIMARS | 7200 | 0 | 73283.3 | Inventory posting for HIMARS | Inventory
T200262 | 2024-09-02 | THAAD | 5400 | 0 | 146227.77 | AP posting for THAAD | AP
T200263 | 2024-09-21 | HIMARS | 5300 | 107815.19 | 0 | Inventory posting for HIMARS | Inventory
T200264 | 2024-03-13 | PAC-3 | 6100 | 151826.44 | 0 | Payroll posting for PAC-3 | Payroll
T200265 | 2024-03-12 | PAC-3 | 6100 | 142884.91 | 0 | Payroll posting for PAC-3 | Payroll
T200266 | 2024-08-23 | PAC-3 | 7200 | 0 | 47617.21 | AP posting for PAC-3 | AP
T200267 | 2024-08-18 | HIMARS | 5100 | 0 | 144120.49 | AP posting for HIMARS | AP
T200268 | 2024-04-05 | HIMARS | 7200 | 89622.18 | 0 | AP posting for HIMARS | AP
T200269 | 2024-11-15 | HIMARS | 5200 | 101678.21 | 0 | Inventory posting for HIMARS | Inventory
T200270 | 2024-06-09 | HIMARS | 5200 | 0 | 62226.88 | Inventory posting for HIMARS | Inventory
T200271 | 2024-08-10 | THAAD | 6100 | 199472.87 | 0 | Payroll posting for THAAD | Payroll
T200272 | 2024-06-15 | Javelin | 7100 | 165481.05 | 0 | Inventory posting for Javelin | Inventory
T200273 | 2024-07-07 | HIMARS | 5100 | 44030.33 | 0 | Journal posting for HIMARS | Journal
T200274 | 2024-06-29 | PAC-3 | 6200 | 141850.49 | 0 | Payroll posting for PAC-3 | Payroll
T200275 | 2024-09-10 | HIMARS | 6200 | 181695.26 | 0 | Payroll posting for HIMARS | Payroll
T200276 | 2024-09-01 | HIMARS | 6200 | 0 | 183561.43 | Payroll posting for HIMARS | Payroll
T200277 | 2024-05-13 | PAC-3 | 5100 | 0 | 230742.41 | Journal posting for PAC-3 | Journal
T200278 | 2024-06-03 | Javelin | 6100 | 0 | 109664.74 | Payroll posting for Javelin | Payroll
T200279 | 2024-08-17 | HIMARS | 5100 | 175431.62 | 0 | Inventory posting for HIMARS | Inventory
T200280 | 2024-10-27 | PAC-3 | 5200 | 0 | 74613.29 | Inventory posting for PAC-3 | Inventory
T200281 | 2024-03-15 | HIMARS | 6200 | 16197.68 | 0 | Payroll posting for HIMARS | Payroll
T200282 | 2024-02-12 | PAC-3 | 6100 | 200328.46 | 0 | Payroll posting for PAC-3 | Payroll
T200283 | 2024-03-04 | Javelin | 6100 | 0 | 46065.49 | Payroll posting for Javelin | Payroll
T200284 | 2024-08-08 | PAC-3 | 6200 | 32610.98 | 0 | Payroll posting for PAC-3 | Payroll
T200285 | 2024-12-11 | THAAD | 5100 | 155188.42 | 0 | Inventory posting for THAAD | Inventory
T200286 | 2024-08-27 | HIMARS | 5100 | 0 | 129304.54 | AP posting for HIMARS | AP
T200287 | 2024-06-26 | Javelin | 5400 | 85178.69 | 0 | AP posting for Javelin | AP
T200288 | 2024-12-20 | HIMARS | 7200 | 0 | 172809.5 | Journal posting for HIMARS | Journal
T200289 | 2024-02-29 | Javelin | 5200 | 0 | 184866.76 | Journal posting for Javelin | Journal
T200290 | 2024-08-22 | THAAD | 7200 | 0 | 12300.94 | Journal posting for THAAD | Journal
T200291 | 2024-02-27 | THAAD | 5100 | 0 | 138583.6 | AP posting for THAAD | AP
T200292 | 2024-06-22 | HIMARS | 6200 | 9761.61 | 0 | Journal posting for HIMARS | Journal
T200293 | 2024-04-20 | THAAD | 5400 | 0 | 201476.85 | AP posting for THAAD | AP
T200294 | 2024-05-24 | HIMARS | 5400 | 0 | 169109.17 | AP posting for HIMARS | AP
T200295 | 2024-12-25 | Javelin | 7100 | 183897.84 | 0 | AP posting for Javelin | AP
T200296 | 2024-11-04 | THAAD | 5400 | 0 | 72772.46 | Inventory posting for THAAD | Inventory
T200297 | 2024-05-08 | HIMARS | 5100 | 0 | 44588.94 | Journal posting for HIMARS | Journal
T200298 | 2024-07-05 | THAAD | 6100 | 206037.55 | 0 | Journal posting for THAAD | Journal
T200299 | 2024-09-02 | THAAD | 6100 | 155458.21 | 0 | Payroll posting for THAAD | Payroll
T200300 | 2024-08-05 | HIMARS | 6100 | 158810.67 | 0 | Payroll posting for HIMARS | Payroll
T200301 | 2024-01-21 | THAAD | 5100 | 0 | 13882.45 | AP posting for THAAD | AP
T200302 | 2024-11-01 | PAC-3 | 5200 | 76717.49 | 0 | Inventory posting for PAC-3 | Inventory
T200303 | 2024-04-27 | THAAD | 5100 | 0 | 52644.25 | AP posting for THAAD | AP
T200304 | 2024-06-19 | THAAD | 7100 | 96833.49 | 0 | Journal posting for THAAD | Journal
T200305 | 2024-01-17 | THAAD | 7200 | 0 | 17942.04 | AP posting for THAAD | AP
T200306 | 2024-09-07 | PAC-3 | 7100 | 84297.38 | 0 | Inventory posting for PAC-3 | Inventory
T200307 | 2024-04-26 | Javelin | 7100 | 150159.17 | 0 | Inventory posting for Javelin | Inventory
T200308 | 2024-07-07 | THAAD | 5300 | 0 | 29782.01 | AP posting for THAAD | AP
T200309 | 2024-02-21 | PAC-3 | 7200 | 130607.57 | 0 | AP posting for PAC-3 | AP
T200310 | 2024-05-24 | PAC-3 | 6200 | 0 | 214363.89 | Payroll posting for PAC-3 | Payroll
T200311 | 2024-07-04 | Javelin | 6200 | 0 | 199326.85 | Payroll posting for Javelin | Payroll
T200312 | 2024-05-30 | Javelin | 7100 | 0 | 24122.13 | Inventory posting for Javelin | Inventory
T200313 | 2024-02-13 | HIMARS | 5300 | 0 | 57237.48 | Inventory posting for HIMARS | Inventory
T200314 | 2024-06-27 | PAC-3 | 5400 | 133124.78 | 0 | AP posting for PAC-3 | AP
T200315 | 2024-03-13 | PAC-3 | 5300 | 115183.19 | 0 | Inventory posting for PAC-3 | Inventory
T200316 | 2024-11-04 | THAAD | 5200 | 136713.4 | 0 | Journal posting for THAAD | Journal
T200317 | 2024-01-07 | PAC-3 | 5100 | 134241.06 | 0 | Inventory posting for PAC-3 | Inventory
T200318 | 2024-12-23 | PAC-3 | 7100 | 158006.91 | 0 | Journal posting for PAC-3 | Journal
T200319 | 2024-05-25 | PAC-3 | 6100 | 0 | 240161.64 | Payroll posting for PAC-3 | Payroll
T200320 | 2024-02-09 | PAC-3 | 5400 | 0 | 102990.22 | Inventory posting for PAC-3 | Inventory
T200321 | 2024-01-31 | THAAD | 5300 | 0 | 179615.91 | Journal posting for THAAD | Journal
T200322 | 2024-06-09 | THAAD | 6200 | 239795.4 | 0 | Payroll posting for THAAD | Payroll
T200323 | 2024-07-30 | THAAD | 5100 | 138895.86 | 0 | Inventory posting for THAAD | Inventory
T200324 | 2024-11-23 | HIMARS | 6200 | 140479.02 | 0 | Payroll posting for HIMARS | Payroll
T200325 | 2024-09-29 | Javelin | 6100 | 88193.39 | 0 | Payroll posting for Javelin | Payroll
T200326 | 2024-11-13 | HIMARS | 5100 | 0 | 166681.45 | Journal posting for HIMARS | Journal
T200327 | 2024-08-17 | PAC-3 | 5400 | 109206.98 | 0 | Inventory posting for PAC-3 | Inventory
T200328 | 2024-01-03 | THAAD | 5400 | 0 | 7686.65 | Journal posting for THAAD | Journal
T200329 | 2024-07-24 | PAC-3 | 5200 | 0 | 212708.62 | Journal posting for PAC-3 | Journal
T200330 | 2024-01-25 | THAAD | 5200 | 0 | 204214.47 | Inventory posting for THAAD | Inventory
T200331 | 2024-06-28 | Javelin | 5400 | 76638.71 | 0 | AP posting for Javelin | AP
T200332 | 2024-11-13 | THAAD | 6100 | 210517.27 | 0 | Payroll posting for THAAD | Payroll
T200333 | 2024-02-07 | PAC-3 | 6100 | 0 | 171907.63 | Payroll posting for PAC-3 | Payroll
T200334 | 2024-11-29 | THAAD | 5200 | 0 | 65885.86 | AP posting for THAAD | AP
T200335 | 2024-05-26 | Javelin | 5400 | 35698.72 | 0 | Inventory posting for Javelin | Inventory
T200336 | 2024-03-29 | THAAD | 6200 | 0 | 198822.96 | Payroll posting for THAAD | Payroll
T200337 | 2024-11-15 | PAC-3 | 7200 | 0 | 94843.62 | Inventory posting for PAC-3 | Inventory
T200338 | 2024-08-07 | HIMARS | 5400 | 0 | 9495.42 | AP posting for HIMARS | AP
T200339 | 2024-08-23 | PAC-3 | 5300 | 134337.91 | 0 | AP posting for PAC-3 | AP
T200340 | 2024-05-02 | THAAD | 5400 | 12673.84 | 0 | AP posting for THAAD | AP
T200341 | 2024-12-29 | HIMARS | 5300 | 34538.3 | 0 | AP posting for HIMARS | AP
T200342 | 2024-10-24 | THAAD | 5400 | 135766.79 | 0 | Journal posting for THAAD | Journal
T200343 | 2024-04-13 | THAAD | 7100 | 53868.36 | 0 | Inventory posting for THAAD | Inventory
T200344 | 2024-12-08 | PAC-3 | 6100 | 0 | 183988.74 | Payroll posting for PAC-3 | Payroll
T200345 | 2024-06-25 | PAC-3 | 5100 | 0 | 231922.46 | AP posting for PAC-3 | AP
T200346 | 2024-06-21 | HIMARS | 7200 | 0 | 44409.11 | Inventory posting for HIMARS | Inventory
T200347 | 2024-05-10 | HIMARS | 7200 | 230683.83 | 0 | AP posting for HIMARS | AP
T200348 | 2024-11-05 | PAC-3 | 7200 | 213401.46 | 0 | Journal posting for PAC-3 | Journal
T200349 | 2024-06-28 | PAC-3 | 6100 | 33948.11 | 0 | Payroll posting for PAC-3 | Payroll
T200350 | 2024-07-20 | PAC-3 | 6100 | 208921.62 | 0 | Payroll posting for PAC-3 | Payroll
T200351 | 2024-09-13 | THAAD | 6100 | 0 | 174762.74 | Payroll posting for THAAD | Payroll
T200352 | 2024-11-09 | THAAD | 5100 | 243707.82 | 0 | Inventory posting for THAAD | Inventory
T200353 | 2024-07-20 | HIMARS | 5200 | 0 | 62976 | Inventory posting for HIMARS | Inventory
T200354 | 2024-11-26 | PAC-3 | 5200 | 0 | 248701.29 | AP posting for PAC-3 | AP
T200355 | 2024-06-29 | HIMARS | 5400 | 106609.5 | 0 | Journal posting for HIMARS | Journal
T200356 | 2024-04-30 | THAAD | 6100 | 240250.52 | 0 | Payroll posting for THAAD | Payroll
T200357 | 2024-07-10 | HIMARS | 7200 | 0 | 203862.56 | AP posting for HIMARS | AP
T200358 | 2024-04-19 | PAC-3 | 5200 | 64314.24 | 0 | Inventory posting for PAC-3 | Inventory
T200359 | 2024-03-04 | Javelin | 6200 | 0 | 32575.85 | Payroll posting for Javelin | Payroll
T200360 | 2024-05-08 | THAAD | 7200 | 78356.13 | 0 | Inventory posting for THAAD | Inventory
T200361 | 2024-12-20 | PAC-3 | 7100 | 0 | 113815.33 | Inventory posting for PAC-3 | Inventory
T200362 | 2024-09-16 | THAAD | 5300 | 0 | 162074.27 | Journal posting for THAAD | Journal
T200363 | 2024-08-19 | HIMARS | 5400 | 162955.63 | 0 | AP posting for HIMARS | AP
T200364 | 2024-06-18 | Javelin | 7200 | 0 | 41882.5 | Inventory posting for Javelin | Inventory
T200365 | 2024-03-07 | HIMARS | 6200 | 0 | 15355.9 | Payroll posting for HIMARS | Payroll
T200366 | 2024-02-29 | PAC-3 | 5300 | 206109.06 | 0 | Journal posting for PAC-3 | Journal
T200367 | 2024-10-08 | HIMARS | 6100 | 0 | 52609.96 | Journal posting for HIMARS | Journal
T200368 | 2024-05-25 | Javelin | 7100 | 26463.64 | 0 | Journal posting for Javelin | Journal
T200369 | 2024-08-28 | HIMARS | 5200 | 0 | 138338.01 | Inventory posting for HIMARS | Inventory
T200370 | 2024-10-29 | PAC-3 | 6200 | 0 | 165122.38 | Payroll posting for PAC-3 | Payroll
T200371 | 2024-05-14 | HIMARS | 5200 | 46566.96 | 0 | Inventory posting for HIMARS | Inventory
T200372 | 2024-11-29 | PAC-3 | 7100 | 6004.86 | 0 | Inventory posting for PAC-3 | Inventory
T200373 | 2024-11-05 | THAAD | 6100 | 72223.7 | 0 | Payroll posting for THAAD | Payroll
T200374 | 2024-07-23 | HIMARS | 5400 | 203400.59 | 0 | Journal posting for HIMARS | Journal
T200375 | 2024-12-26 | Javelin | 7100 | 118106.5 | 0 | AP posting for Javelin | AP
T200376 | 2024-03-24 | Javelin | 6100 | 0 | 194693.84 | Payroll posting for Javelin | Payroll
T200377 | 2024-05-08 | Javelin | 6200 | 0 | 227715.03 | Journal posting for Javelin | Journal
T200378 | 2024-11-16 | THAAD | 6100 | 89405.93 | 0 | Payroll posting for THAAD | Payroll
T200379 | 2024-05-17 | THAAD | 5400 | 0 | 86072.6 | AP posting for THAAD | AP
T200380 | 2024-04-08 | HIMARS | 7100 | 0 | 40965.24 | Journal posting for HIMARS | Journal
T200381 | 2024-11-24 | PAC-3 | 5100 | 93640.92 | 0 | Journal posting for PAC-3 | Journal
T200382 | 2024-05-25 | PAC-3 | 5400 | 0 | 54607.25 | Inventory posting for PAC-3 | Inventory
T200383 | 2024-03-12 | Javelin | 6200 | 0 | 105930.12 | Payroll posting for Javelin | Payroll
T200384 | 2024-03-08 | Javelin | 6100 | 0 | 6049.03 | Payroll posting for Javelin | Payroll
T200385 | 2024-11-23 | THAAD | 6100 | 74047.29 | 0 | Journal posting for THAAD | Journal
T200386 | 2024-06-03 | Javelin | 5400 | 0 | 183051.44 | Journal posting for Javelin | Journal
T200387 | 2024-03-27 | THAAD | 5100 | 0 | 231519.7 | Inventory posting for THAAD | Inventory
T200388 | 2024-12-22 | HIMARS | 7200 | 64158.74 | 0 | AP posting for HIMARS | AP
T200389 | 2024-09-04 | Javelin | 6200 | 0 | 162481.76 | Payroll posting for Javelin | Payroll
T200390 | 2024-07-02 | Javelin | 5300 | 29268.83 | 0 | Inventory posting for Javelin | Inventory
T200391 | 2024-07-04 | THAAD | 5200 | 0 | 142599.97 | Journal posting for THAAD | Journal
T200392 | 2024-04-28 | Javelin | 6100 | 0 | 99896.69 | Journal posting for Javelin | Journal
T200393 | 2024-06-05 | Javelin | 7200 | 190583.17 | 0 | Inventory posting for Javelin | Inventory
T200394 | 2024-11-20 | THAAD | 7200 | 27837.41 | 0 | Inventory posting for THAAD | Inventory
T200395 | 2024-06-02 | THAAD | 7100 | 87328.9 | 0 | AP posting for THAAD | AP
T200396 | 2024-09-15 | THAAD | 7200 | 246689.33 | 0 | Inventory posting for THAAD | Inventory
T200397 | 2024-11-24 | PAC-3 | 6200 | 0 | 102246.94 | Payroll posting for PAC-3 | Payroll
T200398 | 2024-10-07 | THAAD | 5400 | 241748.03 | 0 | Inventory posting for THAAD | Inventory
T200399 | 2024-10-19 | PAC-3 | 7100 | 0 | 129732.85 | AP posting for PAC-3 | AP
T200400 | 2024-11-22 | THAAD | 6100 | 0 | 229534.75 | Payroll posting for THAAD | Payroll
T200401 | 2024-12-28 | Javelin | 6200 | 0 | 214557.35 | Journal posting for Javelin | Journal
T200402 | 2024-02-10 | THAAD | 5400 | 24283.68 | 0 | Inventory posting for THAAD | Inventory
T200403 | 2024-06-28 | PAC-3 | 5300 | 0 | 235458.11 | AP posting for PAC-3 | AP
T200404 | 2024-06-04 | HIMARS | 5200 | 0 | 197059.54 | AP posting for HIMARS | AP
T200405 | 2024-10-01 | HIMARS | 5400 | 144742.17 | 0 | AP posting for HIMARS | AP
T200406 | 2024-05-30 | Javelin | 7200 | 152781.26 | 0 | Inventory posting for Javelin | Inventory
T200407 | 2024-01-09 | Javelin | 5200 | 0 | 111086.21 | Journal posting for Javelin | Journal
T200408 | 2024-08-15 | THAAD | 6200 | 240758.12 | 0 | Payroll posting for THAAD | Payroll
T200409 | 2024-10-28 | PAC-3 | 6200 | 0 | 176998.74 | Payroll posting for PAC-3 | Payroll
T200410 | 2024-08-18 | PAC-3 | 6100 | 0 | 46595.35 | Payroll posting for PAC-3 | Payroll
T200411 | 2024-11-23 | PAC-3 | 7200 | 0 | 110700.71 | Journal posting for PAC-3 | Journal
T200412 | 2024-03-16 | Javelin | 5400 | 0 | 16490.07 | Journal posting for Javelin | Journal
T200413 | 2024-09-21 | PAC-3 | 7200 | 0 | 84739.9 | Inventory posting for PAC-3 | Inventory
T200414 | 2024-01-31 | THAAD | 6100 | 172774.87 | 0 | Payroll posting for THAAD | Payroll
T200415 | 2024-05-19 | Javelin | 6200 | 0 | 110933.69 | Payroll posting for Javelin | Payroll
T200416 | 2024-10-29 | HIMARS | 5200 | 0 | 213297.14 | Inventory posting for HIMARS | Inventory
T200417 | 2024-05-03 | Javelin | 7200 | 0 | 214233.8 | AP posting for Javelin | AP
T200418 | 2024-04-30 | THAAD | 6200 | 0 | 62654.76 | Payroll posting for THAAD | Payroll
T200419 | 2024-05-15 | Javelin | 7100 | 104106.52 | 0 | Inventory posting for Javelin | Inventory
T200420 | 2024-08-29 | Javelin | 7200 | 0 | 206833.58 | Journal posting for Javelin | Journal
T200421 | 2024-11-09 | Javelin | 7100 | 228337 | 0 | AP posting for Javelin | AP
T200422 | 2024-03-20 | HIMARS | 6100 | 0 | 144675.31 | Payroll posting for HIMARS | Payroll
T200423 | 2024-03-26 | Javelin | 7100 | 62482.46 | 0 | AP posting for Javelin | AP
T200424 | 2024-01-04 | HIMARS | 6200 | 118746.25 | 0 | Payroll posting for HIMARS | Payroll
T200425 | 2024-09-09 | THAAD | 7100 | 0 | 50706.69 | Inventory posting for THAAD | Inventory
T200426 | 2024-12-11 | Javelin | 5300 | 53423.71 | 0 | Inventory posting for Javelin | Inventory
T200427 | 2024-05-25 | THAAD | 5100 | 0 | 73712.82 | Inventory posting for THAAD | Inventory
T200428 | 2024-08-15 | Javelin | 6100 | 145002.47 | 0 | Payroll posting for Javelin | Payroll
T200429 | 2024-11-01 | PAC-3 | 7200 | 0 | 117533.03 | Inventory posting for PAC-3 | Inventory
T200430 | 2024-04-15 | PAC-3 | 5100 | 0 | 107084.17 | AP posting for PAC-3 | AP
T200431 | 2024-04-21 | HIMARS | 5100 | 101223.79 | 0 | AP posting for HIMARS | AP
T200432 | 2024-11-24 | PAC-3 | 6200 | 0 | 80563.17 | Payroll posting for PAC-3 | Payroll
T200433 | 2024-12-25 | Javelin | 6100 | 137287.32 | 0 | Journal posting for Javelin | Journal
T200434 | 2024-12-21 | HIMARS | 6200 | 225791.33 | 0 | Payroll posting for HIMARS | Payroll
T200435 | 2024-11-04 | PAC-3 | 5100 | 0 | 9983.5 | Inventory posting for PAC-3 | Inventory
T200436 | 2024-09-17 | HIMARS | 5200 | 218795.99 | 0 | Journal posting for HIMARS | Journal
T200437 | 2024-12-22 | PAC-3 | 5400 | 218924.04 | 0 | AP posting for PAC-3 | AP
T200438 | 2024-11-28 | HIMARS | 7100 | 185696.86 | 0 | Inventory posting for HIMARS | Inventory
T200439 | 2024-08-08 | HIMARS | 6200 | 0 | 197537.38 | Payroll posting for HIMARS | Payroll
T200440 | 2024-09-20 | THAAD | 6100 | 202465.73 | 0 | Payroll posting for THAAD | Payroll
T200441 | 2024-12-14 | Javelin | 6100 | 0 | 87245.06 | Journal posting for Javelin | Journal
T200442 | 2024-12-27 | HIMARS | 6200 | 126049.78 | 0 | Payroll posting for HIMARS | Payroll
T200443 | 2024-11-03 | THAAD | 5200 | 158594.49 | 0 | Inventory posting for THAAD | Inventory
T200444 | 2024-12-16 | Javelin | 7100 | 0 | 61629.38 | Journal posting for Javelin | Journal
T200445 | 2024-03-16 | THAAD | 5100 | 139436.3 | 0 | Journal posting for THAAD | Journal
T200446 | 2024-01-12 | PAC-3 | 7100 | 166414.5 | 0 | Journal posting for PAC-3 | Journal
T200447 | 2024-11-16 | PAC-3 | 6200 | 0 | 89494.08 | Payroll posting for PAC-3 | Payroll
T200448 | 2024-02-07 | PAC-3 | 5300 | 210888.57 | 0 | Inventory posting for PAC-3 | Inventory
T200449 | 2024-06-12 | Javelin | 5100 | 0 | 39498.91 | AP posting for Javelin | AP
T200450 | 2024-09-05 | Javelin | 5300 | 0 | 240133.08 | AP posting for Javelin | AP
T200451 | 2024-06-23 | PAC-3 | 5400 | 183980.37 | 0 | AP posting for PAC-3 | AP
T200452 | 2024-08-06 | PAC-3 | 6100 | 193870.11 | 0 | Payroll posting for PAC-3 | Payroll
T200453 | 2024-01-15 | Javelin | 6100 | 142256.62 | 0 | Payroll posting for Javelin | Payroll
T200454 | 2024-03-17 | PAC-3 | 7100 | 108162.49 | 0 | Inventory posting for PAC-3 | Inventory
T200455 | 2024-03-31 | THAAD | 5200 | 0 | 77335.53 | Inventory posting for THAAD | Inventory
T200456 | 2024-02-04 | THAAD | 6200 | 55732.68 | 0 | Payroll posting for THAAD | Payroll
T200457 | 2024-02-01 | Javelin | 7100 | 205366.71 | 0 | Inventory posting for Javelin | Inventory
T200458 | 2024-02-13 | Javelin | 5400 | 67155.1 | 0 | Inventory posting for Javelin | Inventory
T200459 | 2024-07-25 | THAAD | 6100 | 0 | 177744.58 | Payroll posting for THAAD | Payroll
T200460 | 2024-05-27 | HIMARS | 5300 | 11735.76 | 0 | AP posting for HIMARS | AP
T200461 | 2024-11-29 | PAC-3 | 5100 | 56054.37 | 0 | AP posting for PAC-3 | AP
T200462 | 2024-08-04 | HIMARS | 6200 | 134145.36 | 0 | Payroll posting for HIMARS | Payroll
T200463 | 2024-06-01 | PAC-3 | 5200 | 120456.43 | 0 | Journal posting for PAC-3 | Journal
T200464 | 2024-06-04 | THAAD | 5200 | 0 | 110097.65 | Inventory posting for THAAD | Inventory
T200465 | 2024-04-04 | HIMARS | 5300 | 156094.52 | 0 | Inventory posting for HIMARS | Inventory
T200466 | 2024-11-16 | HIMARS | 7200 | 0 | 135143.7 | Inventory posting for HIMARS | Inventory
T200467 | 2024-07-10 | Javelin | 5100 | 214743.36 | 0 | Journal posting for Javelin | Journal
T200468 | 2024-10-23 | PAC-3 | 5100 | 13286.22 | 0 | AP posting for PAC-3 | AP
T200469 | 2024-03-22 | Javelin | 7100 | 0 | 232196.49 | Inventory posting for Javelin | Inventory
T200470 | 2024-09-03 | HIMARS | 5300 | 18715.17 | 0 | AP posting for HIMARS | AP
T200471 | 2024-03-06 | THAAD | 6200 | 200104.71 | 0 | Payroll posting for THAAD | Payroll
T200472 | 2024-07-28 | HIMARS | 5300 | 52611.38 | 0 | Inventory posting for HIMARS | Inventory
T200473 | 2024-08-09 | PAC-3 | 5300 | 0 | 119412.91 | AP posting for PAC-3 | AP
T200474 | 2024-01-28 | Javelin | 5400 | 105779.83 | 0 | Inventory posting for Javelin | Inventory
T200475 | 2024-06-24 | Javelin | 6100 | 0 | 141777.75 | Payroll posting for Javelin | Payroll
T200476 | 2024-08-15 | Javelin | 7200 | 139195.67 | 0 | Journal posting for Javelin | Journal
T200477 | 2024-01-25 | THAAD | 5100 | 101450.67 | 0 | Inventory posting for THAAD | Inventory
T200478 | 2024-03-21 | PAC-3 | 6100 | 0 | 200987.03 | Payroll posting for PAC-3 | Payroll
T200479 | 2024-04-30 | Javelin | 6200 | 0 | 18175.34 | Payroll posting for Javelin | Payroll
T200480 | 2024-10-12 | THAAD | 6100 | 180736.22 | 0 | Payroll posting for THAAD | Payroll
T200481 | 2024-01-19 | THAAD | 6100 | 90278.64 | 0 | Payroll posting for THAAD | Payroll
T200482 | 2024-03-22 | HIMARS | 7200 | 201717.81 | 0 | AP posting for HIMARS | AP
T200483 | 2024-11-11 | HIMARS | 5300 | 0 | 27270.23 | AP posting for HIMARS | AP
T200484 | 2024-12-06 | HIMARS | 6200 | 82456.92 | 0 | Payroll posting for HIMARS | Payroll
T200485 | 2024-07-17 | PAC-3 | 5200 | 61427.1 | 0 | AP posting for PAC-3 | AP
T200486 | 2024-03-15 | Javelin | 5200 | 0 | 180995.34 | Inventory posting for Javelin | Inventory
T200487 | 2024-03-15 | PAC-3 | 5400 | 196275.91 | 0 | Inventory posting for PAC-3 | Inventory
T200488 | 2024-05-09 | PAC-3 | 7200 | 169676.43 | 0 | Inventory posting for PAC-3 | Inventory
T200489 | 2024-04-19 | PAC-3 | 6200 | 192844.36 | 0 | Payroll posting for PAC-3 | Payroll
T200490 | 2024-10-02 | THAAD | 6100 | 46579.79 | 0 | Payroll posting for THAAD | Payroll
T200491 | 2024-10-20 | PAC-3 | 5300 | 0 | 108391.29 | Inventory posting for PAC-3 | Inventory
T200492 | 2024-07-11 | PAC-3 | 5400 | 0 | 105670.48 | AP posting for PAC-3 | AP
T200493 | 2024-04-02 | HIMARS | 5200 | 235109.91 | 0 | Journal posting for HIMARS | Journal
T200494 | 2024-09-05 | HIMARS | 6100 | 0 | 53742.68 | Payroll posting for HIMARS | Payroll
T200495 | 2024-10-13 | THAAD | 5300 | 65477.98 | 0 | AP posting for THAAD | AP
T200496 | 2024-05-23 | PAC-3 | 7100 | 0 | 187816.67 | Inventory posting for PAC-3 | Inventory
T200497 | 2024-09-09 | HIMARS | 5100 | 31915.64 | 0 | Inventory posting for HIMARS | Inventory
T200498 | 2024-02-21 | HIMARS | 6100 | 123323.57 | 0 | Payroll posting for HIMARS | Payroll
T200499 | 2024-04-09 | HIMARS | 6200 | 116213.58 | 0 | Payroll posting for HIMARS | Payroll
T200500 | 2024-03-28 | Javelin | 5400 | 249584.27 | 0 | Inventory posting for Javelin | Inventory
T200501 | 2024-06-30 | PAC-3 | 5400 | 0 | 212741.42 | AP posting for PAC-3 | AP
T200502 | 2024-12-28 | Javelin | 6100 | 0 | 173629.74 | Payroll posting for Javelin | Payroll
T200503 | 2024-03-10 | PAC-3 | 5300 | 98427.56 | 0 | Inventory posting for PAC-3 | Inventory
T200504 | 2024-01-02 | Javelin | 5300 | 0 | 132336.91 | Inventory posting for Javelin | Inventory
T200505 | 2024-02-17 | HIMARS | 7100 | 0 | 5347.46 | Inventory posting for HIMARS | Inventory
T200506 | 2024-12-21 | THAAD | 7100 | 182222.86 | 0 | Inventory posting for THAAD | Inventory
T200507 | 2024-10-09 | PAC-3 | 5300 | 58923.28 | 0 | Journal posting for PAC-3 | Journal
T200508 | 2024-07-24 | HIMARS | 6200 | 0 | 132040.2 | Payroll posting for HIMARS | Payroll
T200509 | 2024-11-24 | Javelin | 7100 | 216083.25 | 0 | AP posting for Javelin | AP
T200510 | 2024-05-16 | PAC-3 | 6200 | 0 | 75204.11 | Journal posting for PAC-3 | Journal
T200511 | 2024-12-11 | Javelin | 6200 | 222735.44 | 0 | Payroll posting for Javelin | Payroll
T200512 | 2024-05-09 | Javelin | 5100 | 0 | 213131.83 | Journal posting for Javelin | Journal
T200513 | 2024-09-25 | Javelin | 5200 | 0 | 48941.57 | AP posting for Javelin | AP
T200514 | 2024-04-21 | THAAD | 7200 | 199616.32 | 0 | Journal posting for THAAD | Journal
T200515 | 2024-04-22 | HIMARS | 6100 | 0 | 46299.44 | Payroll posting for HIMARS | Payroll
T200516 | 2024-06-07 | PAC-3 | 6200 | 76472.35 | 0 | Payroll posting for PAC-3 | Payroll
T200517 | 2024-05-22 | PAC-3 | 5300 | 0 | 179416.42 | Inventory posting for PAC-3 | Inventory
T200518 | 2024-05-30 | PAC-3 | 5200 | 142161.07 | 0 | Inventory posting for PAC-3 | Inventory
T200519 | 2024-04-13 | THAAD | 6200 | 0 | 5276.51 | Payroll posting for THAAD | Payroll
T200520 | 2024-04-18 | Javelin | 5100 | 60881.77 | 0 | AP posting for Javelin | AP
T200521 | 2024-05-25 | PAC-3 | 5200 | 30041.77 | 0 | Journal posting for PAC-3 | Journal
T200522 | 2024-02-17 | THAAD | 7200 | 0 | 46471.56 | AP posting for THAAD | AP
T200523 | 2024-06-13 | HIMARS | 7200 | 51105.12 | 0 | Inventory posting for HIMARS | Inventory
T200524 | 2024-08-04 | HIMARS | 7200 | 0 | 239349.3 | AP posting for HIMARS | AP
T200525 | 2024-06-18 | Javelin | 7200 | 0 | 227833.76 | AP posting for Javelin | AP
T200526 | 2024-07-12 | Javelin | 5200 | 0 | 197384.3 | Journal posting for Javelin | Journal
T200527 | 2024-07-17 | THAAD | 5200 | 94218.76 | 0 | Inventory posting for THAAD | Inventory
T200528 | 2024-08-03 | THAAD | 5300 | 24301.61 | 0 | Inventory posting for THAAD | Inventory
T200529 | 2024-08-17 | PAC-3 | 5300 | 0 | 52224.81 | AP posting for PAC-3 | AP
T200530 | 2024-07-06 | Javelin | 5300 | 50067.12 | 0 | AP posting for Javelin | AP
T200531 | 2024-06-09 | THAAD | 6100 | 0 | 18680.36 | Journal posting for THAAD | Journal
T200532 | 2024-12-27 | HIMARS | 6100 | 0 | 26213.9 | Payroll posting for HIMARS | Payroll
T200533 | 2024-05-14 | THAAD | 7100 | 0 | 135130.96 | AP posting for THAAD | AP
T200534 | 2024-05-19 | PAC-3 | 5300 | 69482.16 | 0 | AP posting for PAC-3 | AP
T200535 | 2024-02-01 | HIMARS | 5300 | 0 | 55812.69 | Inventory posting for HIMARS | Inventory
T200536 | 2024-08-21 | Javelin | 7200 | 0 | 77769.96 | Inventory posting for Javelin | Inventory
T200537 | 2024-02-02 | PAC-3 | 5100 | 0 | 25766.07 | AP posting for PAC-3 | AP
T200538 | 2024-08-28 | PAC-3 | 6100 | 0 | 66944.28 | Payroll posting for PAC-3 | Payroll
T200539 | 2024-04-21 | Javelin | 5400 | 53867.37 | 0 | Journal posting for Javelin | Journal
T200540 | 2024-05-21 | Javelin | 6200 | 0 | 150739.6 | Payroll posting for Javelin | Payroll
T200541 | 2024-11-05 | HIMARS | 7100 | 151197.46 | 0 | Journal posting for HIMARS | Journal
T200542 | 2024-11-29 | PAC-3 | 7100 | 0 | 110852.5 | AP posting for PAC-3 | AP
T200543 | 2024-06-24 | HIMARS | 5200 | 81563.84 | 0 | Journal posting for HIMARS | Journal
T200544 | 2024-10-13 | HIMARS | 6200 | 68454.62 | 0 | Payroll posting for HIMARS | Payroll
T200545 | 2024-01-18 | THAAD | 7200 | 48000.31 | 0 | Journal posting for THAAD | Journal
T200546 | 2024-05-23 | THAAD | 7100 | 151752.57 | 0 | Inventory posting for THAAD | Inventory
T200547 | 2024-07-05 | HIMARS | 6100 | 13511.83 | 0 | Payroll posting for HIMARS | Payroll
T200548 | 2024-01-31 | Javelin | 5400 | 0 | 142027.12 | AP posting for Javelin | AP
T200549 | 2024-10-24 | THAAD | 7200 | 0 | 30190.95 | Journal posting for THAAD | Journal
T200550 | 2024-04-30 | HIMARS | 5400 | 0 | 245005.4 | Journal posting for HIMARS | Journal
T200551 | 2024-02-01 | Javelin | 5300 | 0 | 183179.84 | Journal posting for Javelin | Journal
T200552 | 2024-04-21 | HIMARS | 5300 | 40862.1 | 0 | Inventory posting for HIMARS | Inventory
T200553 | 2024-11-26 | PAC-3 | 6100 | 28581.39 | 0 | Payroll posting for PAC-3 | Payroll
T200554 | 2024-10-15 | THAAD | 5300 | 0 | 129830.75 | Inventory posting for THAAD | Inventory
T200555 | 2024-07-15 | PAC-3 | 6100 | 0 | 79921.63 | Journal posting for PAC-3 | Journal
T200556 | 2024-12-25 | PAC-3 | 7100 | 200693.54 | 0 | AP posting for PAC-3 | AP
T200557 | 2024-05-07 | HIMARS | 6100 | 196698.2 | 0 | Journal posting for HIMARS | Journal
T200558 | 2024-09-02 | THAAD | 6100 | 103526.87 | 0 | Payroll posting for THAAD | Payroll
T200559 | 2024-01-11 | THAAD | 6100 | 0 | 169695.22 | Payroll posting for THAAD | Payroll
T200560 | 2024-08-30 | HIMARS | 7200 | 165373.28 | 0 | Inventory posting for HIMARS | Inventory
T200561 | 2024-12-27 | THAAD | 6200 | 169135.94 | 0 | Payroll posting for THAAD | Payroll
T200562 | 2024-07-30 | Javelin | 6200 | 0 | 192277.8 | Payroll posting for Javelin | Payroll
T200563 | 2024-01-25 | PAC-3 | 5400 | 0 | 140471.99 | Inventory posting for PAC-3 | Inventory
T200564 | 2024-04-21 | PAC-3 | 6200 | 99602.45 | 0 | Payroll posting for PAC-3 | Payroll
T200565 | 2024-07-05 | THAAD | 6100 | 0 | 181493.42 | Payroll posting for THAAD | Payroll
T200566 | 2024-08-19 | Javelin | 5200 | 0 | 131500.54 | Journal posting for Javelin | Journal
T200567 | 2024-03-05 | Javelin | 6100 | 0 | 39103.17 | Payroll posting for Javelin | Payroll
T200568 | 2024-02-18 | HIMARS | 5100 | 0 | 187908.84 | Journal posting for HIMARS | Journal
T200569 | 2024-07-31 | Javelin | 7200 | 16713.71 | 0 | AP posting for Javelin | AP
T200570 | 2024-05-17 | Javelin | 6200 | 0 | 241364.37 | Payroll posting for Javelin | Payroll
T200571 | 2024-10-10 | HIMARS | 6200 | 0 | 10889.45 | Journal posting for HIMARS | Journal
T200572 | 2024-11-17 | THAAD | 6100 | 155991.49 | 0 | Payroll posting for THAAD | Payroll
T200573 | 2024-11-15 | PAC-3 | 5400 | 0 | 110188.98 | AP posting for PAC-3 | AP
T200574 | 2024-08-16 | PAC-3 | 5200 | 27905.63 | 0 | Journal posting for PAC-3 | Journal
T200575 | 2024-09-30 | THAAD | 6100 | 24136.87 | 0 | Payroll posting for THAAD | Payroll
T200576 | 2024-03-20 | PAC-3 | 7100 | 0 | 189580.09 | Journal posting for PAC-3 | Journal
T200577 | 2024-05-06 | THAAD | 5100 | 0 | 229707.98 | AP posting for THAAD | AP
T200578 | 2024-03-25 | THAAD | 5200 | 129091.54 | 0 | AP posting for THAAD | AP
T200579 | 2024-06-01 | HIMARS | 6200 | 148207.77 | 0 | Payroll posting for HIMARS | Payroll
T200580 | 2024-07-14 | Javelin | 5300 | 0 | 172966.33 | Journal posting for Javelin | Journal
T200581 | 2024-08-07 | Javelin | 5300 | 0 | 87836.11 | Journal posting for Javelin | Journal
T200582 | 2024-08-20 | Javelin | 5200 | 0 | 101742.3 | Journal posting for Javelin | Journal
T200583 | 2024-12-28 | THAAD | 6100 | 29399.22 | 0 | Payroll posting for THAAD | Payroll
T200584 | 2024-10-30 | THAAD | 5200 | 0 | 174284 | Inventory posting for THAAD | Inventory
T200585 | 2024-02-16 | PAC-3 | 7200 | 0 | 166633.39 | Inventory posting for PAC-3 | Inventory
T200586 | 2024-04-01 | THAAD | 6100 | 70555.03 | 0 | Payroll posting for THAAD | Payroll
T200587 | 2024-07-10 | PAC-3 | 7100 | 140529.96 | 0 | Inventory posting for PAC-3 | Inventory
T200588 | 2024-09-24 | HIMARS | 7200 | 128190.13 | 0 | Inventory posting for HIMARS | Inventory
T200589 | 2024-10-22 | Javelin | 6100 | 229486.36 | 0 | Payroll posting for Javelin | Payroll
T200590 | 2024-03-17 | PAC-3 | 5400 | 0 | 245494.61 | AP posting for PAC-3 | AP
T200591 | 2024-05-08 | PAC-3 | 7200 | 87528.25 | 0 | AP posting for PAC-3 | AP
T200592 | 2024-11-29 | PAC-3 | 7100 | 238298.13 | 0 | Journal posting for PAC-3 | Journal
T200593 | 2024-04-11 | Javelin | 7100 | 90922.07 | 0 | AP posting for Javelin | AP
T200594 | 2024-03-01 | HIMARS | 6100 | 45177.05 | 0 | Payroll posting for HIMARS | Payroll
T200595 | 2024-06-09 | HIMARS | 6100 | 124728.12 | 0 | Payroll posting for HIMARS | Payroll
T200596 | 2024-07-04 | Javelin | 5100 | 193249.42 | 0 | AP posting for Javelin | AP
T200597 | 2024-10-28 | PAC-3 | 6200 | 38044.34 | 0 | Payroll posting for PAC-3 | Payroll
T200598 | 2024-06-01 | THAAD | 6100 | 201578.33 | 0 | Payroll posting for THAAD | Payroll
T200599 | 2024-08-24 | HIMARS | 6200 | 0 | 160469.77 | Payroll posting for HIMARS | Payroll
T200600 | 2024-05-15 | PAC-3 | 7100 | 0 | 85934.55 | AP posting for PAC-3 | AP
T200601 | 2024-09-11 | PAC-3 | 6100 | 142725.39 | 0 | Payroll posting for PAC-3 | Payroll
T200602 | 2024-01-17 | THAAD | 5200 | 211026.6 | 0 | Inventory posting for THAAD | Inventory
T200603 | 2024-05-04 | HIMARS | 5400 | 0 | 139702.29 | Journal posting for HIMARS | Journal
T200604 | 2024-03-28 | Javelin | 5100 | 114209.15 | 0 | Journal posting for Javelin | Journal
T200605 | 2024-06-16 | HIMARS | 5400 | 0 | 216799.94 | AP posting for HIMARS | AP
T200606 | 2024-11-01 | HIMARS | 5400 | 150273.8 | 0 | AP posting for HIMARS | AP
T200607 | 2024-05-25 | PAC-3 | 7200 | 0 | 50858.76 | Inventory posting for PAC-3 | Inventory
T200608 | 2024-07-29 | PAC-3 | 6200 | 50793.43 | 0 | Payroll posting for PAC-3 | Payroll
T200609 | 2024-03-17 | THAAD | 7100 | 0 | 9870.58 | Inventory posting for THAAD | Inventory
T200610 | 2024-03-28 | HIMARS | 5200 | 82603.42 | 0 | AP posting for HIMARS | AP
T200611 | 2024-06-27 | Javelin | 5400 | 0 | 176977.38 | Journal posting for Javelin | Journal
T200612 | 2024-03-18 | THAAD | 5200 | 76150.68 | 0 | AP posting for THAAD | AP
T200613 | 2024-12-08 | PAC-3 | 5200 | 0 | 66091.32 | AP posting for PAC-3 | AP
T200614 | 2024-05-28 | Javelin | 5300 | 152668.8 | 0 | Inventory posting for Javelin | Inventory
T200615 | 2024-06-14 | Javelin | 7200 | 84249.5 | 0 | AP posting for Javelin | AP
T200616 | 2024-05-18 | THAAD | 7200 | 0 | 12725.98 | AP posting for THAAD | AP
T200617 | 2024-10-17 | HIMARS | 5400 | 0 | 170068.91 | AP posting for HIMARS | AP
T200618 | 2024-03-29 | Javelin | 7100 | 0 | 126011.05 | AP posting for Javelin | AP
T200619 | 2024-07-24 | Javelin | 6100 | 0 | 119457.66 | Payroll posting for Javelin | Payroll
T200620 | 2024-12-01 | Javelin | 6200 | 68204.08 | 0 | Payroll posting for Javelin | Payroll
T200621 | 2024-05-13 | PAC-3 | 5200 | 142427.18 | 0 | Inventory posting for PAC-3 | Inventory
T200622 | 2024-03-15 | THAAD | 6200 | 149648.91 | 0 | Payroll posting for THAAD | Payroll
T200623 | 2024-02-25 | PAC-3 | 5300 | 218853.96 | 0 | AP posting for PAC-3 | AP
T200624 | 2024-08-02 | THAAD | 5200 | 0 | 208959.92 | Inventory posting for THAAD | Inventory
T200625 | 2024-12-19 | PAC-3 | 6100 | 8776.66 | 0 | Payroll posting for PAC-3 | Payroll
T200626 | 2024-10-03 | HIMARS | 6100 | 22047.54 | 0 | Payroll posting for HIMARS | Payroll
T200627 | 2024-11-16 | PAC-3 | 5100 | 218249.27 | 0 | Journal posting for PAC-3 | Journal
T200628 | 2024-02-25 | THAAD | 5400 | 0 | 12453.47 | Journal posting for THAAD | Journal
T200629 | 2024-07-19 | PAC-3 | 5200 | 219692.68 | 0 | Inventory posting for PAC-3 | Inventory
T200630 | 2024-11-04 | Javelin | 5100 | 0 | 248913.59 | Inventory posting for Javelin | Inventory
T200631 | 2024-08-17 | HIMARS | 7200 | 0 | 117215.84 | AP posting for HIMARS | AP
T200632 | 2024-12-30 | HIMARS | 5100 | 9460.3 | 0 | Inventory posting for HIMARS | Inventory
T200633 | 2024-10-08 | Javelin | 5300 | 178555.76 | 0 | Inventory posting for Javelin | Inventory
T200634 | 2024-10-15 | HIMARS | 7200 | 0 | 62236.8 | Inventory posting for HIMARS | Inventory
T200635 | 2024-12-16 | HIMARS | 5400 | 0 | 192840.97 | AP posting for HIMARS | AP
T200636 | 2024-11-29 | Javelin | 5200 | 0 | 117213.58 | Inventory posting for Javelin | Inventory
T200637 | 2024-11-08 | THAAD | 6100 | 239495.43 | 0 | Payroll posting for THAAD | Payroll
T200638 | 2024-05-26 | THAAD | 6100 | 34179.51 | 0 | Payroll posting for THAAD | Payroll
T200639 | 2024-01-25 | PAC-3 | 6100 | 139969.37 | 0 | Journal posting for PAC-3 | Journal
T200640 | 2024-02-24 | PAC-3 | 6200 | 0 | 132844.85 | Journal posting for PAC-3 | Journal
T200641 | 2024-02-03 | PAC-3 | 6100 | 5422.58 | 0 | Payroll posting for PAC-3 | Payroll
T200642 | 2024-10-13 | PAC-3 | 6100 | 0 | 224204.96 | Journal posting for PAC-3 | Journal
T200643 | 2024-09-22 | PAC-3 | 7200 | 221363 | 0 | Journal posting for PAC-3 | Journal
T200644 | 2024-05-22 | HIMARS | 7200 | 0 | 111174.9 | Inventory posting for HIMARS | Inventory
T200645 | 2024-07-14 | PAC-3 | 6100 | 189542.92 | 0 | Payroll posting for PAC-3 | Payroll
T200646 | 2024-09-06 | THAAD | 7100 | 0 | 110243.83 | Journal posting for THAAD | Journal
T200647 | 2024-08-30 | HIMARS | 7200 | 0 | 75802.78 | Journal posting for HIMARS | Journal
T200648 | 2024-11-17 | Javelin | 7100 | 28406.22 | 0 | Inventory posting for Javelin | Inventory
T200649 | 2024-05-18 | HIMARS | 6200 | 181109.5 | 0 | Payroll posting for HIMARS | Payroll
T200650 | 2024-01-07 | PAC-3 | 6100 | 225078.53 | 0 | Journal posting for PAC-3 | Journal
T200651 | 2024-05-03 | THAAD | 6100 | 47099.47 | 0 | Payroll posting for THAAD | Payroll
T200652 | 2024-08-31 | THAAD | 6200 | 50828.92 | 0 | Journal posting for THAAD | Journal
T200653 | 2024-10-23 | HIMARS | 5400 | 237731.58 | 0 | AP posting for HIMARS | AP
T200654 | 2024-06-21 | THAAD | 5200 | 0 | 185769.54 | Inventory posting for THAAD | Inventory
T200655 | 2024-05-20 | PAC-3 | 5100 | 0 | 65081.34 | Journal posting for PAC-3 | Journal
T200656 | 2024-06-23 | Javelin | 7100 | 0 | 20958.62 | Journal posting for Javelin | Journal
T200657 | 2024-11-25 | PAC-3 | 7100 | 0 | 175457.59 | AP posting for PAC-3 | AP
T200658 | 2024-03-31 | THAAD | 6200 | 34941.84 | 0 | Journal posting for THAAD | Journal
T200659 | 2024-09-25 | Javelin | 5300 | 50379.72 | 0 | AP posting for Javelin | AP
T200660 | 2024-06-07 | THAAD | 5100 | 0 | 101811.53 | Inventory posting for THAAD | Inventory
T200661 | 2024-09-23 | Javelin | 6200 | 0 | 233956.96 | Payroll posting for Javelin | Payroll
T200662 | 2024-10-06 | Javelin | 7100 | 0 | 203347.42 | AP posting for Javelin | AP
T200663 | 2024-06-12 | THAAD | 5300 | 216633.42 | 0 | Journal posting for THAAD | Journal
T200664 | 2024-05-31 | THAAD | 6100 | 42339.7 | 0 | Payroll posting for THAAD | Payroll
T200665 | 2024-12-29 | THAAD | 7100 | 63925.45 | 0 | Journal posting for THAAD | Journal
T200666 | 2024-11-29 | Javelin | 6200 | 246960.96 | 0 | Journal posting for Javelin | Journal
T200667 | 2024-07-25 | Javelin | 6200 | 49807.47 | 0 | Payroll posting for Javelin | Payroll
T200668 | 2024-08-15 | PAC-3 | 5200 | 41834.74 | 0 | Inventory posting for PAC-3 | Inventory
T200669 | 2024-11-12 | PAC-3 | 5200 | 116845.38 | 0 | Inventory posting for PAC-3 | Inventory
T200670 | 2024-12-04 | PAC-3 | 5100 | 0 | 68549.09 | Inventory posting for PAC-3 | Inventory
T200671 | 2024-12-06 | HIMARS | 5200 | 0 | 14868.91 | Journal posting for HIMARS | Journal
T200672 | 2024-04-21 | THAAD | 5400 | 236366.26 | 0 | Inventory posting for THAAD | Inventory
T200673 | 2024-09-11 | PAC-3 | 7100 | 0 | 240708.47 | Journal posting for PAC-3 | Journal
T200674 | 2024-04-05 | Javelin | 7200 | 0 | 47220.34 | Journal posting for Javelin | Journal
T200675 | 2024-02-01 | Javelin | 5200 | 197324.8 | 0 | AP posting for Javelin | AP
T200676 | 2024-07-19 | THAAD | 6100 | 0 | 166919.29 | Payroll posting for THAAD | Payroll
T200677 | 2024-10-24 | THAAD | 5100 | 0 | 231593.7 | Inventory posting for THAAD | Inventory
T200678 | 2024-10-23 | Javelin | 6200 | 0 | 195002.17 | Journal posting for Javelin | Journal
T200679 | 2024-11-22 | HIMARS | 5400 | 0 | 128498.36 | Inventory posting for HIMARS | Inventory
T200680 | 2024-02-09 | HIMARS | 5400 | 194481.1 | 0 | AP posting for HIMARS | AP
T200681 | 2024-07-27 | HIMARS | 7200 | 0 | 20453.42 | AP posting for HIMARS | AP
T200682 | 2024-11-26 | Javelin | 5300 | 0 | 14922.67 | AP posting for Javelin | AP
T200683 | 2024-08-25 | HIMARS | 5400 | 0 | 31964.26 | Inventory posting for HIMARS | Inventory
T200684 | 2024-03-20 | THAAD | 5300 | 138476.48 | 0 | AP posting for THAAD | AP
T200685 | 2024-05-29 | THAAD | 5200 | 141457.05 | 0 | Journal posting for THAAD | Journal
T200686 | 2024-11-28 | PAC-3 | 6200 | 160154.46 | 0 | Payroll posting for PAC-3 | Payroll
T200687 | 2024-08-07 | HIMARS | 5300 | 123303.51 | 0 | AP posting for HIMARS | AP
T200688 | 2024-04-21 | HIMARS | 6200 | 116496.97 | 0 | Payroll posting for HIMARS | Payroll
T200689 | 2024-10-12 | Javelin | 5200 | 46871.8 | 0 | AP posting for Javelin | AP
T200690 | 2024-08-29 | PAC-3 | 5100 | 0 | 201921.37 | Journal posting for PAC-3 | Journal
T200691 | 2024-06-18 | HIMARS | 7200 | 0 | 103036.64 | AP posting for HIMARS | AP
T200692 | 2024-07-02 | HIMARS | 5300 | 0 | 239342.04 | Journal posting for HIMARS | Journal
T200693 | 2024-03-05 | THAAD | 6100 | 242967.58 | 0 | Payroll posting for THAAD | Payroll
T200694 | 2024-03-06 | THAAD | 5100 | 160563.66 | 0 | AP posting for THAAD | AP
T200695 | 2024-11-23 | PAC-3 | 6100 | 64621.36 | 0 | Payroll posting for PAC-3 | Payroll
T200696 | 2024-09-28 | PAC-3 | 7100 | 0 | 81433.03 | AP posting for PAC-3 | AP
T200697 | 2024-01-22 | PAC-3 | 6100 | 169324.01 | 0 | Payroll posting for PAC-3 | Payroll
T200698 | 2024-07-06 | HIMARS | 6100 | 0 | 133397.75 | Payroll posting for HIMARS | Payroll
T200699 | 2024-05-22 | PAC-3 | 7100 | 0 | 24726.56 | Inventory posting for PAC-3 | Inventory
T200700 | 2024-06-28 | Javelin | 5300 | 0 | 246703.96 | Journal posting for Javelin | Journal
T200701 | 2024-04-06 | THAAD | 7200 | 63662.82 | 0 | AP posting for THAAD | AP
T200702 | 2024-08-27 | HIMARS | 6200 | 0 | 64887.66 | Payroll posting for HIMARS | Payroll
T200703 | 2024-09-17 | THAAD | 5200 | 0 | 237232.97 | AP posting for THAAD | AP
T200704 | 2024-05-23 | HIMARS | 5200 | 226043.97 | 0 | Inventory posting for HIMARS | Inventory
T200705 | 2024-10-07 | PAC-3 | 5100 | 221894.29 | 0 | AP posting for PAC-3 | AP
T200706 | 2024-05-18 | PAC-3 | 5100 | 211524.28 | 0 | Journal posting for PAC-3 | Journal
T200707 | 2024-04-23 | Javelin | 5200 | 215436.72 | 0 | Inventory posting for Javelin | Inventory
T200708 | 2024-11-18 | PAC-3 | 7100 | 234892.61 | 0 | Inventory posting for PAC-3 | Inventory
T200709 | 2024-06-13 | Javelin | 5300 | 96802.57 | 0 | Inventory posting for Javelin | Inventory
T200710 | 2024-04-25 | THAAD | 5300 | 0 | 93397.67 | AP posting for THAAD | AP
T200711 | 2024-12-06 | PAC-3 | 7100 | 245699.6 | 0 | Inventory posting for PAC-3 | Inventory
T200712 | 2024-04-06 | PAC-3 | 6100 | 149073.42 | 0 | Journal posting for PAC-3 | Journal
T200713 | 2024-02-06 | HIMARS | 6100 | 0 | 230291.92 | Payroll posting for HIMARS | Payroll
T200714 | 2024-05-21 | PAC-3 | 6200 | 212412.41 | 0 | Payroll posting for PAC-3 | Payroll
T200715 | 2024-04-10 | PAC-3 | 7200 | 189859.69 | 0 | Inventory posting for PAC-3 | Inventory
T200716 | 2024-01-04 | PAC-3 | 5100 | 0 | 242248.15 | Inventory posting for PAC-3 | Inventory
T200717 | 2024-09-22 | HIMARS | 6200 | 0 | 113438.23 | Payroll posting for HIMARS | Payroll
T200718 | 2024-09-18 | PAC-3 | 5100 | 0 | 117309.24 | Inventory posting for PAC-3 | Inventory
T200719 | 2024-04-20 | PAC-3 | 6100 | 90082.92 | 0 | Payroll posting for PAC-3 | Payroll
T200720 | 2024-03-11 | Javelin | 5100 | 105820.34 | 0 | AP posting for Javelin | AP
T200721 | 2024-04-21 | HIMARS | 7100 | 213827.09 | 0 | Inventory posting for HIMARS | Inventory
T200722 | 2024-05-06 | Javelin | 5100 | 39470.38 | 0 | Inventory posting for Javelin | Inventory
T200723 | 2024-05-18 | THAAD | 5200 | 0 | 247648.38 | Journal posting for THAAD | Journal
T200724 | 2024-08-11 | PAC-3 | 6200 | 215531.09 | 0 | Payroll posting for PAC-3 | Payroll
T200725 | 2024-05-11 | THAAD | 6100 | 0 | 233168.15 | Journal posting for THAAD | Journal
T200726 | 2024-04-08 | PAC-3 | 7200 | 57225.23 | 0 | Journal posting for PAC-3 | Journal
T200727 | 2024-04-02 | THAAD | 7200 | 30092.1 | 0 | Inventory posting for THAAD | Inventory
T200728 | 2024-07-26 | THAAD | 5100 | 0 | 193144.7 | AP posting for THAAD | AP
T200729 | 2024-10-05 | HIMARS | 6200 | 0 | 130921.8 | Payroll posting for HIMARS | Payroll
T200730 | 2024-04-15 | HIMARS | 6100 | 0 | 170911.57 | Payroll posting for HIMARS | Payroll
T200731 | 2024-11-03 | HIMARS | 5300 | 244347.24 | 0 | AP posting for HIMARS | AP
T200732 | 2024-07-08 | HIMARS | 7100 | 0 | 148951.32 | AP posting for HIMARS | AP
T200733 | 2024-03-16 | THAAD | 6100 | 84739.19 | 0 | Journal posting for THAAD | Journal
T200734 | 2024-11-10 | THAAD | 7100 | 0 | 34360.96 | Inventory posting for THAAD | Inventory
T200735 | 2024-07-25 | HIMARS | 7200 | 0 | 175034.89 | Journal posting for HIMARS | Journal
T200736 | 2024-09-25 | HIMARS | 7100 | 0 | 105201.69 | Journal posting for HIMARS | Journal
T200737 | 2024-05-24 | Javelin | 7100 | 0 | 193260.58 | Inventory posting for Javelin | Inventory
T200738 | 2024-08-01 | HIMARS | 6200 | 0 | 86894.53 | Payroll posting for HIMARS | Payroll
T200739 | 2024-01-13 | Javelin | 7200 | 138838.38 | 0 | Inventory posting for Javelin | Inventory
T200740 | 2024-07-19 | PAC-3 | 6200 | 175887.26 | 0 | Payroll posting for PAC-3 | Payroll
T200741 | 2024-11-29 | THAAD | 5300 | 172713.39 | 0 | Inventory posting for THAAD | Inventory
T200742 | 2024-06-20 | HIMARS | 6100 | 198306.2 | 0 | Payroll posting for HIMARS | Payroll
T200743 | 2024-04-28 | THAAD | 6200 | 136926.61 | 0 | Payroll posting for THAAD | Payroll
T200744 | 2024-12-21 | HIMARS | 6100 | 100598.01 | 0 | Payroll posting for HIMARS | Payroll
T200745 | 2024-09-08 | HIMARS | 7100 | 198974.56 | 0 | Inventory posting for HIMARS | Inventory
T200746 | 2024-11-09 | HIMARS | 5200 | 196029.32 | 0 | Journal posting for HIMARS | Journal
T200747 | 2024-07-21 | PAC-3 | 6200 | 180594.83 | 0 | Payroll posting for PAC-3 | Payroll
T200748 | 2024-07-24 | Javelin | 7100 | 0 | 89634.36 | Journal posting for Javelin | Journal
T200749 | 2024-06-27 | PAC-3 | 6100 | 0 | 101074.28 | Payroll posting for PAC-3 | Payroll
T200750 | 2024-05-12 | PAC-3 | 7200 | 37283.87 | 0 | Inventory posting for PAC-3 | Inventory
T200751 | 2024-02-15 | Javelin | 5200 | 0 | 145357.22 | Inventory posting for Javelin | Inventory
T200752 | 2024-04-11 | THAAD | 6100 | 168804.16 | 0 | Payroll posting for THAAD | Payroll
T200753 | 2024-08-28 | HIMARS | 5200 | 0 | 202877.21 | Journal posting for HIMARS | Journal
T200754 | 2024-05-04 | PAC-3 | 5300 | 0 | 135542.09 | AP posting for PAC-3 | AP
T200755 | 2024-10-28 | HIMARS | 5100 | 224157.7 | 0 | AP posting for HIMARS | AP
T200756 | 2024-09-17 | PAC-3 | 6100 | 28443.12 | 0 | Journal posting for PAC-3 | Journal
T200757 | 2024-06-01 | HIMARS | 7100 | 176150.01 | 0 | AP posting for HIMARS | AP
T200758 | 2024-04-03 | PAC-3 | 6100 | 0 | 31130.49 | Payroll posting for PAC-3 | Payroll
T200759 | 2024-07-03 | THAAD | 7100 | 9524.15 | 0 | Journal posting for THAAD | Journal
T200760 | 2024-09-30 | PAC-3 | 6200 | 110539.73 | 0 | Payroll posting for PAC-3 | Payroll
T200761 | 2024-10-03 | HIMARS | 6200 | 0 | 65693.92 | Payroll posting for HIMARS | Payroll
T200762 | 2024-05-05 | PAC-3 | 5300 | 0 | 30867.76 | Journal posting for PAC-3 | Journal
T200763 | 2024-05-16 | PAC-3 | 6200 | 0 | 134066.72 | Payroll posting for PAC-3 | Payroll
T200764 | 2024-11-21 | PAC-3 | 7200 | 0 | 207613.68 | Inventory posting for PAC-3 | Inventory
T200765 | 2024-11-28 | THAAD | 5100 | 221627.65 | 0 | Journal posting for THAAD | Journal
T200766 | 2024-10-04 | HIMARS | 5300 | 91522.83 | 0 | AP posting for HIMARS | AP
T200767 | 2024-04-04 | HIMARS | 5200 | 0 | 20987.52 | AP posting for HIMARS | AP
T200768 | 2024-07-19 | Javelin | 6100 | 0 | 130980.76 | Payroll posting for Javelin | Payroll
T200769 | 2024-01-28 | Javelin | 6100 | 0 | 185319.14 | Payroll posting for Javelin | Payroll
T200770 | 2024-06-13 | THAAD | 5100 | 147110.67 | 0 | AP posting for THAAD | AP
T200771 | 2024-11-27 | THAAD | 6100 | 136845.14 | 0 | Payroll posting for THAAD | Payroll
T200772 | 2024-02-28 | THAAD | 7100 | 180039.88 | 0 | AP posting for THAAD | AP
T200773 | 2024-06-19 | Javelin | 5400 | 0 | 60207.54 | Journal posting for Javelin | Journal
T200774 | 2024-01-23 | HIMARS | 6100 | 60260.73 | 0 | Payroll posting for HIMARS | Payroll
T200775 | 2024-11-10 | PAC-3 | 5400 | 0 | 22438.32 | Inventory posting for PAC-3 | Inventory
T200776 | 2024-09-19 | Javelin | 7100 | 0 | 89078.21 | AP posting for Javelin | AP
T200777 | 2024-09-26 | Javelin | 5300 | 0 | 20108.22 | Journal posting for Javelin | Journal
T200778 | 2024-06-15 | THAAD | 5400 | 0 | 76928.48 | Inventory posting for THAAD | Inventory
T200779 | 2024-06-04 | HIMARS | 5400 | 0 | 207030.86 | Inventory posting for HIMARS | Inventory
T200780 | 2024-02-18 | THAAD | 7200 | 0 | 37303.74 | Inventory posting for THAAD | Inventory
T200781 | 2024-05-29 | Javelin | 5100 | 201919.96 | 0 | Inventory posting for Javelin | Inventory
T200782 | 2024-11-04 | Javelin | 7100 | 0 | 109786.79 | Journal posting for Javelin | Journal
T200783 | 2024-03-15 | Javelin | 5200 | 0 | 185595.62 | Journal posting for Javelin | Journal
T200784 | 2024-07-02 | PAC-3 | 5100 | 163593.52 | 0 | Journal posting for PAC-3 | Journal
T200785 | 2024-08-12 | THAAD | 6100 | 0 | 94302.74 | Payroll posting for THAAD | Payroll
T200786 | 2024-10-29 | PAC-3 | 5300 | 0 | 180062.72 | Inventory posting for PAC-3 | Inventory
T200787 | 2024-02-10 | THAAD | 7200 | 0 | 128034.38 | Inventory posting for THAAD | Inventory
T200788 | 2024-03-18 | THAAD | 5100 | 216292.3 | 0 | Journal posting for THAAD | Journal
T200789 | 2024-10-04 | HIMARS | 7100 | 0 | 174101.64 | AP posting for HIMARS | AP
T200790 | 2024-08-29 | HIMARS | 7200 | 35403.73 | 0 | AP posting for HIMARS | AP
T200791 | 2024-07-27 | HIMARS | 5200 | 0 | 99163.06 | AP posting for HIMARS | AP
T200792 | 2024-10-22 | THAAD | 6100 | 0 | 10558.28 | Journal posting for THAAD | Journal
T200793 | 2024-04-29 | Javelin | 5100 | 0 | 54065.21 | AP posting for Javelin | AP
T200794 | 2024-05-22 | THAAD | 5200 | 222979.86 | 0 | Inventory posting for THAAD | Inventory
T200795 | 2024-03-16 | HIMARS | 5400 | 0 | 230531.13 | Journal posting for HIMARS | Journal
T200796 | 2024-12-17 | THAAD | 6200 | 0 | 21807.24 | Journal posting for THAAD | Journal
T200797 | 2024-04-02 | Javelin | 7200 | 101662.11 | 0 | Inventory posting for Javelin | Inventory
T200798 | 2024-04-09 | Javelin | 5300 | 164684.75 | 0 | AP posting for Javelin | AP
T200799 | 2024-06-24 | Javelin | 5400 | 0 | 72946.88 | AP posting for Javelin | AP
T200800 | 2024-12-05 | Javelin | 6100 | 0 | 76272.17 | Payroll posting for Javelin | Payroll
T200801 | 2024-05-22 | PAC-3 | 7100 | 169093.38 | 0 | AP posting for PAC-3 | AP
T200802 | 2024-07-23 | THAAD | 7200 | 0 | 227285.94 | Inventory posting for THAAD | Inventory
T200803 | 2024-03-18 | HIMARS | 7100 | 9487.72 | 0 | Inventory posting for HIMARS | Inventory
T200804 | 2024-03-15 | Javelin | 6100 | 0 | 128120.26 | Payroll posting for Javelin | Payroll
T200805 | 2024-06-30 | Javelin | 5300 | 0 | 236158.37 | AP posting for Javelin | AP
T200806 | 2024-11-04 | THAAD | 7200 | 191403.6 | 0 | Journal posting for THAAD | Journal
T200807 | 2024-03-04 | PAC-3 | 7200 | 0 | 221530.02 | AP posting for PAC-3 | AP
T200808 | 2024-03-09 | THAAD | 6100 | 0 | 78654.82 | Payroll posting for THAAD | Payroll
T200809 | 2024-03-08 | THAAD | 6100 | 0 | 86449.69 | Journal posting for THAAD | Journal
T200810 | 2024-04-20 | HIMARS | 5300 | 0 | 203831.88 | AP posting for HIMARS | AP
T200811 | 2024-05-19 | Javelin | 5300 | 30426.57 | 0 | Inventory posting for Javelin | Inventory
T200812 | 2024-09-18 | THAAD | 5300 | 86395.8 | 0 | Journal posting for THAAD | Journal
T200813 | 2024-12-05 | THAAD | 5100 | 56081.15 | 0 | AP posting for THAAD | AP
T200814 | 2024-10-10 | Javelin | 6200 | 138420.16 | 0 | Payroll posting for Javelin | Payroll
T200815 | 2024-06-01 | Javelin | 6200 | 68479.06 | 0 | Journal posting for Javelin | Journal
T200816 | 2024-06-06 | PAC-3 | 5400 | 191396.41 | 0 | Journal posting for PAC-3 | Journal
T200817 | 2024-07-21 | HIMARS | 5100 | 147930.52 | 0 | AP posting for HIMARS | AP
T200818 | 2024-10-25 | HIMARS | 7200 | 0 | 138982.39 | AP posting for HIMARS | AP
T200819 | 2024-10-17 | Javelin | 6200 | 200126.73 | 0 | Payroll posting for Javelin | Payroll
T200820 | 2024-10-04 | PAC-3 | 7100 | 230588.01 | 0 | AP posting for PAC-3 | AP
T200821 | 2024-03-18 | PAC-3 | 5300 | 0 | 67873.57 | Inventory posting for PAC-3 | Inventory
T200822 | 2024-02-02 | THAAD | 5300 | 247703.89 | 0 | Journal posting for THAAD | Journal
T200823 | 2024-08-15 | PAC-3 | 5100 | 0 | 179118.53 | Inventory posting for PAC-3 | Inventory
T200824 | 2024-01-23 | THAAD | 5100 | 176004.13 | 0 | AP posting for THAAD | AP
T200825 | 2024-04-07 | PAC-3 | 6200 | 0 | 29484.54 | Payroll posting for PAC-3 | Payroll
T200826 | 2024-02-11 | PAC-3 | 6200 | 124438.06 | 0 | Payroll posting for PAC-3 | Payroll
T200827 | 2024-03-09 | THAAD | 5300 | 0 | 15111.09 | AP posting for THAAD | AP
T200828 | 2024-08-12 | PAC-3 | 6200 | 99049.36 | 0 | Journal posting for PAC-3 | Journal
T200829 | 2024-08-20 | THAAD | 5300 | 135991.59 | 0 | Journal posting for THAAD | Journal
T200830 | 2024-11-12 | THAAD | 6200 | 173872.22 | 0 | Journal posting for THAAD | Journal
T200831 | 2024-09-13 | Javelin | 5400 | 192659.75 | 0 | Journal posting for Javelin | Journal
T200832 | 2024-08-30 | HIMARS | 7100 | 0 | 17814.91 | Inventory posting for HIMARS | Inventory
T200833 | 2024-03-08 | HIMARS | 7200 | 169326.28 | 0 | Journal posting for HIMARS | Journal
T200834 | 2024-01-01 | THAAD | 6100 | 0 | 94096.48 | Payroll posting for THAAD | Payroll
T200835 | 2024-09-30 | HIMARS | 5200 | 0 | 189557.79 | Inventory posting for HIMARS | Inventory
T200836 | 2024-07-14 | THAAD | 7100 | 155533.22 | 0 | Inventory posting for THAAD | Inventory
T200837 | 2024-05-17 | PAC-3 | 6100 | 15589.67 | 0 | Payroll posting for PAC-3 | Payroll
T200838 | 2024-08-20 | HIMARS | 5100 | 169131.95 | 0 | AP posting for HIMARS | AP
T200839 | 2024-12-15 | HIMARS | 7200 | 0 | 29535.11 | Inventory posting for HIMARS | Inventory
T200840 | 2024-11-18 | Javelin | 6100 | 88971.4 | 0 | Payroll posting for Javelin | Payroll
T200841 | 2024-04-27 | PAC-3 | 6200 | 124665.81 | 0 | Payroll posting for PAC-3 | Payroll
T200842 | 2024-02-01 | PAC-3 | 7100 | 169027.15 | 0 | Inventory posting for PAC-3 | Inventory
T200843 | 2024-08-18 | PAC-3 | 5100 | 0 | 44964.67 | AP posting for PAC-3 | AP
T200844 | 2024-10-11 | Javelin | 6200 | 0 | 107680.75 | Payroll posting for Javelin | Payroll
T200845 | 2024-05-18 | Javelin | 6200 | 0 | 187337.64 | Payroll posting for Javelin | Payroll
T200846 | 2024-03-26 | Javelin | 5400 | 0 | 107359.12 | AP posting for Javelin | AP
T200847 | 2024-09-21 | Javelin | 6100 | 144416.41 | 0 | Payroll posting for Javelin | Payroll
T200848 | 2024-02-27 | HIMARS | 6200 | 51866.83 | 0 | Payroll posting for HIMARS | Payroll
T200849 | 2024-12-27 | Javelin | 7100 | 215213.35 | 0 | Journal posting for Javelin | Journal
T200850 | 2024-12-18 | PAC-3 | 7200 | 228228.26 | 0 | Inventory posting for PAC-3 | Inventory
T200851 | 2024-03-11 | Javelin | 7200 | 11733.87 | 0 | AP posting for Javelin | AP
T200852 | 2024-01-14 | Javelin | 5200 | 0 | 179113.48 | Journal posting for Javelin | Journal
T200853 | 2024-11-29 | THAAD | 5300 | 173663.23 | 0 | AP posting for THAAD | AP
T200854 | 2024-06-14 | HIMARS | 5200 | 96512.92 | 0 | Journal posting for HIMARS | Journal
T200855 | 2024-11-30 | THAAD | 6100 | 0 | 96499.8 | Payroll posting for THAAD | Payroll
T200856 | 2024-05-21 | THAAD | 5100 | 152115.85 | 0 | AP posting for THAAD | AP
T200857 | 2024-12-30 | Javelin | 6200 | 134651.57 | 0 | Journal posting for Javelin | Journal
T200858 | 2024-02-14 | Javelin | 6100 | 43946.45 | 0 | Payroll posting for Javelin | Payroll
T200859 | 2024-03-23 | HIMARS | 6100 | 197598.28 | 0 | Payroll posting for HIMARS | Payroll
T200860 | 2024-11-19 | HIMARS | 5200 | 180007.9 | 0 | Inventory posting for HIMARS | Inventory
T200861 | 2024-08-26 | HIMARS | 5400 | 142105.66 | 0 | Journal posting for HIMARS | Journal
T200862 | 2024-10-01 | HIMARS | 5400 | 72909.43 | 0 | Journal posting for HIMARS | Journal
T200863 | 2024-09-11 | HIMARS | 5200 | 0 | 57458.48 | AP posting for HIMARS | AP
T200864 | 2024-10-03 | PAC-3 | 6200 | 74559.76 | 0 | Payroll posting for PAC-3 | Payroll
T200865 | 2024-11-08 | THAAD | 5300 | 0 | 205436.9 | AP posting for THAAD | AP
T200866 | 2024-03-27 | HIMARS | 6200 | 0 | 161040.25 | Payroll posting for HIMARS | Payroll
T200867 | 2024-06-07 | PAC-3 | 5300 | 0 | 43547.74 | AP posting for PAC-3 | AP
T200868 | 2024-12-06 | PAC-3 | 5300 | 138873.25 | 0 | Journal posting for PAC-3 | Journal
T200869 | 2024-08-28 | PAC-3 | 5200 | 0 | 133996.33 | AP posting for PAC-3 | AP
T200870 | 2024-01-31 | HIMARS | 5400 | 0 | 69743.67 | Journal posting for HIMARS | Journal
T200871 | 2024-03-02 | HIMARS | 5100 | 240002.4 | 0 | AP posting for HIMARS | AP
T200872 | 2024-12-05 | HIMARS | 7200 | 0 | 90471.21 | Inventory posting for HIMARS | Inventory
T200873 | 2024-10-17 | PAC-3 | 7200 | 140593.98 | 0 | Journal posting for PAC-3 | Journal
T200874 | 2024-07-30 | HIMARS | 5200 | 0 | 240627.62 | Inventory posting for HIMARS | Inventory
T200875 | 2024-01-16 | Javelin | 7100 | 0 | 248529.44 | AP posting for Javelin | AP
T200876 | 2024-10-15 | PAC-3 | 7100 | 43185.79 | 0 | Journal posting for PAC-3 | Journal
T200877 | 2024-04-30 | HIMARS | 6200 | 200810.64 | 0 | Payroll posting for HIMARS | Payroll
T200878 | 2024-12-20 | HIMARS | 6100 | 0 | 53188.18 | Payroll posting for HIMARS | Payroll
T200879 | 2024-06-22 | THAAD | 6200 | 196832.15 | 0 | Payroll posting for THAAD | Payroll
T200880 | 2024-10-08 | THAAD | 5400 | 0 | 168893.15 | Journal posting for THAAD | Journal
T200881 | 2024-05-12 | HIMARS | 6200 | 160977.05 | 0 | Payroll posting for HIMARS | Payroll
T200882 | 2024-09-26 | Javelin | 6100 | 62292.85 | 0 | Payroll posting for Javelin | Payroll
T200883 | 2024-01-20 | Javelin | 6200 | 0 | 93726.45 | Journal posting for Javelin | Journal
T200884 | 2024-05-31 | THAAD | 6100 | 0 | 104735.82 | Payroll posting for THAAD | Payroll
T200885 | 2024-01-10 | PAC-3 | 5200 | 155748.79 | 0 | AP posting for PAC-3 | AP
T200886 | 2024-10-15 | PAC-3 | 6200 | 0 | 186812.69 | Payroll posting for PAC-3 | Payroll
T200887 | 2024-03-27 | Javelin | 5100 | 0 | 89369.89 | AP posting for Javelin | AP
T200888 | 2024-01-04 | Javelin | 5300 | 212455.29 | 0 | AP posting for Javelin | AP
T200889 | 2024-10-11 | HIMARS | 7200 | 240980.42 | 0 | Inventory posting for HIMARS | Inventory
T200890 | 2024-06-01 | PAC-3 | 5400 | 60938.44 | 0 | Inventory posting for PAC-3 | Inventory
T200891 | 2024-08-27 | THAAD | 6200 | 213338.88 | 0 | Payroll posting for THAAD | Payroll
T200892 | 2024-08-12 | THAAD | 5300 | 44758.8 | 0 | Inventory posting for THAAD | Inventory
T200893 | 2024-05-11 | THAAD | 5400 | 10301.63 | 0 | AP posting for THAAD | AP
T200894 | 2024-03-15 | HIMARS | 5400 | 0 | 196770.25 | AP posting for HIMARS | AP
T200895 | 2024-10-18 | THAAD | 5300 | 0 | 60622.8 | Journal posting for THAAD | Journal
T200896 | 2024-04-11 | PAC-3 | 5400 | 244176.66 | 0 | AP posting for PAC-3 | AP
T200897 | 2024-01-25 | Javelin | 7100 | 0 | 148635.62 | AP posting for Javelin | AP
T200898 | 2024-07-12 | Javelin | 6100 | 13117.7 | 0 | Payroll posting for Javelin | Payroll
T200899 | 2024-12-14 | PAC-3 | 5200 | 101447.54 | 0 | Inventory posting for PAC-3 | Inventory
T200900 | 2024-05-21 | PAC-3 | 5200 | 0 | 60783.22 | AP posting for PAC-3 | AP

## Program_Forecasts
As_Of_Date | Program | Month | Original_Budget | Current_EAC | Cumulative_Actuals | Cumulative_Variance
2024-01-05 | THAAD | 2024-01-01 | 4826420.08 | 4967881.2 | 5317416.84 | 345458.84
2024-02-05 | THAAD | 2024-02-01 | 5152087.16 | 5261418.62 | 10289453.19 | 73669.19
2024-03-05 | THAAD | 2024-03-01 | 5088712.32 | 5505039.12 | 15268229.26 | -107379.74
2024-04-05 | THAAD | 2024-04-01 | 5224470.34 | 5261162.85 | 20933785.13 | 157677.13
2024-05-05 | THAAD | 2024-05-01 | 5232078.53 | 5385919.79 | 26174990.04 | -145889.96
2024-06-05 | THAAD | 2024-06-01 | 5378836.06 | 4992425.9 | 31484177.71 | -56202.29
2024-07-05 | THAAD | 2024-07-01 | 5101934.17 | 5287309.78 | 36510003.2 | -71.8
2024-08-05 | THAAD | 2024-08-01 | 5339250.83 | 5407116.88 | 41846260.73 | -6147.27
2024-09-05 | THAAD | 2024-09-01 | 5626335.29 | 5952523.1 | 47131493.04 | -2430066.96
2024-10-05 | THAAD | 2024-10-01 | 5341219.33 | 5360961.4 | 52679542.04 | -2370867.96
2024-11-05 | THAAD | 2024-11-01 | 5496722.59 | 5619056.01 | 58371297.1 | -3250647.9
2024-12-05 | THAAD | 2024-12-01 | 5565788.67 | 5547576.73 | 64353580.61 | -1724779.39
2024-01-05 | Javelin | 2024-01-01 | 3531482.01 | 3686814.46 | 3681620.42 | 50019.42
2024-02-05 | Javelin | 2024-02-01 | 3731882.78 | 3965536.19 | 7687456.42 | 373784.42
2024-03-05 | Javelin | 2024-03-01 | 3715290.47 | 3771924.37 | 11654858.84 | 725363.84
2024-04-05 | Javelin | 2024-04-01 | 3576956.06 | 3393527.84 | 15078241.68 | 1096653.68
2024-05-05 | Javelin | 2024-05-01 | 3410675.26 | 3751929.46 | 18809654.35 | 1243419.35
2024-06-05 | Javelin | 2024-06-01 | 3818384.57 | 3916209.02 | 22500193.57 | 181537.57
2024-07-05 | Javelin | 2024-07-01 | 3550829.55 | 3769745.04 | 26462977.24 | 1200089.24
2024-08-05 | Javelin | 2024-08-01 | 3711919.78 | 3843450.42 | 30004238.71 | 249238.71
2024-09-05 | Javelin | 2024-09-01 | 3614239.86 | 3741455.6 | 33938616.9 | 711894.9
2024-10-05 | Javelin | 2024-10-01 | 3722287.11 | 4147921.6 | 38036969.93 | 342089.93
2024-11-05 | Javelin | 2024-11-01 | 4098164.67 | 4187770.95 | 42235508.12 | -1735517.88
2024-12-05 | Javelin | 2024-12-01 | 3975655.5 | 4236055.49 | 46576618.48 | -1520689.52
2024-01-05 | PAC-3 | 2024-01-01 | 4215782.44 | 4449400.78 | 4478167.19 | 269829.19
2024-02-05 | PAC-3 | 2024-02-01 | 4213809.55 | 4306580.95 | 8477370.04 | 111406.04
2024-03-05 | PAC-3 | 2024-03-01 | 4243425.28 | 3989042.65 | 12494200.57 | 21943.57
2024-04-05 | PAC-3 | 2024-04-01 | 4394148.4 | 4437632.59 | 16924988 | -207248
2024-05-05 | PAC-3 | 2024-05-01 | 4483021.01 | 4622133.13 | 21397065.23 | -707844.77
2024-06-05 | PAC-3 | 2024-06-01 | 4256534.44 | 4291994.38 | 25888515.09 | 67005.09
2024-07-05 | PAC-3 | 2024-07-01 | 4612911.78 | 4925832.89 | 30333759.47 | -1483389.53
2024-08-05 | PAC-3 | 2024-08-01 | 4738684.87 | 4649540.47 | 34819227.29 | -2238764.71
2024-09-05 | PAC-3 | 2024-09-01 | 4599533.15 | 4764193.05 | 39294490.06 | -1629877.94
2024-10-05 | PAC-3 | 2024-10-01 | 4389271.32 | 4438790.85 | 43758306.15 | -1071853.85
2024-11-05 | PAC-3 | 2024-11-01 | 4731009.53 | 4726850.76 | 48749298.89 | -3345513.11
2024-12-05 | PAC-3 | 2024-12-01 | 4524277.33 | 4908865.4 | 53449602.74 | -1427441.26
2024-01-05 | HIMARS | 2024-01-01 | 4609408.83 | 4803706.06 | 5131873.62 | 442520.62
2024-02-05 | HIMARS | 2024-02-01 | 4889555.63 | 4712176.76 | 9862384.11 | 332040.11
2024-03-05 | HIMARS | 2024-03-01 | 4891345.59 | 4742974.17 | 14515819.36 | -60757.64
2024-04-05 | HIMARS | 2024-04-01 | 5161893.69 | 5157683.47 | 19830454.04 | -375249.96
2024-05-05 | HIMARS | 2024-05-01 | 5033892.08 | 5471258.64 | 24761384.97 | -235520.03
2024-06-05 | HIMARS | 2024-06-01 | 5207153.8 | 5438005.96 | 30303733.4 | -761182.6
2024-07-05 | HIMARS | 2024-07-01 | 5010552.16 | 4802166.53 | 35483430.67 | 294115.67
2024-08-05 | HIMARS | 2024-08-01 | 5162771.04 | 4808341.87 | 40443931.5 | -133684.5
2024-09-05 | HIMARS | 2024-09-01 | 5208508.7 | 5133280.94 | 45345956.66 | -972966.34
2024-10-05 | HIMARS | 2024-10-01 | 5329369.68 | 5501772.34 | 50376388.8 | -1783441.2
2024-11-05 | HIMARS | 2024-11-01 | 5354266.88 | 5363782.65 | 56210272.2 | -2636273.8
2024-12-05 | HIMARS | 2024-12-01 | 5211943.84 | 5453440.34 | 61598643.98 | -1104404.02

## KPI (hidden)
Total Spend | Total Budget | Variance | Variance %
225978445.81 | 221594332 | 4384113.81 | 1.978%
Total Spend
$225,978,445.81
Total Budget
$221,594,332.00
Variance
$4,384,113.81
Variance %
2%

## Revenue vs Actual Cost (hidden)
Row Labels | Actual Cost | Revenue
Jan | 18609078.07 | 19228427.44
Feb | 17707585.69 | 18778003.73
Mar | 17616444.27 | 19065304.49
Apr | 18834360.82 | 19396325.1
May | 18375625.74 | 19570942.35
Jun | 19033525.18 | 20135872.92
Jul | 18613550.81 | 19801444.65
Aug | 18323487.65 | 20665766.19
Sep | 18596898.43 | 20621341.15
Oct | 19140650.26 | 20088528.89
Nov | 20715169.39 | 20902693.34
Dec | 20412069.5 | 20360683.11
Grand Total | 225978445.81 | 238615333.36
|  |  | Margin $ | 12636887.55 | Margin % | 5.296%
Margin ($) $12,636,887.55
Margin (%)
5%

## Cumulative Spend vs Budget (hidden)
Row Labels | Actual Spend (Cumulative) | Budget (Cumulative)
Jan | 18609078.07 | 17501250
Feb | 36316663.76 | 35214132
Mar | 53933108.03 | 52998778
Apr | 72767468.85 | 71022687
May | 91143094.59 | 89220473
Jun | 110176619.77 | 107678050
Jul | 128790170.58 | 126075111
Aug | 147113658.23 | 144730488
Sep | 165710556.66 | 163622885
Oct | 184851206.92 | 182596413
Nov | 205566376.31 | 202281352
Dec | 225978445.81 | 221594332
Grand Total

## Budget vs Actual Cost (hidden)
Row Labels | Budget | Actual Cost
HIMARS | 60578394 | 61598643.98
Javelin | 44455202 | 46576618.48
PAC-3 | 53073068 | 53449602.74
THAAD | 63487668 | 64353580.61
Grand Total | 221594332 | 225978445.81
This shape represents a slicer. Slicers are supported in Excel 2010 or later. If the shape was modified in an earlier version of Excel, or if the workbook was saved in Excel 2003 or earlier, the slicer cannot be used.

## Sheet7 (hidden)
Total Material Spend
3385598274.4
PO Count
1100
|  |  |  | Avg Unit Price | Max of Delivery_Date | Max of Order_Date
|  |  |  | 3077816.6131 | 2025-02-08 | 2024-12-30
| Row Labels | Total Spend
| Propulsion | 495369601.57
| Guidance | 531298829.32
| Warhead | 554578485.78
| Hardware | 557324665.01
| Composites | 616716657.99
| Electronics | 630310034.73
| Grand Total | 3385598274.4
|  | Row Labels | Total Spend
|  | AeroDynamics Ltd | 730970161.9
|  | Precision Metals Inc | 729526196.41
|  | DefenseCo Supplies | 668326237.52
|  | RayTech Components | 655347872.59
|  | Orbital Systems | 601427805.98
|  | Grand Total | 3385598274.4
[7 empty] | Row Labels | PO Spend
PO100527
[7 empty] | DefenseCo Supplies | 10820143.4
PO100305
[7 empty] | Orbital Systems | 11001066.48
PO100190
[7 empty] | AeroDynamics Ltd | 11019952.16
PO100415
[7 empty] | Precision Metals Inc | 11195974.01
PO100151
[7 empty] | AeroDynamics Ltd | 11267668.44
PO100764
[7 empty] | AeroDynamics Ltd | 11345382.5
PO100390
[7 empty] | RayTech Components | 11361177.49
PO100883
[7 empty] | Orbital Systems | 11374962.3
PO100788
[7 empty] | AeroDynamics Ltd | 11461405.68
PO100382
[7 empty] | Orbital Systems | 11940076.8
[7 empty] | Grand Total | 112787809.26
Total Material Spend
$3,385,598,274.40
PO Count
1100
Avg Unit Price
$3,077,816.61

## Sheet9 (hidden)
Total Labor Cost
2357961.71
OT Hours
796
|  |  |  | Row Labels | Labor Cost
|  |  |  | HIMARS | 626800.95
|  |  |  | Javelin | 610398.04
|  |  |  | PAC-3 | 562148.51
| Total Hours |  |  | THAAD | 558614.21
| 28976 |  |  | Grand Total | 2357961.71
| Row Labels | Sum of OT_Hours
| Jan | 51
| Feb | 50
| Mar | 92
| Apr | 60
| May | 57
| Jun | 47
| Jul | 64
| Aug | 71
| Sep | 87
| Oct | 58
| Nov | 60
| Dec | 99
| Grand Total | 796
[6 empty] | Row Labels | Total Hours
[6 empty] | Engineering | 7489
[6 empty] | Manufacturing | 7055
[6 empty] | Program Control | 6870
[6 empty] | Test | 7562
[6 empty] | Grand Total | 28976
Total Labor Cost
$2,357,961.71
Total Hours
28976
OT Hours
796

## Program_Lookup (hidden)
Programs
THAAD
Javelin
PAC-3
HIMARS